## IEEE_Cover
January 2023 |  | IEEE 802.15.6ma
IEEE P802.15
Wireless Speciality Networks
Project | IEEE P802.15 Working Group for Wireless Speciality Networks (WSNs)
Title | Progess report of 802.15.6ma TOC
Date Submitted | January 19th, 2023
Source | Marco Hernandez1,3, Ryuji Kohno1,2, Takumi Kobayashi1,2, Minsoo Kim1
1YRP-IAI, Japan; 2YNU, Japan. 3CWC Oulu Univ. Finland
Re: | In response to Call for Proposals.
Purpose | Material for discussion.
Notice | This document has been prepared to assist the IEEE P802.15.6ma. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.6ma.

## TOC
Progress on the Revised Table of Contents
IEEE 802.15.6-2012 Std |  | IEEE 802.15.6ma revision | Status | Notes
Contents | Page | Contents
1. Overview | 1 | 1. Overview | TBD | The text requires revision to reflect the new changes.
1.1 Scope | 1 | 1.1 Scope | TBD | The text requires revision to reflect the new changes.
1.2 Purpose | 1 | 1.2 Purpose | TBD | The text requires revision to reflect the new changes.
2. Normative references | 2 | 2. Normative references | Done | No new change.
3. Definitions, acronyms, and abbreviations | 2 | 3. Definitions, acronyms, and abbreviations
3.1 Definitions | 2 | 3.1 Definitions | TBD | The text requires revision to reflect the new changes.
3.2 Special terms | 7 | 3.2 Special terms | TBD | The text requires revision to reflect the new changes.
3.3 Acronyms and abbreviations | 7 | 3.3 Acronyms and abbreviations | TBD | The text requires revision to reflect the new changes.
4. General framework elements | 10 | 4. General framework elements
4.1 General | 10 | 4.1 General | Done | No new change.
4.2 Network topology | 10 | 4.2 Network topology | TBD | The text requires revision to reflect the new changes.
4.3 Reference model | 11 | 4.3 Reference model | Done | No new change.
4.4 Time base | 12 | 4.4 Time base | TBD | The text requires revision to reflect the new changes.
4.5 MAC and security state diagrams | 12 | 4.5 MAC and security state diagrams | Done | No new change.
4.6 Security paradigm | 15 | 4.6 Security paradigm | Done | No new change.
5. MAC frame formats | 16 | 5. MAC frame formats
5.1 Conventions | 16 | 5.1 Conventions | TBD | The text requires revision to reflect the new changes.
5.2 General format | 17 | 5.2 General format | TBD | The text requires revision to reflect the new changes.
5.3 Management type frames | 27 | 5.3 Management type frames | TBD | The text requires revision to reflect the new changes.
5.4 Control type frames | 55 | 5.4 Control type frames | TBD | The text requires revision to reflect the new changes.
5.5 Data type frames | 60 | 5.5 Data type frames | TBD | The text requires revision to reflect the new changes.
5.6 MAC/PHY Capability fields | 61 | 5.6 MAC/PHY Capability fields | TBD | The text requires revision to reflect the new changes.
5.7 Information elements | 65 | 5.7 Information elements | TBD | The text requires revision to reflect the new changes.
6. MAC functions | 77 | 6. MAC functions
6.1 General | 77 | 6.1 General | TBD | The text requires revision to reflect the new changes.
6.2 Frame processing | 78 | 6.2 Frame processing | TBD | The text requires revision to reflect the new changes.
6.3 Access classification and division | 88 | 6.3 Access classification and division | TBD | The text requires revision to reflect the new changes.
6.4 BAN creation/operation and node connection/disconnection | 90 | 6.4 BAN creation/operation and node connection/disconnection | TBD | The text requires revision to reflect the new changes.
6.5 Random access | 92 | 6.5 Random access | TBD | The text requires revision to reflect the new changes.
6.6 Improvised access and unscheduled access | 98 | 6.6 Improvised access and unscheduled access | TBD | The text requires revision to reflect the new changes.
6.7 Scheduled access and scheduled-polling access | 107 | 6.7 Scheduled access and scheduled-polling access | TBD | The text requires revision to reflect the new changes.
6.8 Access continuation, termination, and timeout | 110 | 6.8 Access continuation, termination, and timeout | TBD | The text requires revision to reflect the new changes.
6.9 MICS band communication | 116 | 6.9 MICS band communication | TBD | The text requires revision to reflect the new changes.
6.10 Two-hop star topology extension | 121 | 6.10 Two-hop star topology extension | TBD | The text requires revision to reflect the new changes.
6.11 Clock synchronization and guard time provisioning | 132 | 6.11 Clock synchronization and guard time provisioning | TBD | The text requires revision to reflect the new changes.
6.12 Power management | 140 | 6.12 Power management | TBD | The text requires revision to reflect the new changes.
6.13 Coexistence and interference mitigation | 142 | 6.13 Coexistence and interference mitigation | TBD | The text requires revision to reflect the new changes.
6.14 MAC/PHY capability handling/interaction and Application Specific IE usage | 147 | 6.14 MAC/PHY capability handling/interaction and Application Specific IE usage | TBD | The text requires revision to reflect the new changes.
6.15 MAC sublayer parameters | 148 | 6.15 MAC sublayer parameters | TBD | The text requires revision to reflect the new changes.
7. Security services | 151 | 7. Security services | Done | No new change.
7.1 Security association and disassociation | 151 | 7.1 Security association and disassociation | Done | No new change.
7.2 PTK creation and GTK distribution | 163 | 7.2 PTK creation and GTK distribution | Done | No new change.
7.3 Message security | 165 | 7.3 Message security | Done | No new change.
7.4 Optional cipher functions | 172 | 7.4 Optional cipher functions | Done | No new change.
8. Narrowband PHY specification | 172 | 8. Narrowband PHY specification | Done | No new change.
8.1 Data-rate-dependent parameters | 173 | 8.1 Data-rate-dependent parameters | Done | No new change.
8.2 PLCP preamble | 176 | 8.2 PLCP preamble | Done | No new change.
8.3 PLCP header | 178 | 8.3 PLCP header | Done | No new change.
8.4 PSDU | 181 | 8.4 PSDU | Done | No new change.
8.5 Constellation mapping | 185 | 8.5 Constellation mapping | Done | No new change.
8.6 General requirements | 187 | 8.6 General requirements | Done | No new change.
8.7 PHY layer timing | 188 | 8.7 PHY layer timing | Done | No new change.
8.8 Transmitter specifications | 190 | 8.8 Transmitter specifications | Done | No new change.
8.9 Receiver specifications | 194 | 8.9 Receiver specifications | Done | No new change.
9. Ultra wideband PHY specification | 196 | 9. Ultra wideband PHY specification | TBD | The text requires revision to reflect the new changes.
9.1 Definition of hubs and devices | 196 | 9.1 Definition of hubs and devices | TBD | The text requires revision to reflect the new changes.
9.2 Modes of operation | 197 | 9.2 Modes of operation | TBD | The text requires revision to reflect the new changes.
9.3 Rules for use of modes and options | 197 | 9.3 Rules for use of modes and options | TBD | The text requires revision to reflect the new changes.
9.4 Pulse shape option | 198 | 9.4 Pulse shape option | TBD | The text requires revision to reflect the new changes.
9.5 UWB PHY frame format | 198 | 9.5 UWB PHY frame format | TBD | The text requires revision to reflect the new changes.
9.6 PSDU construction | 198 | 9.6 PSDU construction | TBD | The text requires revision to reflect the new changes.
9.7 PHR construction | 201 | 9.7 PHR construction | TBD | The text requires revision to reflect the new changes.
9.8 Synchronization header | 204 | 9.8 Synchronization header | TBD | The text requires revision to reflect the new changes.
9.9 IR-UWB symbol structure | 206 | 9.9 IR-UWB symbol structure | TBD | The text requires revision to reflect the new changes.
9.10 UWB modulations | 209 | 9.10 UWB modulations | TBD | The text requires revision to reflect the new changes.
9.11 IR-UWB PSDU timing parameters | 215 | 9.11 IR-UWB PSDU timing parameters | TBD | The text requires revision to reflect the new changes.
9.12 Operating frequency bands | 217 | 9.12 Operating frequency bands | TBD | The text requires revision to reflect the new changes.
9.13 Transmit spectral mask | 218 | 9.13 Transmit spectral mask | TBD | The text requires revision to reflect the new changes.
9.14 IR-UWB pulse shapes | 219 | 9.14 IR-UWB pulse shapes | TBD | The text requires revision to reflect the new changes.
9.15 Type II hybrid ARQ mechanism | 224 | 9.15 Type II hybrid ARQ mechanism | TBD | The text requires revision to reflect the new changes.
9.16 FM-UWB | 228 | 9.16 FM-UWB | TBD | The text requires revision to reflect the new changes.
9.17 General UWB PHY requirements | 231 | 9.17 General UWB PHY requirements | TBD | The text requires revision to reflect the new changes.
9.18 General radio specifications | 232 | 9.18 General radio specifications | TBD | The text requires revision to reflect the new changes.
10. Human body communications PHY specification | 235 | 10. Human body communications PHY specification | TBD | Under consideration to be removed
10.1 General | 235 | 10.1 General | TBD | Under consideration to be removed
10.2 HBC packet structure | 235 | 10.2 HBC packet structure | TBD | Under consideration to be removed
10.3 HBC transmitter | 236 | 10.3 HBC transmitter | TBD | Under consideration to be removed
10.4 PLCP Preamble | 237 | 10.4 PLCP Preamble | TBD | Under consideration to be removed
10.5 Start frame delimiter and rate indicator | 239 | 10.5 Start frame delimiter and rate indicator | TBD | Under consideration to be removed
10.6 PHY Header | 242 | 10.6 PHY Header | TBD | Under consideration to be removed
10.7 PSDU | 244 | 10.7 PSDU | TBD | Under consideration to be removed
10.8 Transmitter specifications | 247 | 10.8 Transmitter specifications | TBD | Under consideration to be removed
10.9 Receiver specifications | 248 | 10.9 Receiver specifications | TBD | Under consideration to be removed
10.10 General requirements | 248 | 10.10 General requirements | TBD | Under consideration to be removed
10.11 PHY layer timing | 249 | 10.11 PHY layer timing | TBD | Under consideration to be removed
Annex A (informative) Bibliography | 250 | Annex A (informative) Bibliography | TBD | The text requires revision to reflect the new changes.
Annex B (informative) Coexistence applicability guide | 251 | Annex B (informative) Coexistence applicability guide | TBD | The text requires revision to reflect the new changes.
Annex C (informative) Ultra wideband | 252 | Annex C (informative) Ultra wideband | TBD | The text requires revision to reflect the new changes.
Annex D (informative) Features of human body communication | 256 | Annex D (informative) Features of human body communication | TBD | Under consideration to be removed