## IEEE_Cover
March 2023 |  | DCN 15-23-0114-02-007a
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | Comment Resolution for 802.15 Letter Ballot 1st Recirculation
Date Submitted | March 07 2023
Source | Huy Nguyen (Kookmin University) | Voice: n/a
| Yeong Min Jang (Kookmin University) | E-mail: ngochuy.hust@gmail.com, yjang@kookmin.ac.kr
| Sang-Kyu Lim (ETRI) | sklim@etri.re.kr
| Sangsung Choi (Kookmin University) | sschoi@kookmin.ac.kr
Re:
Abstract | Comment resolution for Letter Ballot #195
Purpose | [This document is used to submit comments for an 802.15 Letter Ballot.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
INSTRUCTIONS: Please use this form to enter your comments. When complete please submit with your vote as described in the Letter Ballot Notification Name / Affiliation - These fields are required. Email / Phone # - please enter a valid email address and contact telephone number. The editors may use these to contact you if there are questions relating to your comment. This information will NOT be made public. Page/Sub-clause/Line Number - If you wish to reference multiple pages, provide the details in the comment field. Please specify Table / Figure References in the comment field in addition to the Page and Line Number. Comment/Proposed Change - These fields are required. Enter your comment and proposed change in these fields, respectively. Use plain text characters only. If you use any characters entered with "Ctrl" or "Alt" keys; or if you use symbols of any kind, if may result in an error which invalidates the comment. E/T -Only one letter is allowed, either E or T. Enter E if comment is editorial or T if comment is technical. Must be Satisfied? - This field is required. Enter Yes or No and spell out completely. If you vote "No" (Disapprove), the data will be associated with your "No" (Disapprove) vote. This categorization is used to differentiate those comments submitted as part of your "No" (Disapprove) vote from other comments that you may wish to submit. Only those comments that have a "Yes" in the "Must be Satisfied" box will be considered as part of your negative vote.
CID | Name | Affiliation | Email | Phone # | Page | Sub-clause | Line # | Comment | Proposed Change | E/T | Must Be Satisfied? (enter Yes or No) | Status | Resolution
1 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 18 | 8.2 | 1 | In Table 79a, the FECs for RS-OFDM are Hamming code (8,4) and RS(15,11). The sub-clause 16.1.4 describes that Hamming (8,4) or Reed Solomon(15,11) code may be used. However, Hamming (15,11) for Mode1 and RS(15,11) for Mode 2 are shown in Table 151a. So, Which one is correct ? | If Hamming (8,4) for Mode 1 and RS (15,11) for Mode 2 are correct, then change Hamming (15,11) for Mode 1 to Hamming (8,4) in Table 151a. If Hamming (15,11) for Mode 1 and RS (15,11) for Mode 2 are correct, then the FECs for RS-OFDM specified in Table 79a and 16.1.4 should be changed to Hamming code (15,11) and RS (15,11) | T | Yes | accepted | Updated table 79a and 151a based on Document DCN 15-23-0113-01-007a
2 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 18 | 8.2 | 1 | In Table 79a, the optical clock rates for MIMO C-OOK are 10kHz, 20kHz, 30kHz, and 40kHz. In Table 115 on page 23, the optical clock rates are 20kHz and 40kHz. The optical clock rates described in 16.2.2 are 8kHz or 10kHz. The optical clock rates shown in Table 151c are 20kHz and 40kHz. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 115, 16.2.2 and Table 151c with respect to optical clock rates for MIMO C-OOK. | T | Yes | accepted | Updated table 79a, 115, and 151c based on Document DCN 15-23-0113-01-007a
3 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 18 | 8.2 | 1 | The blank for RLL of MIMO C-OOK is shown in Table 79a. | Put "Manchester" in the blank for the consistency with Table 151c. | T | Yes | accepted | Updated table 79a based on Document DCN 15-23-0113-01-007a
4 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 18 | 8.2 | 1 | According to 16.1.5, three QAM levels, 4-QAM, 16-QAM, and 64-QAM, can be used for RS-OFDM modulation scheme. If so, the data rates corresponding to each QAM level should be shown in Table 79a. | Add the data rates corresponding to each QAM level to RS-OFDM in Table 79a. | T | Yes | accepted | Updated table 79a based on Document DCN 15-23-0113-01-007a
5 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 18 | 8.2 | 1 | In Table 79a, the optical clock rates for MIMO OOK are 1.5kHz, 2kHz, and 2.5kHz. In Table 115 on page 24, the optical clock rates are 2kHz and 3kHz. The optical clock rates described in 16.4.2 on page 31 are 20Hz or 30Hz. The optical clock rates shown in Table 151f are 1.5kHz, 2kHz, and 3kHz. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 115, 16.4.2 and Table 151f with respect to optical clock rates for MIMO OOK. | T | Yes | accepted | Updated table 115 and sub-clause 16.4.2 based on Document DCN 15-23-0113-01-007a
6 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 23 | 9.5.2 | 1 | phyOfdmFec in Table 115 | If Hamming (8,4) for Mode 1 and RS (15,11) for Mode 2 are correct, then delete "2: FEC: Hamming (15,11)" in Table 115. If Hamming (15,11) for Mode 1 and RS (15,11) for Mode 2 are correct, then delete "1: FEC: Hamming (8,4)" in Table 115. | T | Yes | accepted | Updated table 115 based on Document DCN 15-23-0113-01-007a
7 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 23 | 9.5.2 | 1 | With regard to "phyOfdmFrame" in Table 115, according to Table 151a, OFDM symbol lengths for Mode 1 and Mode 2 are 64 bits and 128 bits, respectively. However, 32 bits and 64 bits are shown here in Table 115. So, which one is correct ? | Keep the technical consistency between Table 115 and Table 151a with respect to OFDM symbol length | T | Yes | accepted | Updated table 115 and table 151a based on Document DCN 15-23-0113-01-007a
8 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 23 | 9.5.2 | 1 | In Table 79a, the optical clock rates for MIMO C-OOK are 10kHz, 20kHz, 30kHz, and 40kHz. In Table 115 on page 23, the optical clock rates are 20kHz and 40kHz. The optical clock rates described in 16.2.2 are 8kHz or 10kHz. The optical clock rates shown in Table 151c are 20kHz and 40kHz. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 115, 16.2.2 and Table 151c with respect to optical clock rates for MIMO C-OOK. | T | Yes | accepted | Updated table 115 and sub-clause 16.2.2 based on Document DCN 15-23-0113-01-007a
9 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 23 | 9.5.2 | 1 | Accoding to Table 151c, data sub-packet lengths are specified. However, the PHY PIB attribute for data sub-packet length of MIMO C-OOK is not shown in Table 115. | Add the PHY PIB attribute for data sub-packet length of MIMO C-OOK to Table 115 | T | Yes | accepted | Updated table 115 and sub-clause 16.2.7 based on Document DCN 15-23-0113-01-007a
10 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 24 | 9.5.2 | 1 | Accoding to Table 151d, data sub-packet lengths are specified. However, the PHY PIB attribute for data sub-packet length of O-NOMA is not shwon in Table 115. | Add the PHY PIB attribute for data sub-packet length of O-NOMA to Table 115 | T | Yes | accepted | Updated table 115 and sub-clause 16.2.7 based on Document DCN 15-23-0113-01-007a
11 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 24 | 9.5.2 | 1 | In Table 79a and Table 151c, MIMO C-OOK has Mode 1, Mode 2, Mode 3, and Mode 4. However, only Mode 1 and Mode 2 are shown in Table 115. | If MIMO C-OOK has Mode 1, Mode 2, Mode 3, and Mode 4, then specify Mode 3 and Mode 4 for MIMO C-OOK in Table 115. | T | Yes | accepted | Updated table 115 based on Document DCN 15-23-0113-01-007a
12 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 24 | 9.5.2 | 15 | In Table 79a, 16.3.3, and Table 151d, the FECs for O-NOMA are Hamming code (8,4) and RS(15,11). However, In Table 115, the FECs for O-NOMA are Hamming code (8,4), Hamming (15,11) and RS(15,11). | If the specifications on FECs for O-NOMA shown in the Table 79a, 16.3.3 and Table 151d are correct, then delete "Hamming (15,11)" in Table 115. | T | Yes | accepted | Updated table 115 based on Document DCN 15-23-0113-01-007a
13 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 24 | 9.5.2 | 1 | In Table 79a, the optical clock rates for MIMO OOK are 1.5kHz, 2kHz, and 2.5kHz. In Table 115 on page 24, the optical clock rates are 2kHz and 3kHz. The optical clock rates described in 16.4.2 on page 31 are 20Hz or 30Hz. The optical clock rates shown in Table 151f are 1.5kHz, 2kHz, and 3kHz. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 115, 16.4.2 and Table 151f with respect to optical clock rates for MIMO OOK. | T | Yes | accepted | Updated table 115, table 79a, and sub-clause 16.4.2 based on Document DCN 15-23-0113-01-007a
14 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 25 | 9.5.2 | 1 | In Table 79a and Table 151f, MIMO OOK has Mode 1, Mode 2, and Mode 3. However, only Mode 1 and Mode 2 are shown in Table 115 on page 25. | If MIMO OOK has Mode 1, Mode 2, and Mode 3, then specify Mode 3 for MIMO OOK in Table 115. | T | Yes | accepted | Updated table 115 based on Document DCN 15-23-0113-01-007a
15 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 25 | 9.5.2 | 1 | Accoding to Table 151f, data sub-packet lengths for MIMO OOK are specified. However, the PHY PIB attribute for data sub-packet length of MIMO OOK is not shown in Table 115. | Add the PHY PIB attribute for data sub-packet length of MIMO OOK to Table 115 | T | Yes | accepted | Updated table 115 based on Document DCN 15-23-0113-01-007a
16 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 26 | 16.1.2 | 9 | The title of 16.1.2 is "Encoder configuration". By the way, the sentences shown in the subclause mainly describe the optical clock rates for RS-OFDM. | Change the title of this subclause from "Encoder configuration" to "Optical clock rate". | T | Yes | revised | revised sub-clause 16.1.2 with more detail about encoder configuration (data rate, data sub-packet structure, etc.) "A packet of data is modulated using OFDM modulation. RS-OFDM data packet structure is illustrated in Figure 216b. The optical clock rate is at 20 kHz or 40 kHz. The optical clock rate at which RS-OFDM symbols are clocked out is configurable over PHY PIB attribute phyOfdmOpticalClockRate. The data packet structure is shown in Figure 216b. A data sub-packet shall consist of two subfields: a sequence number part and a payload part. "
17 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 26 | 16.1.2 | 14 | Figure 216b has something to do with 16.1.3 rather than 16.1.2. | Move the Figure 216b from 16.1.2 to 16.1.3. | T | Yes | accepted | Moved Figure 216b from sub-clause 16.1.2 to 16.1.3
18 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 27 | 16.1.3 | 1 | Lettering style in the title of the subclause 16.1.3 | Change "Sequence Number inserting" to "Sequence number inserting" to keep the editorial consistency. | E | No | accepted | Changed "Sequence Number inserting" to "Sequence number inserting"
19 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 27 | 16.1.4 | 6 | In Table 79a, the FECs for RS-OFDM are Hamming code (8,4) and RS(15,11). The sub-clause 16.1.4 describes that Hamming (8,4) or Reed Solomon(15,11) code may be used. However, Hamming (15,11) for Mode1 and RS(15,11) for Mode 2 are shown in Table 151a. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 151a and 16.1.4 with respect to FECs for RS-OFDM. | T | Yes | accepted | Deleted Hamming (15,11) in table 115.
20 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 27 | 16.1.6 | 1 | Lettering style in the title of the subclause 16.1.6 | Change "Hermitian Mapping" to "Hermitial mapping" to keep the editorial consistency. | E | No | accepted | Changed title of 16.1.6 "Hermitian Mapping" to "Hermitial mapping"
21 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 27 | 16.1.6 | 19 | "RS-OFDM frame length" is shown on this line. "OFDM symbol length" is shown in Table 151a. Are those the same ? | If they are the same, then use the same terminology. | T | Yes | accepted | changed "OFDM symbol length" to "RS-OFDM frame length" in table 151a
22 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 27 | 16.1.6 | 19 | How does Hermitian Mapping described in 16.1.6 relate to "phyOfdmmode" and "phyOfdmFrame" shown on this line ? | If Hermitian Mapping has nothing to do with "phyOfdmmode" and "phyOfdmFrame", then delete the sentences from line #19 to line #20. | T | Yes | accepted | delete the sentences "The modes of RS-OFDM shall be configured via the PHY PIB attribute phyOfdmMode. And RS-OFDM frame length shall be configured via the PHY PIB attribute phyOfdmFrame."
23 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 27 | 16.1.7 | 24 | According to 16.1.5, three QAM levels, 4-QAM, 16-QAM, and 64-QAM, can be used for RS-OFDM modulation scheme. If so, the data rates corresponding to each QAM level should be shown in Table 151a. | Add the data rates corresponding to each QAM level to RS-OFDM in Table 151a. | T | Yes | accepted | Updated table 79a based on Document DCN 15-23-0113-01-007a
24 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 27 | 16.1.7 | 24 | In Table 79a, the FECs for RS-OFDM are Hamming code (8,4) and RS(15,11). The sub-clause 16.1.4 describes that Hamming (8,4) or Reed Solomon(15,11) code may be used. However, Hamming (15,11) for Mode1 and RS(15,11) for Mode 2 are shown in Table 151a. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 151a and 16.1.4 with respect to FECs for RS-OFDM. | T | Yes | accepted | Deleted Hamming (15,11) in table 115.
25 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 27 | 16.1 |  | The sub-clause describing OFDM frame length or OFDM symbol length is not shown. | Add a subclause describing OFDM frame length or OFDM symbol length to 16.1. | T | Yes | revised | Rewrited content in 16.1.2 to "A packet of data is modulated using OFDM modulation. RS-OFDM data packet structure is illustrated in Figure 216b. The optical clock rate is at 20 kHz or 40 kHz. The optical clock rate at which RS-OFDM symbols are clocked out is configurable over PHY PIB attribute phyOfdmOpticalClockRate. The data packet structure is shown in Figure 216b. A data sub-packet shall consist of two subfields: a sequence number part and a payload part. RS-OFDM frame length shall be configured via the PHY PIB attribute phyOfdmFrame."
26 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 28 | 16.2.2 | 4 | In Table 79a, the optical clock rates for MIMO C-OOK are 10kHz, 20kHz, 30kHz, and 40kHz. In Table 115 on page 23, the optical clock rates are 20kHz and 40kHz. The optical clock rates described in 16.2.2 are 8kHz or 10kHz. The optical clock rates shown in Table 151c are 20kHz and 40kHz. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 115, 16.2.2 and Table 151c with respect to optical clock rates for MIMO C-OOK. | T | Yes | accepted | Updated table 115, table 79a, and sub-clause 16.2.2 based on Document DCN 15-23-0113-01-007a
27 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 28 | 16.2.2 | 3 | 16.2.2 consists of three parts mainly describing optical clock rates, data packet structure, and preamble. And also, "Encoder" in the title of 16.2.2 is confused in "RLL encoder in Figure 216c. | 1. Change the title of 16.2.2 from "Encoder configuration" to "Optical clock rate". 2. Move the second paragraph except the last sentence describing "preamble" and Figure 216d from 16.2.2 to 16.2.4. 3. Move the last sentence of the second paragraph describing "preambe" from 16.2.2 to 16.2.6. | T | Yes | accepted | Updated subclauses 16.2.2, 16.2.4 and 16.2.6 based on Document DCN 15-23-0113-01-007a
28 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 28 | 16.2.3 | 15 | In Table 79a, Table 115, and Table 151c, the FECs for MIMO C-OOK are Hamming code (8,4), Hamming (15,11) and RS(15,11). However, the sub-clause 16.2.3 describes that Hamming (8,4) or Reed Solomon(15,11) code may be used. | If the specifications on FECs for MIMO C-OOK shown in the Tables are correct, then add "Hamming (15,11)" to 16.2.3. | T | Yes | accepted | inserted Hamming(15, 11) in 16.2.3
29 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 28 | 16.2.4 | 18 | Lettering style in the title of the subclause 16.2.4 | Change "Sequence Number inserting" to "Sequence number inserting" to keep the editorial consistency. | E | No | accepted | updated title of sub-clause 16.2.4 "Sequence Number inserting" to "Sequence number inserting"
30 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 29 | 16.2.5 | 1 | The title of 16.2.5 is "RLL coding". However, all of the sentences in 16.2.5 are the same as 16.2.4 and they have nothing to do with RLL coding. | Rewrite the sentences in 16.2.5. | T | Yes | accepted | rewrited content in 16.2.5: "RLL coding shall be applied in the payload subfield to maintain an average brightness at 50%. Manchester code and 4B6B code are suggested for OOK mode. The configuration of RLL code shall be implemented over the PHY PIB attribute phyMimoCookRLLCode. Manchester code or 4B6B code is suggested for MIMO C-OOK mode."
31 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 29 | 16.2.7 | 12 | In Table 79a, the optical clock rates for MIMO C-OOK are 10kHz, 20kHz, 30kHz, and 40kHz. In Table 115 on page 23, the optical clock rates are 20kHz and 40kHz. The optical clock rates described in 16.2.2 are 8kHz or 10kHz. The optical clock rates shown in Table 151c are 20kHz and 40kHz. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 115, 16.2.2 and Table 151c with respect to optical clock rates for MIMO C-OOK. | T | Yes | accepted | Updated table 115, table 79a, and 151c based on Document DCN 15-23-0113-01-007a
32 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 29 | 16.2 |  | The sub-clause describing "Data sub-packet length" is not shown. | Add a subclause describing "Data sub-packet length" to 16.2. | T | Yes | revised | Rewrite content in 16.2.2 as follow "The data packet structure is shown in Figure 216d. A data sub-packet shall consist of four subfields: LED-ID part, a sequence number part, a forward payload, and a backward payload part. A packet consists of multiple similar data sub-packets to avoid missing data between adjacent images. The number of repetitions depends on the communication mode specified later. The data sub-packet format of MIMO C-OOK is illustrated in Table 151b. The data sub-packet length of MIMO C-OOK shall be configured via the PHY PIB attribute phyMimoCookSubPacketLength."
33 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 30 | 16.3.2 | 1 | In Table 79a, Table 115, and Table 151d, the optical clock rates for O-NOMA are 2kHz and 4kHz. However, the sub- The optical clock rates shown in 16.3.2 are 10kHz or 20kHz. So, Which one is correct ? | If the specifications on the optical clock rates for O-NOMA shown in the Tables are correct, then change the optical clock rates shown in 16.3.2 from "10 kHz or 20 kHz" to "2 kHz or 4 kHz". | T | Yes | accepted | Updated sub-clause 16.3.2: "A packet of data is modulated using O-NOMA modulation. The optical clock rate is at 2 kHz or 4 kHz. The optical clock rate at which O-NOMA symbols are clocked out is configurable over PHY PIB attribute phyNomaOpticalClockRate."
34 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 31 | 16.4.2 | 3 | 16.2.2 consists of two parts mainly describing optical clock rates and data packet structure rather than encoder configuration. | 1. Change the title of 16.2.2 from "Encoder configuration" to "Optical clock rate". 2. Move the sentences describing "data packet structure" including Figure 216h and Table 151e from 16.4.2 to 16.4.4. | T | Yes | revised | 1: Revise title of16.4.2 from "Encoder configuration" to "Data packet structure" 2: Move the second sentence from 16.4.2 to 16.4.7
35 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 31 | 16.4.2 | 4 | In Table 79a, the optical clock rates for MIMO OOK are 1.5kHz, 2kHz, and 2.5kHz. In Table 115 on page 24, the optical clock rates are 2kHz and 3kHz. The optical clock rates described in 16.4.2 on page 31 are 20Hz or 30Hz. The optical clock rates shown in Table 151f are 1.5kHz, 2kHz, and 3kHz. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 115, 16.4.2 and Table 151f with respect to optical clock rates for MIMO OOK. | T | Yes | accepted | Updated sub-clause 16.4.2: "A packet of data is modulated using OOK modulation. The optical clock rate is at 1.5 kHz, 2 kHz, or 2.5 Hz."
36 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 32 | 16.4.5 | 6 | According to Table 79a, Table 115, and Table 151f, Manchester, 4B6B, and 8B10B code can be used for MIMO OOK. However, 8B10B is not found in 16.4.5. | Add "8B10B code" to 16.4.5. | T | Yes | accepted | Updated sub-clause 16.4.5: "Manchester code, 4B6B, or 8B10B code is suggested for MIMO-OOK mode."
37 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 32 | 16.4.7 | 19 | In Table 79a, the optical clock rates for MIMO OOK are 1.5kHz, 2kHz, and 2.5kHz. In Table 115 on page 24, the optical clock rates are 2kHz and 3kHz. The optical clock rates described in 16.4.2 on page 31 are 20Hz or 30Hz. The optical clock rates shown in Table 151f are 1.5kHz, 2kHz, and 3kHz. So, Which one is correct ? | Keep the technical consistency between Table 79a, Table 115, 16.4.2 and Table 151f with respect to optical clock rates for MIMO OOK. | T | Yes | accepted | Updated table 115, table 79a, and sub-clause 16.4.2 based on Document DCN 15-23-0113-01-007a
38 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 32 | 16.4.7 | 19 | From the Table 115 on page 25 and Table 151e on page 31, the preambles for MIMO OOK are 6 bits, 10 bits, and 14 bits. However, the preambles shown in Table 151f are 6 bits and 10 bits. | If the preambles for MIMO OOK shown in Table 115 and 151e are correct, then change the preamble for Mode 3 from "6 bits" to "14 bits". | T | Yes | accepted | Updated table 151f based on Document DCN 15-23-0113-01-007a
39 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 32 | 16.5 | 20 | No line space between Table 151f and the title of 16.5 | Insert a line space between Table 151f and the title of 16.5. | E | No | accepted | inserted more space between Table 151f and title of 16.5
40 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 32 | 16.5.1 | 24 | "Right LED array" is shown in Figure 216i. Here, what is "Right" in "Right LED array" ? Do you mean one is "Right LED array" and the other one is "Left LED array" ? | If my estimation is correct, then one of two "Right LED array" should be changed to "Left LED array". | T | Yes | accepted | revised figrue 216i based on Document DCN 15-23-0113-01-007a
41 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 34 | 16.5.3.3 | 16 | "Right LED array" is shown in Figure 216n. Here, what is "Right" in "Right LED array" ? Do you mean one is "Right LED array" and the other one is "Left LED array" ? | If my estimation is correct, then one of two "Right LED array" should be changed to "Left LED array". | T | Yes | accepted | revised figrue 216i based on Document DCN 15-23-0113-01-007a
42 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 41 | O.3 | 2 | No line space between Figure caption of Figure O.11 and Figure O.12. | Insert a line space. | E | No | accepted | Insert a line space between Figure O.11 and O.12
43 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 41 | O.4 | 13 | No line space between the first paragraph and Figure O.13. | Insert a line space. | E | No | accepted | Insert a line space between the first paragraph and Figure O.13.
44 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 42 | O.5 | 9 | No line space between the first paragraph and Figure O.16. | Insert a line space. | E | No | accepted | Insert a line space between the first paragraph and Figure O.16.
45 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 43 | O.7 | 9 | No line space between the first paragraph and Figure O.18. | Insert a line space. | E | No | accepted | Insert a line space between the first paragraph and Figure O.18
46 | Sang-Kyu Lim | ETRI | sklim@etri.re.kr |  | 44 | P.1 | 13 | No line space between Figure P.1 and the second paragraph | Insert a line space. | E | No | accepted | Insert a line space between Figure P.1 and paragraph
Note on J40: SAMSUNG: check later