## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [Timeline of TG15.6ma]
Date Submitted: [15th March 2023]
Source: [Ryuji Kohno1,2, Marco Hernandez3] [1;Yokohama National University, 2;YRP International Alliance Institute(YRP-IAI), 3: CWC, University of Oulu]
Address [1; 79-5 Tokiwadai, Hodogaya-ku, Yokohama, 240-8501 Japan
2; YRP1 Blg., 3-4 HikarinoOka, Yokosuka-City, Kanagawa, 239-0847 Japan
3: CWC, University of Oulu, Oulu, Finalnd]
Voice:[1; +81-90-5408-0611], FAX: [+81-45-383-5528],
Email:[1: kohno@ynu.ac.jp, 2: kohno@yrp-iai.jp, 3: marco.Hernandez@ieee.org] Re: []
Abstract: [This document contains timeline of TG15.6ma for Revision of P802.15.6-2012 with Enhanced Dependability.
Purpose: [information]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Timeline of IEEE 802.15 TG6ma (Revision of IEEE802.15.6-2012) Atlanta, GA, USA March 16th, 2023 Ryuji Kohno1,2, Marco Hernandez2,3 1: Yokohama National University(YNU), Japan 2: YRP International Alliance Institute(YRP-IAI) 3: Centre for Wireless Communications(CWC), University of Oulu, Finland

## Slide 3
TG 6ma Timeline
Tech Req Doc July 2022
Chan Mod Doc. Call Proposals Sept 2022
Harmon Proposals March 2023
1st Submission date of draft proposals and Specification Framework Doc January 2023
2nd Submissionuedate of priposals and drafting March 2023
Integrated Draft Proposal
Draft0 May 2023
1st Letter Ballot Sept 2023
Comment Resolution 1st recir Nov 2023
SA ballot
Jan. 2024
Revcom July 2024
SA Recirculation Mar 2024
RevcomConditional Approval
May 2024
Notes: SASB/RevCom scheduled for 2024 a guess

## Slide 4
Note: the deadlines are subject to change.
Timeline details.

## Slide 5: Project Schedule (working baseline)
Proposed project schedule |  | May-22 | Jun-22 | Jul -22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov24 | Dec 24 |  |  |  |  | 
Technical Requirement Document(TRD) Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Start Call for Proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1st Submission Due Data for Proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Extended 2nd Submission Due Date for Proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Integrate proposals/contributions with Performance Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop draft integrated standard satisfying TRD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
draft 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TG draft review and resion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG pre-ballot review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-ballot review and comment resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First letter Ballot(1st LB) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LB comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG Recirculatoin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 1st recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, first SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SA Resirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, SA recirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conditional or unconditional approval to RevCom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Optional 2nd SA recirc if needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RevCom meets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | `
You are Here
Notes: SASB/RevCom scheduled for 2024 a guess

## Slide 6
Thank You !
Any Questions ?