## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [Timeline of TG15.6ma]
Date Submitted: [15th March 2023]
Source: [Ryuji Kohno1,2, Marco Hernandez3] [1;Yokohama National University, 2;YRP International Alliance Institute(YRP-IAI), 3: CWC, University of Oulu]
Address [1; 79-5 Tokiwadai, Hodogaya-ku, Yokohama, 240-8501 Japan
2; YRP1 Blg., 3-4 HikarinoOka, Yokosuka-City, Kanagawa, 239-0847 Japan
3: CWC, University of Oulu, Oulu, Finalnd]
Voice:[1; +81-90-5408-0611], FAX: [+81-45-383-5528],
Email:[1: kohno@ynu.ac.jp, 2: kohno@yrp-iai.jp, 3: marco.Hernandez@ieee.org] Re: []
Abstract: [This document contains timeline of TG15.6ma for Revision of P802.15.6-2012 with Enhanced Dependability.
Purpose: [information]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Timeline of IEEE 802.15 TG6ma (Revision of IEEE802.15.6-2012) Atlanta, GA, USA March 16th, 2023 Ryuji Kohno1,2, Marco Hernandez2,3 1: Yokohama National University(YNU), Japan 2: YRP International Alliance Institute(YRP-IAI) 3: Centre for Wireless Communications(CWC), University of Oulu, Finland

## Slide 3
TG 6ma Timeline
Tech Req Doc(TRD) July 2022
TRD,CMD
Call Proposals Sept 2022
Presentation of proposalsNov2022 Jan.2023
Harmonization of Proposals
Mar 2023
Std Draft V0
May 2023
Finish integration of technical proposals. Draft v1
July2023
WG pre-ballot
Sept 2023
Comments and resolution for pre-ballot.
Nov 2023
WG letter ballot (LB)
Jan. 2024
Revcom Approve
Jul 2024
SB recirculation if required
Jun 2024
RevcomSubmission
June 2024
Notes: SASB/RevCom scheduled for 2024 a guess
EC approval to SB, SB submission
Mar 2024
SB recirculation
May 2024

## Slide 4
Note: the deadlines are subject to change.
Timeline details.
Topic | Deadline | Notes
Technical Requirements Document (TRD). Channel Model Document (CMD). Call for Proposals. | Sept. 2022 | TRD describes the technical requirements baseline for the evaluation of proposals. The CMD contains the channel models for different use cases targeted by the Std. Announcement of call for proposals.
Due day for proposals | March 10th, 2023 | Postponed from January 2023
Presentation of proposals | Nov. 2022, January, March 2023 | Start of discussions for harmonization of proposals.
Harmonization of Proposals | March 2023 | Agreements on key technologies.
Std Draft v.0 | May 2023 | Mostly editorial revisions and start integrating text of agreed proposals.
Std Draft v. 1 | July 2023 | Finish integration of technical proposals.
Std Draft v. 1 recirculation | August 2023 | TG approval
WG pre-ballot | September 2023 | WG pre-ballot submission.
Comments and resolution for pre-ballot. | November 2023 | Finish resolutions to pre-ballot comments and recirculation.
WG letter ballot (LB) | January 2024 | LB submission
LB recirculation | January 2024 | Comment-resolutions to LB recirculation
Conditional approval for Sponsor Ballot (SB) | January 2024 | Seek conditional approval
Final LB recirculation. EC approval | March 2024 | Just before the March meeting.
EC approval to SB | March 2024 | 
SB submission | March 2024 | 
SB recirculation | May 2024 | Resolutions to SB.
Conditional/unconditional approval to RevCom | May 2024 | Submission to SASB agenda
SB recirculation if required | June 2024 | 
RevCom submission | June 2024 | RevCom approval

## Slide 5: Project Schedule (working baseline)
Proposed project schedule |  | May-22 | Jun-22 | Jul -22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov24 | Dec 24 |  |  |  |  | 
Technical Requirement Document(TRD) Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Start Call for Proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1st Submission Due Data for Proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Extended 2nd Submission Due Date for Proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Integrate proposals/contributions with Performance Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop draft integrated standard satisfying TRD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Draft v0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TG draft review and resion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Finish integration of technical proposals drsft v1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-ballot review and comment resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comments and resolution for pre-ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG Letter Ballot (LB) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LB recirculation Conditional approval for Sponsor Ballot (SB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final LB recirculation. EC approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
iEC approval to SB SB submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SB recirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conditional/unconditional approval to RevCom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SB recirculation if required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Revcom submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RevCom meets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | `
You are Here
Notes: SASB/RevCom scheduled for 2024 a guess

## Slide 6
Thank You !
Any Questions ?