## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: Licensed Narrowband Amendment TG16t March Closing Report
Date Submitted: 2023-03-16
Source: Tim Godfrey, EPRI
Abstract: Closing Report
Purpose: Closing Report
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: TG16t March Plenary Agenda
Introductions, Secretary, Review and Approve Agenda
Policy Review
Presentation and Review of Contributions for Draft
Adjourn

## Slide 3: Meeting Plan for week
Tuesday PM1 1:30pm EDT
Wednesday PM1 1:30pm EDT
Thursday AM2 10:30am EDT
Thursday PM1 1:30pm EDT

## Slide 4: Contributions for March 2023 Plenary
08-Mar-2023 ET | 2023 | 118 | 0 | TG16t (Lic-NB) | P802.15.16t D0.4 Review | Vishal Kalkundrikar (Ondas)
14-Mar-2023 ET | 2023 | 163 | 0 | TG16t (Lic-NB) | Response to DPP Comments | Menashe Shahar | 14-Mar-2023 11:50:01 ET | Download, Revise
14-Mar-2023 ET | 2023 | 159 | 0 | TG16t (Lic-NB) | SEM12.5kHzMaskJ | Ondas | 14-Mar-2023 08:46:31 ET | Download, Revise
14-Mar-2023 ET | 2023 | 158 | 0 | TG16t (Lic-NB) | Cyber Security changes | Ondas | 14-Mar-2023 08:27:22 ET | Download, Revise
14-Mar-2023 ET | 2022 | 643 | 5 | TG16t (Lic-NB) | Direct Peer to Peer | Vishal Kalkundrikar (Ondas) | 15Mar-2023 08:07:27 ET | Download, Revise

## Slide 5: March Progress
Review Document 118r0.
Review Document 163.
Review document 158
Review document 159
Review document 643r3, 4, 5

## Slide 6: Draft Review Plan
Plan for draft review
  Harry to adopt and incorporate 643r5 except for DPP Mode 2 TDD
  Doc 158 revision on Cyber Security – follow up document to be submitted by Yael from Ondas. March 21
  Complete Draft 0.8 Harry to provide to TG by March 27
  Teleconference with Task Group to review of D0.8 Wednesday April 5 8am PT
  Any changes from review to become draft D0.9
  Initiate WG Comment Collection on Draft 0.9 Monday April 17
  Review comments – May Interim
  May Interim - Motion for WG Letter Ballot on D1.0 – starting 2 weeks after May Interim
Initiate Plan to include broader set of stakeholders (from first meeting of TG16t) in Letter Ballot to receive comments. Request access from WG Chair.

## Slide 7: Project Timeline
Milestone | Date
Task Group Start | Jan 2020
SRD Approval | April 2021
SDD Approval | Jan 2022
Draft Development | 
Informal TG review of draft | Mar 2023
Working Group Letter Ballot | May 2023
Working Group Recirculation Letter Ballot | Sep 2023
SA Ballot | Nov 2023
Forward to RevCom | Mar 2024
PAR Expiration Date: 31 Dec 2024
If needed, request PAR extension July 2024

## Slide 8: Plans
Teleconference April 5, 8am PT
4 Meeting slots in May, same days and times as March
At May interim, Review and resolve comments from comment collection on D0.9