## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: Licensed Narrowband Amendment TG16t April Teleconference Presentation
Date Submitted: 2023-04-05
Source: Tim Godfrey, EPRI
Abstract: Meeting Agenda and Presentation
Purpose: Chair’s presentation for task group meeting
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Opening
Introductions
Secretary for meeting
Agenda review and Approval

## Slide 3: Contributions for April Teleconference
05-Apr-2023 ET | 2022 | 643 | 6 | TG16t (Lic-NB) | Direct Peer to Peer | Vishal Kalkundrikar (Ondas) | 05-Apr-2023 09:23:48 ET | Download, Revise
01-Apr-2023 ET | 2023 | 201 | 0 | TG16t (Lic-NB) | ieee802.16t Security Modifications | Yael (Ondas) | 01-Apr-2023 19:16:17 ET | Download, Revise
22-Mar-2023 ET | 2023 | 193 | 0 | TG16t (Lic-NB) | Security modifications | Yael (Ondas) | 22-Mar-2023 12:48:18 ET | Download, Revise
Latest Draft P802.16t_D0.8.pdf 2023-03-30 18:30 2.7M

## Slide 4: Review from March
Plan for draft review
  Harry to adopt and incorporate 643r5 except for DPP Mode 2 TDD
  Doc 158 revision on Cyber Security – follow up document to be submitted by Yael from Ondas. March 21
  Complete Draft 0.8 Harry to provide to TG by March 27
  Teleconference with Task Group to review of D0.8 Wednesday April 5 - 8am PT
  Any changes from review to become draft D0.9
  Initiate WG Comment Collection on Draft 0.9 Monday April 17
  Review comments – May Interim
  May Interim - Motion for WG Letter Ballot on D1.0 – starting 2 weeks after May Interim
Initiate Plan to include broader set of stakeholders (from first meeting of TG16t) in Letter Ballot to receive comments. Request access from WG Chair.

## Slide 5: Discussion

## Slide 6: Project Timeline
Milestone | Date
Task Group Start | Jan 2020
SRD Approval | April 2021
SDD Approval | Jan 2022
Draft Development | 
Informal TG review of draft | Mar 2023
Working Group Letter Ballot | May 2023
Working Group Recirculation Letter Ballot | Sep 2023
SA Ballot | Nov 2023
Forward to RevCom | Mar 2024
PAR Expiration Date: 31 Dec 2024
If needed, request PAR extension July 2024

## Slide 7: Future Meetings
May 2023 Wireless Interim
  May 15-18, 2023 Orlando, FL, USA
July 2023 Plenary
  July 10-13, 2023 Berlin, Germany
Sept 2023 Wireless Interim
  Sept 11-14, 2023 Atlanta, GA

## Slide 8: Closing
Any Other Business
Actions
Adjourn