## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: Licensed Narrowband Amendment TG16t April 25th Teleconference Presentation
Date Submitted: 2023-04-25
Source: Tim Godfrey, EPRI
Abstract: Meeting Agenda and Presentation
Purpose: Chair’s presentation for task group meeting
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Opening
Introductions
Secretary for meeting
Agenda review and Approval
  Review Draft D0.9
  Review contributions
  Initiate WG Comment Collection

## Slide 3: Contributions for April 25 Teleconference
Latest Draft P802.16t_D0.9.pdf 2023-03-30 18:30 2.7M
25-Apr-2023 ET | 2023 | 209 | 0 | TG16t (Lic-NB) | 0.8 comments | Juha Juntunen (MCC) | 25-Apr-2023 00:11:01 ET | Download, Revise
18-Apr-2023 ET | 2022 | 643 | 7 | TG16t (Lic-NB) | Direct Peer to Peer | Vishal Kalkundrikar (Ondas) | 18-Apr-2023 09:15:02 ET | Download, Revise
25-Apr-2023 ET | 2023 | 212 | 0 | TG16t (Lic-NB) | P802.15.16t D0.9 Review | Vishal Kalkundrikar (Ondas) | 25-Apr-2023 10:04:16 ET | 

## Slide 4: Plan for draft review
  Harry to adopt and incorporate 643r5 except for DPP Mode 2 TDD
  Doc 158 revision on Cyber Security – follow up document to be submitted by Yael from Ondas. March 21
  Complete Draft 0.8 Harry to provide to TG by March 27
  Teleconference with Task Group to review of D0.8 Wednesday April 5 - 8am PT
  Any changes from review to become draft D0.9
  Review Draft D0.9 on April 25 Teleconference
  Initiate WG Comment Collection on Draft 0.9 Monday May 1
  Review and resolve D0.0 comments – May Interim
  May Interim - Motion for WG Letter Ballot on D1.0 – starting 2 weeks after May Interim
Initiate Plan to include broader set of stakeholders (from first meeting of TG16t) in Letter Ballot to receive comments. Request access from WG Chair.

## Slide 5: April 5 Teleconference Discussion / Minutes
Attendees Tim Godfrey, Harry Bims, Menashe Shahar, Vishal K, Juha Juntunen.
Review comments in document 203, capture resolutions from this teleconference in r1.
Review Doc 802.15-22-643r6.
Next Steps
  643r7 to be posted
  Vishal implements cross-reference fixes
  Security document 201r0 replaces previous contribution 193r0 – to be reviewed.
Teleconference April 25 at 8am PDT to review updates and approve content for D0.9
  Based on teleconference discussion Next Draft 0.9 to be created
  Task Group Comment Collection ongoing.
  In Orlando discuss and resolve final comments on D0.9
Following Orlando, create 1.0 and conduct WG Letter Ballot

## Slide 6: April 25 Teleconference – discussion/minutes
Completed review 212r0 with comments on D0.9, capture notes in 212r1.
A further update of comments in 643r7 is needed – plan to get 643r8 on DPP. Plan to review in May interim.
Can we create a narrowband profile?
Reviewing document 209r1, Pick up review process with “Section 8.6.5.2” in May meeting
  Menashe will review 209r1 regarding DPP section to prepare 643r8.
Harry will fix page numbering and distribute Framemaker.

## Slide 7: Project Timeline
Milestone | Date
Task Group Start | Jan 2020
SRD Approval | April 2021
SDD Approval | Jan 2022
Draft Development | 
Informal TG review of draft | Mar 2023
Working Group Letter Ballot | May 2023
Working Group Recirculation Letter Ballot | Sep 2023
SA Ballot | Nov 2023
Forward to RevCom | Mar 2024
PAR Expiration Date: 31 Dec 2024
If needed, request PAR extension July 2024

## Slide 8: Future Meetings
May 2023 Wireless Interim
  May 15-18, 2023 Orlando, FL, USA
July 2023 Plenary
  July 10-13, 2023 Berlin, Germany
Sept 2023 Wireless Interim
  Sept 11-14, 2023 Atlanta, GA

## Slide 9: Closing
Any Other Business
Actions
Adjourn