## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: Suggested 15.7a Schedule and Milestones
Date Submitted: May 18, 2023
Source: Yeong Min Jang, Kookmin University
Voice: +82-2-910-5068 E-Mail: yjang@kookmin.ac.kr
Re:
Abstract: This contribution presents a proposed timeline with milestones. It is offered to the committee which can adopt, modify or ignore the suggested timeline.
Purpose:
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2
9/2020
1/2021
1/2022
1/2023
CFA Issued
CFA Responses
Finalize TRD and Release CFP
Hear CFP Proposals
Proposal mergers & Draft D0
Draft D1
Draft D2& LB1
Timeline Summary
Details on the next five pages.
This contribution presents a proposed timeline with milestones. It is offered to the committee which can adopt, modify or ignore the suggested timeline.
1/2025
Draft D3 & LB2
Draft D4 & LB3
15.7a to SA for publication
Draft D6 & SA Ballot 1
1/2024
Draft D8 & SA Ballot 3
Draft D7 & SA Ballot 2
Draft D5 & LB4

## Slide 3
2020 |  |  | 
Q3 | July | August | September
 |  |  | Affirm officers Update web page Approve schedule & milestone Release Draft CFA
Q4 | October | November | December
 |  | Hear CFA responses Start preparing (ad-hoc) TRD | 

## Slide 4
2021 |  |  | 
Q1 | January | February | March
 | (Hear CFA responses) TRD Editing Channel model discussion and finalization (if possible) |  | Finalize channel model (if it is not done in January) Finalize and approve TRD Start preparation CFP (and challenge to release CFP)
Q2 | April | May | June
 |  | Finalize and release CFP | 
Q3 | July | August | September
 | Hear CFP responses |  | Hear remaining CFP responses Start proposal mergers
Q4 | October | November | December
 |  | Continue proposal mergers Start preparation of revision baseline D0 | 

## Slide 5
2022 |  |  | 
Q1 | January | February | March
 | Finalize revision baseline draft D0 Commence task group review and comment resolution |  | Continue task group review and comment resolution Finalize revision baseline draft D1
Q2 | April | May | June
 |  | Continue task group review and comment resolution Prepare Draft D2 | 
Q3 | July | August | September
 | Continue task group review and comment resolution Finalize first WG letter ballot (LB1) draft D2 |  | Submit D2 to WG for LB1
Q4 | October | November | December
 |  | Start LB1 comment resolution Prepare D3 for LB2 | LB1 comment resolution Prepare D3 for LB2

## Slide 6
2023 |  |  | 
Q1 | January | February | March
 | Finish LB1 comment resolution Submit D3 to WG for LB2 Start LB2 (1st recirculation) | Start LB2 comment resolution | LB2 comment resolution Prepare D4 for LB3
Q2 | April | May | June
 |  | Finish LB2 comment resolution Submit D4 to WG for LB3 (2nd recirculation) | Start LB3 comment resolution
Q3 | July | August | September
 | Complete LB3 comment resolution Prepare D5 for LB4 Submit D5 to WG for LB4 (3rd recirculation) | LB4 comment resolution | Prepare SA Ballot document Prepare D6 for SA Ballot 1
Q4 | October | November | December
 | Submit SA Ballot 1 package document to WG | Start SA Ballot 1 | SA Ballot 1 comment resolution

## Slide 7
2024 |  |  | 
Q1 | January | February | March
 | Complete SA Ballot 1 comment resolution Prepare D7 document Submit D7 for SA Ballot 2 | Start SA Ballot 2 | SA Ballot 2 comment resolution Prepare D8 document Submit D8 for SA Ballot 3
Q2 | April | May | June
 | Start SA Ballot 3 | SA Ballot 3 comment resolution Prepare D9 for SA Ballot 4 | Start SA Ballot 4
Q3 | July | August | September
 | Resolve final SA editorial comments and prepare final Draft D10 for publication |  | Have a publication party!
Q4 | October | November | December