## IEEE Cover
July 2023 |  | Doc: P802.15-23-0360-01-6ma
IEEE 802.15
Wireless Specialty Networks
Title | TG6ma draft action items
Date submitted | July 11th, 2023
Source | Marco Hernandez; YRP-IAI, Japan, CWC Oulu Univ. Finland
Ryuji Kohno; YRP-IAI, Japn, YNU, Japan
Purpose | TG timeline
Notice | This document has been prepared to assist the IEEE P802.15.6ma as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and IEEE P802.15 may make it publicly available.

## Action Items
Topic item | Deadline | Action items | Progress | Notes
PHY: HARQ description. | Aug/2023 | Kento, Marco
PHY: Ranging description | Aug/2023 | Daisuke, Kohno, Marco | 20%
PHY: HRP UWB parameters, FEC combinations for coexistence. | Aug/2023 | Marco | 80%
MAC: MAC frame formats | Sep/2023 | Dr Joo, Minsoo, Marco
MAC: MAC functional description including coexitence and C2C | Sep/2023 | Dr Joo, Minsoo, Marco
MAC: MAC services | Sep/2023 | Dr Joo, Minsoo, Marco
MAC: Ranging description | Sep/2023 | Dr Joo, Minsoo, Daisuke, Marco