## IEEE Cover
July 2023 |  | Doc: P802.15-23-0360-04-6ma
IEEE 802.15
Wireless Specialty Networks
Title | TG6ma draft action items
Date submitted | July 11th, 2023
Source | Marco Hernandez; YRP-IAI, Japan, CWC Oulu Univ. Finland
Ryuji Kohno; YRP-IAI, Japn, YNU, Japan
Purpose | TG timeline
Notice | This document has been prepared to assist the IEEE P802.15.6ma as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and IEEE P802.15 may make it publicly available.

## Action Items
Topic item | Deadline | Action items | Progress | Notes
PHY: HARQ description. |  | Kento, Marco | 95% | HARQ parameters based on simulations pending
PHY: HARQ simulations |  | Kento, Daisuke, Marco | 10% | Results pending
PHY: Ranging description |  | Kohno, Marco | 95% | Ranging parameters based on simulations pending
PHY: Ranging simulations |  | Daisuke | 50% | Results for coexistence and channel model pending
PHY: FEC combinations for coexistence. |  | Marco | 100% | Done.
PHY: FEC simulations for coexistence. |  | Daisuke, Kento, Marco | 100% | Relevant coexistence scenarios: 2, 3, 4
PHY: UWB parameters |  | Marco | 10% | UWB parameters based on simulations
MAC: MAC frame formats |  | Marco, Dr Joo | 60% | Based on harmonization. We finally have an agreement on generic MAC frame format
MAC: MAC functional description including coexistence and C2C |  | Marco, Dr Joo | 20% | General description of the multiple BANs coordination protocol. Dr Joo should follow.
MAC: MAC services |  | Marco, Dr Joo | 20% | Same as above
MAC: MAC simulation for coexistence |  | Daisuke, Marco | 10% | This may be an issue
MAC: Ranging simulations |  | Daisuke | 20% | Preliminary results