## IEEE Cover
July 2023 |  | Doc: P802.15-23-0361-04-6ma
IEEE 802.15
Wireless Specialty Networks
Title | TG6ma Timeline
Date submitted | July 11th, 2023
Source | Marco Hernandez; YRP-IAI, Japan, CWC Oulu Univ. Finland
Ryuji Kohno; YRP-IAI, Japn, YNU, Japan
Purpose | TG timeline
Notice | This document has been prepared to assist the IEEE P802.15.6ma as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and IEEE P802.15 may make it publicly available.

## TG Schedule
Topic item | Deadline | Action items | Notes | Progress
Std Draft v.1.14 WG pre-ballot recirculation. | March/2024 | Disposition of comments. MAC text based on harmonization. Updates of simulations for MAC and PHY. | We hope to launch what is missing for the new MAC (frame formats and services), after the agreement on multi-band coordination.
Towards the May 2024 meeting | May/2024 | Adding MAC text. Revise PHY text. Editorial revisions.
Target WG letter ballot (LB) submission | May/2024 |  | 1. Based on pre-ballot resolutions, prepare Draft v. 2.0 2. Request LB submission before the January meeting. Consequently, the January meeting is used to resolve comments.
1st LB recirculation | July/2024 |  | Comment-resolutions to LB recirculation.
2nd LB recirculation | Sep/2024 |  | Comment-resolutions to LB recirculation.
Conditional approval for Sponsor Ballot (SB) | Sep/2024 |  | Seek conditional approval for SB by the Executive Committee.
Final LB recirculation. | Nov/2024 |  | WG approval to request SB submission.
Request EC approval for SB | Nov/2024 |  | Request SB approval by the EC (conditional or not)
IEEE SA Sponsor Ballot submission | Dec/2024 |  | One month for IEEE SA editorial review.
1st SB recirculation | Jan/2025 |  | Comment-resolutions to SB and recirculation.
2nd SB recirculation | Feb/2025 |  | Comment-resolutions to SB and recirculation.
Request conditional/unconditional approval to RevCom | March/2025 |  | Submission to SASB agenda
Final SB recirculation, if required. Submission to RevCom | May/2025 |  | Submission to SASB
RevCom submission | Jun/2025 |  | RevCom approval