## Comments-Resolutions
CID: Comment's ID. Resolution: Accepted: The proposed change is accepted as it is. Accepted in principle: The proposed change concept is accepted, but the resolution contains modifications accepted by the Working Group. Rejected: The proposed change is rejected providing a reason. Last updated: Month/Day/Year [time] of the last resolution update. Resolution done? : Yes or No (blank): use by the editor for progress tracking.
CID | Name | Category | Clause # | Page # | Line # | Comment | Proposed Change | Resolution | Last updated | Resolution done? | 2026-08-05 18:40
21 | Hiroki Saito | Editorial | 5.2.1.1.7 | 19 | 3 | Reference source not found.", which seems to be an error in the reference source, is found in the text. (I checked the entire document for similar errors and found no others.) | Enter the correct reference. | Accepted. | 2023-09-14 | Yes
6 | Seong-Soon Joo | General | 5.8 | 74 | 3 | HRP MAC is used without defining the term. A different frame formats are specified in the sub-clause of the clause "5. MAC frame formats". | Deinfe the HRP MAC in clause 4. Move sub-clause to a new clause for HRP MAC. | Accepted in principle. Define HRP MAC in clause 4. | 2023-09-14 | Yes
10 | Seong-Soon Joo | Technical | 5.8.1, 5.8.2 | 74 | 13, 22 | Control channel and Common channel are not fully described and confused in terms. It is not clear whether channel concepts are dependent on physical channel or on logical channel. | Need more comlete description on control channel and common channel. If common chanel of 5.8.2 is about physical channel, it should be described in the 9.12 Operating ferequency bands. | Accepted in principle. Describe control channel and common data channel functional description in the operating frequency bands. | 2023-09-14 | Yes
22 | Yasuharu Amezawa. | Technical | 5.8.1 | 74 | 13 | Although there is a statement "Data channel (DC) with a superframe structure for data transmission and ranging," is the ranging pursued between coordinator and hub? The following statement seems to mean if the ranging is pursued between coordinators each other. 9.1.16.1.1 General "This specification is for ranging, relative positioning, and localization for human and vehicle body area networks (HBAN and VBAN) using Ultra-Wide Band (UWB) physical layer (PHY) that uses two-way ranging (TWR) technology." | Provide more complete description on NMP. | Accepted in principle. Describe NMP functional description. | 2023-09-14 | Yes
23 | Yasuharu Amezawa. | Technical | 5.8.3.4 | 75 | 14 | Although the same value (=0) is assumed as IEEE 802.15.4-2012, is ti necessar to identify difference between 15.4 and 15.6ma? In the farme structure described hereafter between 15.4 and 15.6ma. | Provide more complete description on CFP and CAP. Need a desription on HRP MAC superframe structure. | Accepted in principle. Describe CAP and CFP functional description and length of CAP and CFP. | 2023-09-14 | Yes
11 | Seong-Soon Joo | Technical | 5.8.4 | 76 | 10 | Network Management Period (NMP) is used without defining the term. | Insert a new clause for HRP MAC, "7. HRP MAC", in the draft. | Accepted. | 2023-09-14 | Yes
12 | Seong-Soon Joo | Technical | 5.8.4 | 77 | 15, 17 | Contention Free Period (CFP), Contention Access Period (CAP) are used without defining the terms. | Provide complete description on HRP MAC superframe structure. | Accepted. | 2023-09-14 | Yes
7 | Seong-Soon Joo | General | 6.16 | 148 | 3 | The title of sub-caluse 6.16 is the same as the title of clause 6. sub-claus 6.16 is isolated with the leagcy MAC funtions. | Provide complete description on synchronization with the other BAN superframe. | Accepted. | 2023-09-14 | Yes
13 | Seong-Soon Joo | Technical | 6.16.1 | 148 | 19 | There is no prior information on how to numbering a slot in CFP and CAP. | Be a sub-clause of new clause for HRP MAC. | Accepted in principle. Clarify the HRP MAC clause contains this subclause. | 2023-09-14 | Yes
14 | Seong-Soon Joo | Technical | 6.16.2 | 149 | 9 | The meaning of "synchronize with the superframe" is not clear. | Provide complete sentences in a clause or remove the sub clause 6.17.1. | Accepted. | 2023-09-14 | Yes
8 | Seong-Soon Joo | General | 6.17 | 150 | 11 | sub-claus 6.17 is isolated with the leagcy MAC funtions. | Remove the sub clause 6.17.2. | Accepted in principle. Clarify the HRP MAC clause contains this subclause. | 2023-09-14 | Yes
15 | Seong-Soon Joo | General | 6.17.1 | 150 | 12 | Sub-clause "Requirements on Dependable BAN Operation" is wirtten in incomplete sentences and is described in clause where defines Dependable BAN. | Provide complete description in-lined with the HRP MAC superframe structure. | Accepted. | 2023-09-14 | Yes
16 | Seong-Soon Joo | General | 6.17.2 | 150 | 23 | Sub-clause "Design considerations" is written in incomplete sentences and is needed to check whether contained in draft or not. | Provide complete description in-lined with the HRP MAC superframe structure. | Accepted. | 2023-09-14 | Yes
33 | Takafumi Suzuki | Technical | 6.16.4 | 150 | 6 | In a use case of BMI, a time lag between ECoG detection by sensors inside a brain and signal reception is very important, so back-off time of ECoG packets must be restricted within permisible time period. ECoG packets is categorized as the highest QoS level 7 and then the packets should be transmitted in CFP, However, if the length of CFP is not enough long to transmit all ECoG packets, then the overflowed ECoG packets must be transmitted in next superframe, then long delay over a superframe length causes. |  | Accept in principle. Check CFP period and CAP period design to guarantee high data rate with minimun latency. | 2023-09-14 | Yes
17 | Seong-Soon Joo | Technical | 6.17.3 | 151 | 2 | Sub-clause "Changes on Structure of Beacon Period" is written in incomplete sentecnes and is not in-lined with the HRP MAC superframe structure. | Provide complete description in-lined with the HRP MAC superframe structure. | Accepted. | 2023-09-14 | Yes
18 | Seong-Soon Joo | Technical | 6.17.4 | 151 | 29 | Sub-clause "Modified Active Superframe Interleaving with Adjustment" is written in incomplete sentecnes and is not in-lined with the HRP MAC superframe structure. | Be a sub-clause of new clause for HRP MAC. | Accepted in principle. Clarify the HRP MAC clause contains this subclause. | 2023-09-14 | Yes
19 | Seong-Soon Joo | Technical | 6.17.5 | 151 | 37 | Sub-clause "Modified Active Superframe Interleaving Interleaving with Regulation" is written in incomplete sentecnes and is not in-lined with the HRP MAC superframe structure. | Provide complete description and move to clause 4. | Accepted in principle. Clarify the HRP MAC clause contains this subclause. | 2023-09-14 | Yes
24 | Yasuharu Amezawa | Technical | 6.17.3 | 151 | 18 | newly joined BAN searches beacon access phase and relocates the beacon slot with beacon slot assign rules Considering the above operation, we think that a function such as suppressing transmission from the node during the transition period of becon slot change is necessary. | Reduce redundant contents. | Accepted in principle. The node cannot transmit any packet in the transition period | 2023-09-14 | Yes
9 | Seong-Soon Joo | General | 6.18 | 152 | 5 | sub-claus 6.18 is isolated with the leagcy MAC funtions. | please make corresponding change. | Accepted in principle. Clarify the HRP MAC clause contains this subclause. | 2023-09-14 | Yes
20 | Seong-Soon Joo | Technical | 6.18 | 152 | 5 | Sub-clause "Class of coexistence environment" is written in incomplet setneces and is needed to check where is adequate place. | please refer to 15-23-0296-02-04ab-tfd-of-nb-cca-for-assisting-uwb-channel-access | Accepted in principle. Describe the 8 coexistence classes. | 2023-09-14 | Yes
25 | Yasuharu Amezawa | Technical | 6.17.5 | 152 | 3 | There is the statement "BAP > EAP > Scheduled MAP > RAP > CAP," does it pursue not in the access phase of CAP/CFP but does it 5 in the access pheses as the same as 802.15.6-2012? It is different from the definition of D-Beacon. | please make corresponding change. | Accepted in principle. Clarify the statement in line 3. | 2023-09-14 | Yes
1 | Huan Ban Li | General | 8 | 183 | 1 | Many contents of this clause are the same as the original 15.6 whereas only new amendments should be provided. | Try to unify these two subclauses. | Rejected. 6ma is a revision, the entire Std 2012 is open for revision. | 2023-09-14 | Yes
26 | Yasuharu Amezawa | Technical | 9. | 197 | 13 | Although there is the statement "The PLCP constructs the PHY layer protocol data unit (PPDU) by concatenating the synchronization header(SHR), physical layer header (PHR), physical layer service data unit (PSDU) that encapsulates MPDUs, and the frame check sequence (FCS) formed by the parity bits of a cyclic-redundancy code (CRC), respectively." does FCS(CRC) given in PHY? In case current available devices in 15.4z may not be implementable. |  | Accepted in principle. Check CRC in 4z and how to harmonize. | 2023-09-14 | Yes
27 | Yasuharu Amezawa | Technical | 9.1.1 | 198 | 4 | Although there is the satement "The order of building blocks depends on the use case and it is set up after association and signaled by an application to the PLCP according to Table 54. At start-up the UWB frame type shall be set to one (communication) regardless of the application." current available devices for 15.4z may not purform change dynamically packet mode(Frame type in Table 54). |  | Rejected. The std 6ma aims for new UWB implementations. | 2023-09-14 | Yes
31 | Yasuharu Amezawa | Technical | 9.1.1.3.1 | 199 | 15 | BCC is an FEC for correction of bit errors while RS code is an FEC for correction of burst errors in general. So why don't you apply interleaver between outer and inner codes? |  | Accepted in principle. Check interleavers with simulations. | 2023-09-14 | Yes
32 | Yasuharu Amezawa | Technical | 9.1.1.3.1 | 199 | 15 | Since curent channel models are mainly focused on no mobility but stastical environment such as between a transmitter in a brain etc. and a reciver on a skin, no fading is assumed and then FCC has been selected for limited length burst errors. However, under various classes of coexistence, more poweful FEC with burst error correction should be designed for enhanced dependability. |  | Accepted in principle. Check coexistence scenarios with simulations with several FEC configurations. | 2023-09-14 | Yes
28 | Yasuharu Amezawa | Technical | 9.1.2.1.7 | 211 | 5 | In current avauilable devices for 15.4z, there is no way to control in mixed between for ranging and not for ranging. |  | Rejected. The std 6ma aims for new UWB implementations. | 2023-09-14 | Yes
29 | Yasuharu Amezawa | Technical | 9.1.2.1.8 | 211 | 11 | Current availabel devices for 15.4z may not dynamically changepacket mode( Frame type in Table 54). |  | Rejected. The std 6ma aims for new UWB implementations. | 2023-09-14 | Yes
30 | Yasuharu Amezawa | Technical | 9.1.3.1 | 212 | 9 | If Kasami sequence is applied in preamble, current availabe devices for 15.4z may not indentify the preamble. Is it OK? |  | Rejected. The std 6ma includes Ipatov sequences as optional; hence 6ma devices can detect 4z devices. | 2023-09-14 | Yes
2 | Huan Ban Li | General | 9.1.15.12 | 238 | 11, 12 | If there are two modes, it should be better to denote them as Mode 1 and Mode 2 instead of Mode 1 and Mode 3. | If there are two modes, it should be better to denote them as Mode 1 and Mode 2 instead of Mode 1 and Mode 3. | Accepted. | 2023-09-14 | Yes
3 | Huan Ban Li | Technical | 9.1.15.12 | 238 | 11, 15 | Suggest to add an optional NB CCA mode to faciliate CCA operation among different types of UWB radios. | Suggest to add an optional NB CCA mode to faciliate CCA operation among different types of UWB radios. | Accepted in principle. Add NB CCA for 6ma HRP UWB | 2023-09-14 | Yes
4 | Huan Ban Li | General | 9.2.16.8 | 278 | 9 | If FM-UWB is not updated, it sgould not be included in this amendment. | If FM-UWB is not updated, it sgould not be included in this revision. | Accepted. | 2023-09-14 | Yes
5 | Huan Ban Li | Technical | 9.2.16.9 | 278 | 21 | Contents of this subclause overlaps with subclause 9.1.15.12. | Contents of this subclause overlaps with subclause 9.1.15.12. | Accepted. | 2023-09-14 | Yes
34 | Seong-Soon Joo | Technical | 6.1 | 77 | 12 | The revison history must be located in introduction. The general concept of revision is introduced in Clause 4. The overview of revision MAC function will be followed legacy MAC function description. | Sentence "At first a major revision of std.1EEE802.15.6 is described in subclause 6.2 for enhanced dependability in multiple classes of existence" goes to introduction. Sentence "A new definition of a control channel and a data channel in UWB frequency band channels is introduced to ensure enhanced dependability in the classes of new BANs of this revision with the legacy BANs of IEEE802.15.6-2012, and other UWB and narrowband PANs" goes to new clasue 4.5 Coexisting mutlple depedable BANs The description of dependable MAC functions are introduced at the end of 6.1. | Accepted | 2023-11-14 | Yes
35 | Seong-Soon Joo | Technical | 6.2 | 77 | 28 | The title of sub-caluse 6.2 is inappropriate as a standard's title. The descrition of 6.2 is inappropriate as a standard description. The location of 6.2 needs to be reallocated in Clause 6. | Change the title "Major revision" into "Dependable BANs". Move 6.2 intto 6.16 Dependable BANs. | Accepted | 2023-11-13 | Yes
36 | Seong-Soon Joo | Technical | 6,3 | 80 | 16 | The location of 6.3 needs to be reallocated in Clause 6. | Merge 6.3 MAC functions and 6.18 MAC functions into 6.16 Dependable BANs. | Accepted | 2023-11-13 | Yes
37 | Seong-Soon Joo | Technical | 6.18 | 155 | 3 | sub-claus 6.18 is duplicated with 6.3 MAC funtions. | Replace 6.18.1 with 6.3.1. | Accepted | 2023-11-13 | Yes
38 | Seong-Soon Joo | Technical | 6.20 | 159 | 5 | Sub-clause "Class of coexistence environment" is written in incomplet setneces. This concept needs to be appeared in the clause 4. | Provide complete description and move to new clasue 4.5 Coexisting mutlple depedable BANs. | Accepted | 2023-11-14 | Yes
39 | Seong-Soon Joo | Technical | 6.2.4 | 79 | 31,33 | How to setup the length of superframe is not described. NNMP, NCFP, NCAP are used without definition. | Provide how to determine the length of superframe, NNMP, NCFP, and NCAP with the resritions. | Accepted | 2023-11-13 | Yes
40 | Seong-Soon Joo | Technical | 6.3.2 | 82 | 7 | In a BAN, the procedure of nodes reconnection for transiting to new superframe structure is not described. | Provide a procedure how to reconnect nodes in a BAN to follow the new superframe structure. | Accepted | 2023-11-13 | Yes
41 | Seong-Soon Joo | Technical | 5.8 | 73 | 21 | The title of subclause 5.8 is inappropriate. |  | Accepted | 2023-11-13 | Yes
42 | Seong-Soon Joo | Technical | 5.8.1, 5.8.2 | 73 | 22 | Two subclauses need to be relocated. | Propose to move the contents of two subclauses into the new subclause 4.5 Coexsiting dependable BANs. | Accepted | 2023-11-14 | Yes
43 | Seong-Soon Joo | Technical | 5.8 | 76, 77 | 1 | Iincomplete sentences and missing contents. | Provide complete description. | Accepted | 2023-11-13 | Yes
44 | Seong-Soon Joo | Technical | 6.19.1, 6.19.2 | 157 | 12 | Two subclauses are inappropriate in subcaluse 6.19, need to be relocated. | Propose to move the contents of two subclauses into the new subclause 4.5 Coexsiting dependable BANs. | Accepted | 2023-11-13 | Yes
45 | Seong-Soon Joo | Technical | 6.19.3, 6.19.4,6.19.5 | 158 | 2 | Three subclauses are incomplete and not aligned with the MAC framr for dependable BANs. | Provide complete description. | Accepted | 2023-11-13 | Yes
46 | Yasuharu Amezawa | Technical | general |  |  | IEEE802.15.6ma is assumed primarily to use two of more UWB band channels for control and data channels to perform enhanced dependability in coexistince of multiple UWB networks. If a current available major UWB devices, then it iseems to be difficult to implement two or more UWB channels by interupt operation. | Even if an available UWB device does not support two UWB band channels, then the two or more devices can make multiple bands operation with an external processor among devices although synchronizaton of system clocks, c-beacon and d-beacon among devices makes cntrol/data channels transition restricted. UWB devices supporting two or more UWB band channels are looked forward. | The draft Std specifies the possibility to use of two channels for control and data. Implementation of two radio interfaces with a different frequency band is implementation dependant. | 2023-11-13 | yes
47 | Yasuharu Amezawa | Technical |  |  |  | In coexisinting multiple BANs environment, 15.6ma proposes transmission timeing of D-Beacon which is slot number since MAC started, can be set up in dependable BAN Beacon IE of D-Beacon which is a new management frame transmitted by a group coordinator or coordinator hub. | Provided that resolution of slot assignment may be the same as about pAllocationSlotMin(=500usec), the slot number can be controlled with software in a current available major UWB device, and after set up transmission frame(D-Beacon), transmission can be completed within a limited time period. And there is no restrict to complete transmission process in a simple MAC-PDU. | TBD | 2023-11-13 | not yet
48 | Yasuharu Amezawa | Technical |  |  |  | Slot index in beacon access phase (BAP) which is a transmission location of D-Beacon is necessary for any new BAN coordinator or leaf hub to join in coexiting a group of 6ma dependable BANs, but this issue is not descibed in the document of draft1.7 and 1.9. | A new BAN coordinator or a leaf hub transmits a D-Beacon for joining in a coexiting group at random selecting slot index within indexes of vacum slots in gtroup or super coordinator's managing BAP. This issue should be described in class ! Coexitence in some sub-clause. | Accepted in principle. Details of group formation will be provided. | 2023-11-13 | not yet
49 | Yasuharu Amezawa | Technical |  |  |  | It is proposed that D-Beacon is applied to inform Access Offset which is a staring point informed by a new BAN's coordinator or leaf hub to its coordinating nodes when a new BAN is joining in a group of coexiting BANs. However, if CFPs of coexisting BANs is overlapped, then it is difficult to perform dependency in Class 1 of coexistence. | If a group or super coordinator control access phase of all coordinatos of a group of coexiting BANs, then contention of CFPs of all coexiting BANs can be avoided for enhanced dependability. | Accepted in principle. Details of merging of superframes will be provided. | 2023-11-13 | not yet
50 | Takumi Kobayashi | General | 9.1.17 | 247 | 5 | In 4.7.1, coexistence environments are explaind and defined as class 0 to 7. It seems that the inteference in classes 1 and 2 can be reduced by MAC technologies and control schemes. On the other hand, interference in case of classes 3 to 7 (interference from NOT802.15.6 series wireless and/or the other electro-magnetic radiative systems) should be reduced and mitigated in the PHY layer and/or signal processing. In the clause 9.1.17, interference mitigation technologies on physical layer and signal processing have been explaind. That becomes better to understand if the sentences explain that the techniques described in 4.7.1 is more focussing on the interference mitigation for coexistence level 3 to 7 that cannot be mitigated by MAC technique. | I would suggest to insert following paragraph at the beginning of the 9.1.17. "In 4.7.1, coexistence environments are explaind and defined as class 0 to 7. Inteference from the other devices in classes 1 and 2 can be reduced by MAC technologies and control schemes. On the other hand, interference in case of classes 3 to 7 (interference from NOT802.15.6 series wireless and/or the other electro-magnetic radiative systems) cannot be controled by MAC technique and that should be reduced and mitigated in the PHY layer and/or signal processing. In this clause, interference mitigation technologies on physical layer and signal processing are explaind more focussing on the interference mitigation for coexistence level 3 to 7 that cannot be mitigated by only MAC technique." | Accepted in principle. In this clause, interference mitigation technologies on physical layer and signal processing are explaind more focussing on the interference mitigation for coexistence level 3 to 7 that cannot be mitigated by only MAC technique. | 2023-11-13 | yes
51 | Ryuji Kohno | Technical |  |  |  | Before introducing interference mitigation technology, we need to identify or recognize which type of the networks are coexisting in order to identify the coexistence class enviroment in the PHY layer. | The issue should be described in clause 4. Classes 1, 2: detection of beacon, preamble. Also the MAC modes 1,2 description. | Accepted in principle. Details will be provided. | 2023-11-13 | not yet
52 | Yasuharu Amezawa, Ryuji Kohno | Technical |  |  |  | In a current draft, for class 1 of coexistene, it seems that a group coordinator or coordinator hub transmits only information of starting point of access phase of CAP and CFP to other coordinators of coexisting BANs in a group or a leaf hub. Individual leaf hubs control their own access phase of CAP and CFP by individual B-Beacons independently. In order to perform enhanced dependabiity, a group coordinator or coordinator hub should manage or control all access phases of other coordinators or leaf coordinators in the same group in class 1 of coexistence. | A scheme of a group coordimato's or coordinator hub's controlling all access phase of CFP and CAP of all other coordinators or leaf hubs in the same group of coexisting BANs in class 1 by adding some information in D-Beacon. Since CAP is a period in which contention must be assumed, any temporal overlap of CAPs in both a group coordinator and other coordinators in the same group of coexisting BANs may be no probem. However, when packet traffic increases according to increase of nodes, PER(Packet Error Ratio) must increase. So, an extra scheme to assign CAP into other periods such as non access period(NAP) may be better, In order to perform enhanced dependability, a group coordinator or coordinator hub should control all CAPs of the same group of coexisting BANs be assigned within the same time slot or into other new periods such as NAP. The following figure A shows a our proposal of revised Access Offse. Figure A 1)Detect D-Beacon of BAN#1 by group coordinator or coordinator hub of BAN#2 b0 b11 b0 b11 CAP start offset CAP length CFP start offset CFP length ※superframes最大長=4096スロットを想定 図 2-12 Access Offset修正案イメージ 本資料の提案仕様案での動作イメージを図 2-13に記す。 14 / 30 ©Copyright 2023 Mobile Techno Corp. １）BAN#2のcooridnator hubがBAN#1のD-Beaconを検出 superframe (BAN#1) slot num. 0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 用途 BAP CAP(BAN#1) CFP(BAN#1) IDLE ２）BAN#2のhubがleaf hubとしてdependable BANへの参加要求送信 superframe (BAN#1) slot num. 0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 用途 BAP CAP(BAN#1) CFP(BAN#1) IDLE ３）BAN#1のcoordinator hubがBAN#2のhubをleaf hubとしてdependable BANへの参加を受理 superframe (dependable BAN) slot num. 0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 用途 BAP CAP(BAN#1) CFP(BAN#1) CAP(BAN#2) CFP(BAN#2) IDLE 図 2-13 leaf hubへのslot割り当て制御処理 | TBD | 2023-11-15 | Yes
| Yasuharu Amezawa, Ryuji Kohno | Technical |  |  |  |  | 1)Detect D-Beacon of BAN#1 by group coordinator or coordinator hub of BAN#2 FIgure B 2) In case that coordinator of BAN#2 transmits request to join in a group of coexisting BANs as a leaf hub which is not a group coordinator 3 ) Group coordinator or coordinator hub of BAN#1 accepts a request of coordinator of BAN#2 asamember coordinator or leaf hub This detail is described in doc.#15-22-0593-00-06ma
53 | Yasuharu Amezawa, Ryuji Kohno | Technical |  |  |  | The current draft describes only using Access Request of D-Beacon but no detail to join in a group of coexisting BANs in Class 1 of coexistence. In order to improve dependability of data transmission and ranging in Class 1 of coexistence, it is important to determine assignment of resourcce or number of slots according to the number of nodes or maximum number of high QoS packets in all coexisting BANs. | We propose all coordinators in a group of coexisting BANs in Class 1 should broadcast the number of covering nodes or maximum number of high QoS packets when a BAN comes to join in a group of coexisting BANs as shown in figure D. Figure D Image of Revised Access Reques In transition of incoming and outgoing BANs in a group of coexiting BANs, structure of superframes may be changed. The meanwhile, temporally packet loss may increase. So, before coordinators transmit information of joinining in a group or leaving from a group to a group coordinator or coordimnator hub, member coordinator or leaf hub should transmit request for all nodestemporally to stop packet transmission in order to resuce packet loss. Instead of individual request to stop packet transmission, it is more efficient to add information for stop packet transmission into D-Beacon. We propose that a scheme of extending D-Beacon Subtype field and a new Resource suspend indicator field in order to stop all packet transmission from all nodes. in efficient. Moreover, each node which is stopped packet transmission in Resource suspend indicator field should transmit Connection Request management frame when member coordinators or leaf hubs will transmit Superframe Adjust field. In the current draft, when a new BAN joins in a group of coexisting BANs and a new superframe is synchronized, each member coordinator or leaf hub transmits Superframe Adjust field to all nodes. The Superframe Adjust field in the current draft as shown in Figure G. Beacon Slot Offset and BAP Length in each BAN are defined. However, since starting points of BAP is not always the same in each BAN, it seems difficult to coexist together. We propose to revise Superframe Adjust field as shown in Figure H in order to synchronize all BANs. During BAP Start Offset, number of slots for offset between current D-Beacon location and a new BAP can be determined. Figure E | TBD | 2023-11-15
In the current draft, when a new BAN joins in a group of coexisting BANs and a new superframe is synchronized, each member coordinator or leaf hub transmits Superframe Adjust field to all nodes. The Superframe Adjust field in the current draft as shown in Figure G. Beacon Slot Offset and BAP Length in each BAN are defined. However, since starting points of BAP is not always the same in each BAN, it seems difficult to coexist together. We propose to revise Superframe Adjust field as shown in Figure H in order to synchronize all BANs. During BAP Start Offset, number of slots for offset between current D-Beacon location and a new BAP can be determined. This detail is described in doc.#15-22-0593-00-06ma
54 | Ryuji Kohno | Technical | 10.2 | 279 |  | MAC for UWB ranging and localization is not good enough descibed yet in draft#1.9 although most of their specification could be refered from IEEE802.15.4z std document. To perform both data transmission and ranging at the same time or superframe, the draft assumes that a packet of ranging could be transmitted and retransmitted back as a pair of dual directional packets within CFP(contention free period) by one-sided or double-sided TWR(tow way ranging). How can we presearve two time slots in the same CFP for such a pair of dual ranging packets? | Applicable range of raning and localization should be assumed and restricted so that around radio trip backcan be completed into CFP in one or a few successive superframes. This is an advantage of 15.6ma MAC which has CFP and CAP in a sense of hybrid contention free and contention access protocol while 15.4z is based on a contention access protocol such as CSMA/CD, ALOHA.
55 | Ryuji Kohno | General |  |  |  | Many BAN usecases may be sensing and feedback controlling between vital and other sensors, and robot and accutuators. This means after a packet from a sensor in a body to a coordinator of BAN in uplink is transmitted, its feedback packet from a coordinator to a an acutuator in down link may be returned back. In the MAC of 15.6ma, such a pair of packets transmission in up and down links could be specified in order to manage packet slot assignment in CFP and CAP to reduce contention. | Some literature regarding such an efficient packet access control can be refereed and possible to choose most feasible solution.
55

## IEEE Cover
November 2023 |  | Doc: P802.15-23-0476-09-6ma
IEEE 802.15
Wireless Specialty Networks
Title | Comment-Resolution Database for Pre-Ballot WG
Date submitted | November 15th, 2023
Source | Marco Hernandez; YRP-IAI, Japan, CWC Oulu Univ. Finland
Ryuji Kohno; YRP-IAI, Japn, YNU, Japan
Purpose | Discussion
Notice | This document has been prepared to assist the IEEE P802.15.6ma as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and IEEE P802.15 may make it publicly available.