## IEEE_Cover
Sep 2023 |  | 15-23-0497-01-04me | Instructions: Fill in month and year at B1 Update doc# in D1 Fill in TG project number in C7 Fill in date in C8. Fill in your name and address in C9:D11 Update TG project number in C15 For each LB Duplicate the LBxxx_template sheet Rename the copied sheet as LBxxx, where xxx is the letter ballot number (or LBxxx_Rogue for rogue comments). Do not use spaces in the sheet names.
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15 Consolidated Letter Ballot Comment for IEEE P802.15.4me
Date Submitted | 2023-09-12
Source | Tero Kivinen | Voice: n/a
Self
E-mail: kivinen@iki.fi
Re:
Abstract | Consolidated letter ballot comments for IEEE P802.15.4me
Purpose | [This document is used to consolidate comments for an 802.15 Letter Ballots.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## LBxxx_template
INSTRUCTIONS: Duplicate this template, and rename it to match the LBxxx where xxx is the letter ballot number. Copy all comments from submitted comment sheets to this sheet by using copy and Paste Special / Paste Text Only them starting from B3 cell. Then add “i-1”, “r1-1”, “r2-1” etc (initial, recirculation1, recirculation2 etc) to the A2 column and drag lover right corner to cover all comments, so each comment gets comment id assigned. Before posting this to the mentor delete column D. Other1, other2, other3 etc can be used for keeping track of your own things, like “Comment group”, “Person assigned to”, “Status in document”. If the Dispotion status is Revised or Rejected you need to have Dispotion detail, and if it is Accepted you can’t have Dispotion status (sheet will show red error in those cases). Remove this line 1 after you have read the instructions as it is no longer needed, and will just unnecessarely consume screen estate. After deleting line 1, freeze first line and column.
Comment ID | Name | Affiliation | Email (remove this column before posting to mentor) | Page | Sub-clause | Line # | Comment | Proposed Change | Category | Must Be Satisfied? | Disposition Status | Disposition Detail | Other1 | Other2 | Other3
i-1

## LB197
Comment ID | Name | Affiliation | Page | Sub-clause | Line # | Comment | Proposed Change | Category | Must Be Satisfied? | Disposition Status | Disposition Detail | Done | Assigned | Other3
i-138 | Pablo Corbalán Pelegrín | NXP Semiconductors | 14 | Introduction | 3 | "This is the fourth revision..." | This is the fifth revision | Editorial | No | Accepted
i-139 | Pablo Corbalán Pelegrín | NXP Semiconductors | 14 | Introduction | 1 | Introduction does not state changes made by 2020 revision nor the changes planned by 2023 current draft. | Add paragraph stating the changes made by the 2020 revision and another paragraph for the changes plannes as part of this draft. | Editorial | No | Accepted
i-108 | Stephan Sand | German Aerospace Center (DLR) | 45 | 4.3 | 8 | There is a note in parenthesis, which is not in the NOTE format as on the previous page. | Move the Note in parentheses after the next sentence and use the NOTE format as on P44L5. | Editorial | No | Accepted
i-106 | Zhenzhen Ye | Redpoint Positioning | 53 | 5.7.1 | 17 | Why the general superframe structure is treated as "Optional features" and included in 10.2 but leaves some special variants of the superframe structure such as Beacon superframe (5.7.1.1), DSME (5.7.1.2), slotframes (5.7.13), and TMCTP superframe (5.7.1.4) in the mandatory section 5.7.1? | If we need to keep 5.7.1.1-5.7.1.4 in its current place, we should move the general description of the superframe structure from 10.2 to 5.7.1. | General | Yes | Revised | Text in section 5 needs to be rewritten and reorganized so that it is clear what optional features. |  | ben
i-107 | Zhenzhen Ye | Redpoint Positioning | 64 | 6.4 | 26 | Why the section of device association and disassociation with a PAN is left in section 10.18, not included in section 6.4? | recommend to move section 10.18 to be a subsection of section 6.4. | General | No | Rejected | All optional features have been moved to section 10, and if there is any leftover of associations or disassications.
i-109 | Stephan Sand | German Aerospace Center (DLR) | 157 | 8.3.2 | 3 | The subclause reference 6.9.1.4 does not exist. The correct reference should be 10.26.1.4 Ranging counter time unit. | Please correct the reference to 6.9.1.4 to 10.26.1.4. Please correct also further occurences at: P157 RangingTxTime row, 4th column; P164 RxRangingCounter row, 4th column; TXRangingCounter row, 4 column; P165 Table 4th column 8 occurences; P165 Table 4th column 2 occurences; P465L6, P469L14, P469L16, and P472L6. | Editorial | No | Accepted
i-1 | Billy Verso | Qorvo | 171 | 8.4.3.1 | 6 | In Table 8-35—MAC PIB attributes, attributes macLifsPeriod and macSifsPeriod both reference clause 11.1.3.13 in the Range column. This is not the correct reference, it should be 11.1.4 | Change References to 11.1.4 | Editorial | Yes | Accepted
i-110 | Stephan Sand | German Aerospace Center (DLR) | 344 | 10.14.2.1 | 4 | The acronym FSCD is introduced here but not listed in Subclause 3.2. | Please introduce the acronyms FSCD in Subclause 3.2 | Editorial | No | Rejected | The FSCD is already defined on section 3.2. Actually as the FSCD is only used as an part of the IE name, it should not be listed in the 3.2, but I will not remove it from there yet.
i-111 | Stephan Sand | German Aerospace Center (DLR) | 344 | 10.14.2.1 | 8 | The acronym MIC is introduced here but not listed in Subclause 3.2. | Please introduce the acronyms MIC in Subclause 3.2 | Editorial | No | Rejected | The MIC is already defined in section 3.2.
i-83 | Alex Krebs | Apple Inc | 448 | 10.26.1.2.2 | 37 | Math symbols have unreadable encoding | maintain 802.15.4z notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-112 | Stephan Sand | German Aerospace Center (DLR) | 448 | 10.26.1.2.1 | 27 | "ranging initation RFRAME" is a duplication as RFRAME is a ranging frame. | Please replace "ranging initation RFRAME" with "initation RFRAME" | Editorial | No | Accepted
i-84 | Alex Krebs | Apple Inc | 449 | 10.26.1.2.2 | 8 | Math symbols have unreadable encoding | maintain 802.15.4z notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-85 | Alex Krebs | Apple Inc | 450 | 10.26.1.2.3 | 5 | Math symbols have unreadable encoding | maintain 802.15.4z notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-113 | Stephan Sand | German Aerospace Center (DLR) | 454 | 10.26.3 | 18 | "both of those these values" contains an extra "those" | Please remove "those" | Editorial | No | Accepted
i-114 | Stephan Sand | German Aerospace Center (DLR) | 454 | 10.26.3 | 21 | The acronym RMI is introduced here but not listed in Subclause 3.2. | Please introduce the acronyms RMI in Subclause 3.2 | Editorial | No | Rejected | RMI IE is an acronym that is only used as an name of the IE, and we do not define them as separate acronyms, unless it is used somewhere when not referencing the IE.
i-115 | Stephan Sand | German Aerospace Center (DLR) | 457 | 10.26.5 | 1 | The sentence is missing a verb. | Replace "us" with "shall come back" | Technical | No | Revised | Chage “us via parameters of the MCPS-DATA.confirm primitivie” to “shall be provided by the MCPS-DATA.confirm primitivie”
i-116 | Stephan Sand | German Aerospace Center (DLR) | 457 | 10.26.5 | 11 | The dagger mark after phyRanging is not superscripted as in Table 12-2 P594. | Please superscript the dagger mark after phyRanging | Editorial | No | Rejected | Unfortunately the framemaker does remove the superscript when it make this type of references. The dagger mark should not be there at all, but I have not found a easy way to get rid of it here, but keep it in the table 12-2.
i-117 | Stephan Sand | German Aerospace Center (DLR) | 457 | 10.26.6.1 | 27 | No "RangingStsS1Fom" is defined | Replace "RangingStsS1Fom" with "RangingStsSFom" | Editorial | No | Revised | There is no RangingStsSFom either, I assume you mean RangingStsFom? Changing to that.
i-118 | Stephan Sand | German Aerospace Center (DLR) | 457 | 10.26.6.3 | 40 | The acronym RRMC is introduced here but not listed in Subclause 3.2. | Please introduce the acronyms RRMC in Subclause 3.2 | Editorial | No | Rejected | RRMC IE is an acronym that is only used as an name of the IE, and we do not define them as separate acronyms, unless it is used somewhere when not referencing the IE.
i-119 | Stephan Sand | German Aerospace Center (DLR) | 458 | 10.26.6.4 | 14 | The acronym RRTI is introduced here but not listed in Subclause 3.2. Similar RRTN is introduced on L19, but not introduced in Subclause 3.2 | Please introduce acronyms RRTI and RRTN in Subclause 3.2 | Editorial | No | Rejected | RRTI IE or RTN IE is an acronym that is only used as an name of the IE or part of the field name, and we do not define them as separate acronyms, unless it is used somewhere when not referencing the IE.
i-120 | Stephan Sand | German Aerospace Center (DLR) | 459 | 10.26.6.4 |  | In Figure 10-195 there is an "RPRT IE". Should this be an "RRTN IE"? RPRT is never used throught the draft. | Please replace "RPRT" with "RRTN" | Editorial | No | Rejected | RRMC IE is an acronym that is only used as an name of the IE, and we do not define them as separate acronyms, unless it is used somewhere when not referencing the IE.
i-121 | Stephan Sand | German Aerospace Center (DLR) | 465 | 10.26.8.2 | 17 | The acronym RSSD is introduced here but not listed in Subclause 3.2. | Please introduce the acronyms RSSD in Subclause 3.2 | Editorial | No | Rejected | RPRT IE is an acronym that is only used as an name of the IE, and we do not define them as separate acronyms, unless it is used somewhere when not referencing the IE.
i-122 | Stephan Sand | German Aerospace Center (DLR) | 468 | 10.26.8.3 | 9 | Reference to Figure 6-48v of 802.15.4z-2020 | Please replace "6-48v" with "10-226" | Editorial | No | Accepted
i-123 | Stephan Sand | German Aerospace Center (DLR) | 468 | 10.26.8.3 | 11 | Reference to Figure 6-48z of 802.15.4z-2020 | Please replace "6-48z" with "10-230" | Editorial | No | Accepted
i-124 | Stephan Sand | German Aerospace Center (DLR) | 468 | 10.26.8.4 | 17 | The acronym RMI is introduced here but not listed in Subclause 3.2. | Please introduce the acronyms RMI in Subclause 3.2 | Editorial | No | Rejected | RMI IE is an acronym that is only used as an name of the IE, and we do not define them as separate acronyms, unless it is used somewhere when not referencing the IE.
i-125 | Stephan Sand | German Aerospace Center (DLR) | 468 | 10.26.8.4 | 7 | Reference to "6.9.6 and 6.9.7" of 802.15.4z-2020 | Please replace with "10.26.6, 10.28, and 10.29" | Editorial | No | Revised | Page number is wrong, it should be 470. There is reference to 6.9.6 and 6.9.7 on page 467, they need to be fixed too.
i-126 | Stephan Sand | German Aerospace Center (DLR) | 470 | 10.26.8.5 | 8 | The acronym RCPCS is introduced here but not listed in Subclause 3.2. | Please introduce the acronyms RCPCS in Subclause 3.2 | Editorial | No | Rejected | RCPCS IE is an acronym that is only used as an name of the IE, and we do not define them as separate acronyms, unless it is used somewhere when not referencing the IE.
i-127 | Stephan Sand | German Aerospace Center (DLR) | 470 | 10.26.8.5 | 10 | Reference to "6.9.4.1" of 802.15.4z-2020 | Please replace with "10.26.4.1" | Editorial | No | Accepted
i-128 | Stephan Sand | German Aerospace Center (DLR) | 470 | 10.26.8.5 | 29 | Reference to "15.2.6.2" of 802.15.4z-2020 | Please replace with "16.2.6.2" | Editorial | No | Accepted
i-129 | Stephan Sand | German Aerospace Center (DLR) | 472 | 10.26.8.6 | 6 | Reference to "6.9.1.4" of 802.15.4z-2020 | Please replace with "10.26.1.4" | Editorial | No | Accepted
i-130 | Stephan Sand | German Aerospace Center (DLR) | 472 | 10.26.8.6 | 8 | Reference to "6.9.6.4" of 802.15.4z-2020 | Please replace with "10.26.6.4" | Editorial | No | Accepted
i-131 | Stephan Sand | German Aerospace Center (DLR) | 472 | 10.26.8.6 | 8 | Reference to "6.9.6.5" of 802.15.4z-2020 | Please replace with "10.26.6.5" | Editorial | No | Revised | Line number is wrong, it should be 11. Otherwise accepted.
i-6 | Billy Verso | Qorvo | 481 | 10.27.2.1 | 7 | This is the only place RSTUs is used. Since this is a unit abbriviation you don’t need the "s", Normally it is 5 cm and 1cm, not 5 cms. If you want a plural write long hand expansion "centimeters". | Change to "RSTU" | Technical | No | Accepted
i-2 | Billy Verso | Qorvo | 486 | 10.29.1 | 1 | Old 4z typo "The RDM IE can be omitted from the RDM in the case..." should read "The RDM IE can be omitted from the RCM in the case.." | Change 13th word on the line from "RDM" to "RCM". | Technical | Yes | Accepted
i-3 | Billy Verso | Qorvo | 486 | 10.29.2 | 26 | There is no reason why a capital S is used for "Slot zero" here, lower case is used in two other cases. | Change to "slot zero". | Editorial | Yes | Accepted
i-86 | Alex Krebs | Apple Inc | 488 | 10.29.2 | 20 | Math symbols have unreadable encoding | maintain 802.15.4z notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-4 | Billy Verso | Qorvo | 509 | 10.29.8.3 | 5 | I notice the following "If the field value is one, it indicates that ranging slots are scheduled for the exchange of deferred data frame(s) after the ranging cycle, …", which is the only use of the term "ranging cycle" in the whole std and this is not defined. | Change to: "If the field value is one, it indicates that ranging slots are scheduled for the TRANSMISSION of deferred data frame(s) after the ranging EXCHANGE, …" (not using the capitals of course, which I have put in here to clearly show the changed words.. | Technical | Yes | Accepted
i-87 | Alex Krebs | Apple Inc | 520 | 10.30.2.2 | 8 | Math symbols have unreadable encoding | maintain 802.15.4z notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-132 | Li-Hsiang Sun | Mediatek | 546 | 10.33.1 | 18 | In figure 10-263, the right most 2 nodes is labeld wrong | change labels to "Device B_M MAC" and "Device B_M next higher layer" | Editorial | No |  |  |  |  | Technical, proposed accept
i-134 | Henk de Ruijter | Silicon Labs | 593 | 12.3.2 | 2 | phyCcaDuration is too long for SUN OFDM (960 us). 802.11ah has much shorter CCA times (< 40 us) which works unfavorable for SUN OFDM. | Specify the phyCcaDuration for SUN OFDM as: "For the SUN OFDM PHY, the default value is 16 divided by the nominal bandwidth in Hertz, as specified in Table 21-10." | Technical |  | Revised | The I-r181 will move phy specufic values to the phy clause. This means we need to define it there. Add new 21.5.14 Cca having content of “The recommended value of phyCcaDuration is 16 divided by the nominal bandwidth in hertz, as specified in Table 21-10.”
i-99 | Riku Pirhonen | NXP | 642 | 16.2.6.2 | 89 | Add explanation of an issue with lentght 127 code Ci 10 at end of the paragraph. | [... Table 16-8 as well.] When using length 127 ternary codes, use of preamble code Ci 10 should be avoided with BPRF SP0, SP1 and SP2. Preamble code is used to initialize the spreading LFSR as described in sub-clause 16.3.2. In case of Ci 10, it results in a scrambling sequence that has series of constant values, and scrambling is not consistently efficient. | General | No |  |  |  | Ben, Billy
i-7 | Lei Huang | Huawei | 643 | 16.2.6.2 | 1 | Code indexed 13 is reserved for DPS only and should not be used for HRP UWB channels 4, 7, 11 and 15. | In the note a of Table 16-8, change "codes indexed 9 through 13" to "codes indexed 9 through 12". | Technical | Yes |  |  |  | Ben, Billy
i-8 | Lei Huang | Huawei | 643 | 16.2.6.2 | 1 | Code indexed 13 is reserved for DPS only and should not be used for HRP UWB channels 4, 7, 11 and 15. | In the note a of Table 16-8, change "codes indexed 9 through 13" to "codes indexed 9 through 12". | Technical | Yes |  |  |  | Ben, Billy
i-9 | Lei Huang | Huawei | 643 | 16.2.6.2 | 1 | Code indexed 13 is reserved for DPS only and should not be used for HRP UWB channels 4, 7, 11 and 15. | In the note a of Table 16-8, change "codes indexed 9 through 13" to "codes indexed 9 through 12". | Technical | Yes |  |  |  | Ben, Billy
i-10 | Lei Huang | Huawei | 643 | 16.2.6.2 | 1 | Code indexed 13 is reserved for DPS only and should not be used for HRP UWB channels 4, 7, 11 and 15. | In the note a of Table 16-8, change "codes indexed 9 through 13" to "codes indexed 9 through 12". | Technical | Yes |  |  |  | Ben, Billy
i-11 | Lei Huang | Huawei | 643 | 16.2.6.2 | 1 | Code indexed 13 is reserved for DPS only and should not be used for HRP UWB channels 4, 7, 11 and 15. | In the note a of Table 16-8, change "codes indexed 9 through 13" to "codes indexed 9 through 12". | Technical | Yes |  |  |  | Ben, Billy
i-12 | Lei Huang | Huawei | 643 | 16.2.6.2 | 1 | Code indexed 13 is reserved for DPS only and should not be used for HRP UWB channels 4, 7, 11 and 15. | In the note a of Table 16-8, change "codes indexed 9 through 13" to "codes indexed 9 through 12". | Technical | Yes |  |  |  | Ben, Billy
i-13 | Lei Huang | Huawei | 643 | 16.2.6.2 | 1 | Code indexed 13 is reserved for DPS only and should not be used for HRP UWB channels 4, 7, 11 and 15. | In the note a of Table 16-8, change "codes indexed 9 through 13" to "codes indexed 9 through 12". | Technical | Yes |  |  |  | Ben, Billy
i-14 | Lei Huang | Huawei | 643 | 16.2.6.2 | 1 | Code indexed 13 is reserved for DPS only and should not be used for HRP UWB channels 4, 7, 11 and 15. | In the note a of Table 16-8, change "codes indexed 9 through 13" to "codes indexed 9 through 12". | Technical | Yes |  |  |  | Ben, Billy
i-88 | Alex Krebs | Apple Inc | 652 | 16.3.1 | 21-27 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-89 | Alex Krebs | Apple Inc | 653 | 16.3.2 | 13, 14 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-90 | Alex Krebs | Apple Inc | 654 | 16.3.2 | 10,11 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-91 | Alex Krebs | Apple Inc | 655 | 16.3.3.2 | 14, 15, 16, 23 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-92 | Alex Krebs | Apple Inc | 656 | 16.3.3.2 | 3 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-93 | Alex Krebs | Apple Inc | 662 | 16.4.4 | 12 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-100 | Riku Pirhonen | NXP | 662 | 16.4.4 | 9 | 16.4.4 defines symmetric and precursor free pulse shapes. Precursor free pulse shape is defined by figure 16-24, so it is unnecessary and counterintuitive to define requirements for it also using cross-correlation with a symmetric reference pulse. On the other hand, symmetric pulse cannot use the mask in figure 16-24, so the requirements for the symmetric pulse can be set using cross-correlation with a symmetric reference pulse. Proposal separates the requirements for symmetric and precursor free pulse. | Replace "The transmitted pulse shape…" with "The transmitted symmetric pulse shape…" | Technical | No |  |  |  | Ben, Billy
i-15 | Kristian Granhaug | Novelda | 663 | 16.4.4 | 19 | "Butterworth pulse" is not well-defined. Suggest to use "Butterworth filter" instead. Also capital 'B'. | "The pulse p(t) is an 8 order butterworth pulse" => "The pulse p(t) is derived from an 8th order Butterworth filter" | Editorial | No |  |  |  |  | Technical, changing butterworth to Butterworth in the whole document is editorial, and is accepted.
i-94 | Alex Krebs | Apple Inc | 663 | 16.4.4 | 3,4,12-18, | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-101 | Riku Pirhonen | NXP | 663 | 16.4.4 | 7 | see above | Replace ", the transmitted pulse" with ", the transmitted symmetric pulse" | Technical | No |  |  |  | Ben, Billy
i-102 | Riku Pirhonen | NXP | 663 | 16.4.4 | 17 - 22 | Remove references to the cross correlation test for precursor free pulse | Remove paragraph on lines 17-22 | Technical | No |  |  |  | Ben, Billy
i-103 | Riku Pirhonen | NXP | 663 | 16.4.4 | 26 - 28 | Remove reference to figure 15-13 (which actually should have been 16-23, but remove anyway) | Remove "In Figure 15-13, the middle ... Pulses are recommended". | [5 empty] | Ben, Billy
i-104 | Riku Pirhonen | NXP | 664 | 16.4.4 | 1 | Remove references to the cross correlation test for precursor free pulse | Remove figure 16-23 | Technical | No
i-105 | Riku Pirhonen | NXP | 664 | 16.4.4 | 6 | Reference is to old table number | replace "Table 15-12" with "Table 16-28" | Editorial | No | Accepted
i-95 | Alex Krebs | Apple Inc | 667 | 16.5.2 | 10-13 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-96 | Alex Krebs | Apple Inc | 668 | 16.5.3 | 9,15 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-97 | Alex Krebs | Apple Inc | 669 | 16.5.4 | 8 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-135 | Henk de Ruijter | Silicon Labs | 718 | 20.5 | 14-16 | This may not be optimal if the higher center frequency is further away compared to the next lower center frequency. | Align with Wi-SUN PHY TPS (Annex B): "The channel of the new PHY operating mode shall be the one with center frequency closest to that of the original channel used for the mode switch PPDU. If there are two channels that are equally distant from the original channel, the higher channel shall be used." | Technical |  | Revised | Change “If not, the center frequency shall be the next higher available center frequency of the new mode. If there is no higher center frequency available in the new mode, it shall use the next lower available center frequency of the new mode.” to “The channel of the new PHY operating mode shall be the one with center frequency closest to that of the original channel used for the mode switch PPDU. If there are two channels that are equally distant from the original channel, the higher channel shall be used."
i-136 | Henk de Ruijter | Silicon Labs | 718 | 20.5 | 18-19 | Wording could be improved | Change to "If a device does not support mode switch or mode switch is not enabled..." | Editorial |  | Accepted
i-137 | Henk de Ruijter | Silicon Labs | 718 | 20.5 | 20-22 | Settling delay for FSK to FSK is not necesarilly shorter compared for FSK to another modulation scheme. Also, 510 us may be too short, especially when CSMA/CA is needed during the settling time. | Remove modulation scheme dependencies and align better with Wi-SUN by specifying a max settling time of 1.5 ms. | Technical |  | Revised | Change “If the modulation scheme of the new mode is FSK, the settling delay shall be in the range of zero to 100 µs. If the modulation scheme of the new mode is not FSK, the settling delay shall be in the range of 200 µs to 500 µs.” to “The settling delay shall be in the range of 510 µs to 1.5 ms”
i-18 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 799 | 24 | 1 | Introduction Section is missing | Add introduction section 24.1. Text will be provided by e-mail | Editorial | No |  |  |  | Joerg | Revised
i-19 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 799 | 24.2.1 | 18 | Refrence is wrong, should be Figure 24-2 | Change "Figure 24-1" to "Figure 24-2" | Editorial | Yes | Accepted
i-20 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 799 | 24.2.1 |  | Figure caption is wrong, should be Figure 24-2 | Change "Figure 24-1" to "Figure 24-2" | Editorial | Yes | Accepted
i-21 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 800 | 24.2.2.3 | 12 | It is not clear that 24.2.2.3 only applies to the non-split mod. | Add text that indicates 24.2.2.3 is only relevant for the non-split mode. | Editorial | No |  |  |  | Joerg | Revised
i-22 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 800 | 24.2.2.1 | 3 | Refrence is wrong, should be Figure 24-3 | Change "Figure 24-2" to "Figure 24-3" | Editorial | Yes | Accepted
i-23 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 800 | 24.2.2.1 |  | Figure caption is wrong, should be Figure 24-3 | Change "Figure 24-2" to "Figure 24-3" | Editorial | Yes | Accepted
i-24 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 800 | 24.2.2.3 | 13 | Refrence is wrong, should be Figure 24-4 | Change "Figure 24-3" to "Figure 24-4" | Editorial | Yes | Accepted
i-25 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 800 | 24.2.2.3 |  | Figure caption is wrong, should be Figure 24-4 | Change "Figure 24-3" to "Figure 24-4" | Editorial | Yes | Accepted
i-26 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 800 | 24.2.3 | 16 | Refrence is wrong, should be Figure 24-5 | Change "Figure 24-4" to "Figure 24-5" | Editorial | Yes | Accepted
i-27 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 800 | 24.2.3 |  | Figure caption is wrong, should be Figure 24-5 | Change "Figure 24-4" to "Figure 24-5" | Editorial | Yes | Accepted
i-28 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 801 | 24.2.5 | 9 | It is not clear that 24.2.5 only applied to the split mode. | Add text that indicates 24.2.5 is onyl relevant for the split mode. | Editorial | No |  |  |  | Joerg | Revised
i-29 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 801 | 24.2.5 | 10 | Refrence is wrong, should be Figure 24-6 | Change "Figure 24-5" to "Figure 24-6" | Editorial | Yes | Accepted
i-30 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 801 | 24.2.5 |  | Figure caption is wrong, should be Figure 24-6 | Change "Figure 24-5" to "Figure 24-6" | Editorial | Yes | Accepted
i-31 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 801 | 24.2.5 | 12 | Refrence is wrong, should be Figure 24-7 | Change "Figure 24-6" to "Figure 24-7" | Editorial | Yes | Accepted
i-32 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 801 | 24.2.5 |  | Figure caption is wrong, should be Figure 24-7 | Change "Figure 24-6" to "Figure 24-7" | Editorial | Yes | Accepted
i-33 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 801 | 24.3.1 | 18 | Refrence is wrong, should be Table 24-1 | Change "Figure 24-10" to "Table 24-1" | Editorial | Yes | Accepted
i-34 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 801 | 24.3.1 |  | Table caption is wrong, should be Table 24-1 | Change "Table 24-8" to "Table 24-1" | Editorial | Yes | Accepted
i-35 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 802 | 24.3.1 |  | Table caption is wrong, should be still Table 24-1 | Change "Table 24-8" to "Table 24-1" | Editorial | Yes | Accepted
i-36 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 803 | 24.3.2 | 2 | Figure captions are wrong. Additional full stop. | Change references to "Figure 24-8" and "Figure 24-9", remove additional full stop. | Editorial | Yes | Accepted
i-37 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 803 | 24.3.2 |  | Figure caption is wrong, should be Figure 24-9 (lower figure). Position is not correct. | Change "Figure 24-7" to "Figure 24-9". Move after line 9 on page 804. | Editorial | Yes | Revised | Swap order of the Split mode and Non-split mode reference modulator diagrams, fix figure numbers.
i-38 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 804 | 24.3.2 | 10 | It is not clear that the following text only applies to the split mode. | Add text that indicates that the followig text until the end of 24.3.2 only applies to the split mode. | Editorial | Yes |  |  |  | Joerg | Revised
i-39 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 804 | 24.3.3 | 23 | References are wrong, should be Table 24-2 and Table 24-3 | Change "Table 24-1" to "Table 24-2" and "Table 24-2" to "Table 24-3" | Editorial | Yes | Accepted
i-40 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 804 | 24.3.3 |  | Table caption is wrong, should be "Table 24-2" (upper table) | Change "Table 24-1" to "Table 24-2" | Editorial | Yes | Accepted
i-41 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 804 | 24.3.3 |  | Table caption is wrong, should be "Table 24-3" lower table) | Change "Table 24-2" to "Table 24-3" | Editorial | Yes | Accepted
i-42 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 805 | 24.3.4.2 | 7 | It is not clear that the text starting in line 7 until the end of 24.3.4.2 only applied for split mode. | Add clarification that text starting in line 7 is only relevant for split mode. | Editorial | No |  |  |  | Joerg | Revised
i-43 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 805 | 24.3.4.2 | 8 | Reference is wrong, should be "Figure 24-10" | Change "Figure 24-9" to "Figure 24-10" | Editorial | Yes | Accepted
i-44 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 805 | 24.3.4.2 | 11 | Reference is wrong, should be "Figure 24-10" | Change "Figure 24-9" to "Figure 24-10" | Editorial | Yes | Accepted
i-45 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 805 | 24.3.4.2 | 12 | Reference is wrong, should be "Figure 24-10" | Change "Figure 24-9" to "Figure 24-10" | Editorial | Yes | Accepted
i-46 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 805 | 24.3.4.3 | 18 | Reference is wrong, should be "Figure 24-10" | Change "Figure 24-9" to "Figure 24-10" | Editorial | Yes | Accepted
i-47 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 806 | 24.3.5.2 | 6 | Space is missing after "K=7," | Add missing space | Editorial | No | Accepted
i-48 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 806 | 24.3.5.2 | 7 | Reference is wrong, should be "Figure 24-11" | Change "Figure 24-10" to "Figure 24-11" | Editorial | Yes | Accepted
i-49 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 806 | 24.3.5.2 |  | Figure caption is wrong, should be Figure 24-11 | Change "Figure 24-10" to "Figure 24-11" | Editorial | Yes | Accepted
i-50 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 806 | 24.3.5.2 | 16 | Reference is wrong, should be "Figure 24-12" | Change "Figure 24-11" to "Figure 24-12" | Editorial | Yes | Accepted
i-51 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 806 | 24.3.5.2 |  | Figure caption is wrong, should be Figure 24-12 (lowre figure) | Change "Figure 24-11" to "Figure 24-12" | Editorial | Yes | Accepted
i-52 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 806 | 24.3.5.2 | 22 | Reference to table is wrong, should be "Table 24-5" | Change "Table 24-4" to "Table 24-5" | Editorial | Yes | Accepted
i-53 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 807 | 24.3.5.2 | 1 | Reference to figure is wrong, should be "Figure 24-12" | Change "Figure 24-11" to "Figure 24-12" | Editorial | Yes | Accepted
i-54 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 807 | 24.3.5.2 | 6 | Reference to table is wrong, should be "Table 24-5" | Change "Table 24-4" to "Table 24-5" | Editorial | Yes | Accepted
i-55 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 807 | 24.3.5.3.2 | 16 | Reference to figure is wrong, should be "Figure 24-13" | Change "Figure 24-12" to "Figure 24-13" | Editorial | Yes | Accepted
i-56 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 807 | 24.3.5.3.2 |  | Figure caption is wrong, should be Figure 24-13 | Change "Figure 24-12" to "Figure 24-13" | Editorial | Yes | Accepted
i-57 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 807 | 24.3.5.3.2 | 17 | Reference to figure is wrong, should be "Figure 24-11" | Change "Figure 23-6" to "Figure 24-10" | Editorial | Yes | Accepted
i-58 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 807 | 24.3.5.3.3 | 25 | Reference to figure is wrong, should be "Figure 24-13" | Change "Figure 24-13" to "Figure 24-13" | Editorial | Yes | Accepted
i-59 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 808 | 24.3.5.3.3 |  | Figure caption is wrong, should be Figure 24-14 (top figure) | Change "Figure 23-13" to "Figure 24-13" | Editorial | Yes | Accepted
i-60 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 808 | 24.3.5.3.4 | 8 | Reference to figure is wrong, should be "Figure 24-15" | Change "Figure 23-14" to "Figure 24-15" | Editorial | Yes | Accepted
i-61 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 808 | 24.3.5.3.4 |  | Figure caption is wrong, should be Figure 24-15 (bottom figure) | Change "Figure 23-14" to "Figure 24-15" | Editorial | Yes | Accepted
i-62 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 808 | 24.3.5.3.4 | 20 | Reference to table is wrong, should be "Table 24-4" | Change "Table 24-3" to "Table 24-4" | Editorial | Yes | Accepted
i-63 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 809 | 24.3.5.3.4 | 16 | Reference to table is wrong, should be "Table 24-4" | Change "Table 24-3" to "Table 24-4" | Editorial | Yes | Accepted
i-64 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 809 | 24.3.5.3.4 | 17 | Reference to table is wrong, should be "Table 24-4" | Change "Table 24-3" to "Table 24-4" | Editorial | Yes | Accepted
i-65 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 809 | 24.3.5.3.4 |  | Table caption is wrong, should be "Table 24-4" | Change "Table 24-3" to "Table 24-4" | Editorial | Yes | Accepted
i-66 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 810 | 24.3.5.3.4 |  | Table caption is wrong, should be "Table 24-4" | Change "Table 24-3" to "Table 24-4" | Editorial | Yes | Accepted
i-67 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 810 | 24.3.6 |  | It is not clear that this section only applies to the non-split mode | Clarify that text is only valid for non-split mode. | Editorial | No |  |  |  | Joerg | Revised
i-68 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 811 | 24.3.6 | 4 | Reference to table is wrong, should be "Table 24-5" | Change "Table 24-4" to "Table 24-5" | Editorial | Yes | Accepted
i-69 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 811 | 24.3.6 |  | Table caption is wrong, should be "Table 24-5" | Change "Table 24-4" to "Table 24-5" | Editorial | Yes | Accepted
i-70 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 811 | 24.3.6 | 6 | Reference to table is wrong, should be "Table 24-5" | Change "Table 24-4" to "Table 24-5" | Editorial | Yes | Accepted
i-71 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 811 | 24.3.7.1 | 13 | Reference to table is wrong, should be "Table 24-6" | Change "Table 24-15" to "Table 24-6" | Editorial | Yes | Accepted
i-72 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 811 | 24.3.7.1 |  | Table caption is wrong, should be "Table 24-6" | Change "Figure 24-15" to "Table 24-6" | Editorial | Yes | Accepted
i-73 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 813 | 24.3.7.3 | 1 | Reference to table is wrong, should be "Table 24-7" | Change "Table 24-5" to "Table 24-7" | Editorial | Yes | Accepted
i-74 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 813 | 24.3.7.3 |  | Table caption is wrong, should be "Table 24-7" | Change "Table 24-5" to "Table 24-7" | Editorial | Yes | Accepted
i-75 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 814 | 24.3.8.2 | 6 | Reference to table is wrong, should be "Table 24-8" | Change "Table 24-6" to "Table 24-8" | Editorial | Yes | Accepted
i-76 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 814 | 24.3.8.2 |  | Table caption is wrong, should be "Table 24-8" | Change "Table 24-6" to "Table 24-8" | Editorial | Yes | Accepted
i-77 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 814 | 24.3.8.2 | 9 | Reference to table is wrong, should be "Table 24-9" | Change "Table 24-7" to "Table 24-9" | Editorial | Yes | Accepted
i-78 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 815 | 24.3.8.2 |  | Table caption is wrong, should be "Table 24-9" | Change "Table 24-7" to "Table 24-9" | Editorial | Yes | Accepted
i-79 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 817 | 24.3.10 | 2 | Reference to table is wrong, should be "Table 24-10" | Change "Table 24-8" to "Table 24-10" | Editorial | Yes | Accepted
i-80 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 817 | 24.3.10 |  | Table caption is wrong, should be "Table 24-10" | Change "Table 24-8" to "Table 24-10" | Editorial | Yes | Accepted
i-81 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 818 | 24.5 | 12 | Reference is wrong, should reference section and not figure | Change "in Figure 23.3" to "in 23.3" | Editorial | Yes | Accepted
i-82 | Joerg Robert | TU Ilmenau/Fraunhofer IIS | 819 | 24.6.5 | 17 | "-" should be in front of number and not on the next line | Move "-" in front of 97dBm | Editorial | Yes | Accepted
i-16 | Kristian Granhaug | Novelda | 858 | 27.3.13 | 6 | Suggest to use "intersymbol interference" for consistency across other clauses. | "inter-symbol" => "intersymbol" | Editorial | No | Accepted
i-5 | Billy Verso | Qorvo | 871 | 29 | 1 | This CMB PHY clause should be clause 30 since the previous clause RCC DSSS BPSK PHY is also clause 29. | Change numbering of this and subsequent clauses to follow each other, (so that this clause is clause 30). | Editorial | Yes | Accepted
i-98 | Alex Krebs | Apple Inc | 980 | H.3 | 3-8 | Math symbols have unreadable encoding | maintain 802.15.4-2020 notation/encoding | Editorial | Yes | Rejected | The format of the equations is same as it was n the 4z. If there is something specific that needs to be changed made specific comments explainging the issues.
i-17 | Libra Xiao | NewRadio Technologies Co., Ltd. | [6 empty] | Yes | Rejected | There is no comment, and there is no proposed change.
i-133 | Vinod Kristem | Apple |  |  |  | The figures and Equations throughtout the document are not clear, and difficult to follow | Fix the figures and equations | Editorial | Yes | Rejected | They show up fine on the pdf-viewers I have been using, and I did verify that the fonts are embded.

## LB197_rogue
Comment ID | Name | Affiliation | Page | Sub-clause | Line # | Comment | Proposed Change | Category | Must Be Satisfied? | Disposition Status | Disposition Detail | Done | Assigned | Other3
I-r1 | Tero Kivinen | Self | 6 | Participants line 8 |  | Add WG secretary name here. | Fill in the name. | Editorial | No | Accepted
I-r2 | Tero Kivinen | Self | 13 | Historical_participants line 13 |  | The list of people working for 802.15.4-2020 is missing from here. | Add new text "The following members of the IEEE P802.15 Working Group participated in the development of the third revision, IEEE Std 802.15.4-2020:" and fill in the names. | Editorial | No | Accepted
I-r3 | Tero Kivinen | Self | 15 | Introduction line 1 |  | This text is not about the current revision, but the 2020 revision. | Change this text to describe what 2020 revision did. | Editorial | No |  |  |  | Tero
I-r4 | Tero Kivinen | Self | 15 | Introduction | 9 | The description of what the current revision included is missing. | Add text describing what this current revision added. | Technical | No |  |  |  | Tero
I-r164 | Kunal Shah | Apple | 15 | 1 | 1 | This should capture what is the current revision of the standard is planning to cover. The paragraph needs to be updated to keep what was planned in 2020 from 2015 revision. | Include a new paragraph to state what is this revision is planned to cover. | Editorial | No |  |  |  | Tero
I-r5 | Tero Kivinen | Self | 39 | 3.1 | 12 | Not first use of MAC. | Do not expand here. | Editorial | No | Accepted
I-r6 | Tero Kivinen | Self | 40 | 3.2 | 12 | DCS is only used in one heading. | Remove DCS from acronym list. | Editorial | No | Accepted
I-r7 | Tero Kivinen | Self | 47 | 5.2.3 | 23 | First use of RCC in text. | Expand here. | Editorial | No | Accepted
I-r8 | Tero Kivinen | Self | 47 | 5.2.2 | 17 | First use of SUN in text. | Expand here. | Editorial | No | Accepted
I-r9 | Tero Kivinen | Self | 48 | 5.2.6 | 13 | First use LECIM in text. | Expand here. | Editorial | No | Accepted
I-r10 | Tero Kivinen | Self | 48 | 5.2.7 | 19 | First use of MBAN in text. | Expand here. | Editorial | No | Accepted
I-r11 | Tero Kivinen | Self | 48 | 5.2.5 | 4 | First use of RFID in text. | Expand here. | Editorial | No | Accepted
I-r12 | Tero Kivinen | Self | 49 | 5.4 | 3 | First use MPM in text. | Expand here. | Editorial | No | Accepted
I-r13 | Tero Kivinen | Self | 49 | 5.5.1 | 13 | First use of PAN. | Expand here. | Editorial | No | Accepted
I-r14 | Tero Kivinen | Self | 53 | 5.6.2 | 7 | First use of RS-GFSK. | Do not expand here. | Editorial | No | Accepted
I-r15 | Tero Kivinen | Self | 53 | 5.6.2 | 7 | Is this list of coexistence document complete, do we have some that needs to be added to this list, i.e., did any amendments included contain their own coexistence documents that needs to be added. | Update the list of coexistence documents. | Technical | No
I-r16 | Tero Kivinen | Self | 53 | 5.7.1 | 17 | Add new 5.7.1.1 Overview section that will explain that there is multiple superframe structure types that can be used, or the network can also be formed without using any of them. | Add overview section. Include dashed list of ways of forming superframe structures, and references to them (superframe, dsme, tsch, tmtcp). | Technical | No |  |  |  | Ben
I-r17 | Tero Kivinen | Self | 55 | 5.7.2.3 | 18 | This section only describes indirect transfer. My understanding is that coordinator can also send data directly to the device, without using indirect data transfer, but it is not described here at all. | Add description of sending data from coordinator to device without using indirect data transfer. Or perhaps change section header to say data transfer from a coordinator using indirect data transfer. | Technical | No | Revised | Change title to say indirect data transfer from coordinator, do similar change in 5.7.2.1 list. |  | Tero
I-r18 | Tero Kivinen | Self | 56 | 5.7.4 | 16 | First use of IE in text. | Expand here. | Editorial | No | Accepted
I-r19 | Tero Kivinen | Self | 56 | 5.7.3 | 13 | This is first use of MFR outside figures. | Expand here. | Editorial | No | Accepted
I-r20 | Tero Kivinen | Self | 56 | 5.7.3 | 13 | This is first use of MHR outside figures. | Expand here. | Editorial | No | Accepted
I-r21 | Tero Kivinen | Self | 56 | 5.7.2.4 | 4 | I do not think measures of synchronizing with the originating device are fully outside the scope of this standard. I think RIT for example is one of those. | Remove last sentence of this paragraph. | Technical | No | Accepted
I-r22 | Tero Kivinen | Self | 58 | 5.7.7 | 25 | Add reference to 802.15.9 which describe those security architectural elements. | Add reference to 802.15.9. | Technical | No | Accepted
I-r23 | Tero Kivinen | Self | 61 | 6.3.1 | 21 | First use IFS. | Expand here. | Editorial | No | Accepted
I-r24 | Tero Kivinen | Self | 61 | 6.3.1 | 19 | Expand IFS in the header, so it will get expanded in the table of content. | Expand IFS in header. | Editorial | No | Accepted
I-r25 | Tero Kivinen | Self | 64 | 6.4.1.1 | 30 | This is not first use of ED. | Do not expand here. | Editorial | No | Accepted
I-r26 | Tero Kivinen | Self | 64 | 6.3.2.1 | 9 | Remove reference to LBT and 920 from here. | Remove the text between "i.e. two... [B4]". | Technical | No | Accepted
I-r27 | Tero Kivinen | Self | 64 | 6.3.2.1 | 19 | Remove reference to LBT. | The CCA already has LBT built in using phyCcaDuration, so there is no need to mention it here. Remove text between "i.e., ... LBT,". | Technical | No | Accepted
I-r28 | Tero Kivinen | Self | 64 | 6.4.1.1 | 30 | Combine list of optional scans. | Change "In addition, device may be able to perform ED, active, or enhanced active scan.". Or should it be "may perform" without "able to". | Technical | No | Accepted
I-r29 | Tero Kivinen | Self | 64 | 6.4.1.1 | 29 | Orphan scan feature has been moved to section 10, thus it is optional. | Move orphan scan from line 29 to line 30 and include it in the list of optional scans. | Technical | No | Accepted
I-r30 | Tero Kivinen | Self | 64 | 6.4.1.2 | 40 | ED channel scan is optional to implement, thus this should be moved to the section 10. | Move ED channel chan to section 10. | Technical | No | Accepted
I-r31 | Tero Kivinen | Self | 65 | 6.4.1.3 | 9 | Active scan and enhanced active scan are both optional, and should be moved to section 10. Only passive channel scan is mandatory. | Split accordingly and move active scan part to section 10. Lines 11-13, figure 6-3, 20-P66L8, P66L20, P67L7-14, P67L19-25 should be moved there. This should include both normal active scan and enhanced active scan. | Technical | No | Accepted
I-r32 | Tero Kivinen | Self | 68 | 6.4.2.2 | 5 | Description of SUN specific processing should be moved to 10.13, creating new section 10.13.2 Starting a pan there. | Move sentece "If the device is a SUN...as described in 10.8.3" to new 10.13.2. | Technical | No | Accepted
I-r33 | Tero Kivinen | Self | 68 | 6.4.2.2 | 12 | Superframe specific feature should be moved to 10.2. | Move "On receipt of this primitive ... as specified in 10.2.2.6" to new section 10.2.3 Starting a PAN, and rewrite to match. | Technical | No | Accepted
I-r34 | Tero Kivinen | Self | 68 | 6.4.2.3 | 22 | Remove word "superframe". | I.e., say using current configuration, so this text is not superframe structure specific. | Technical | No | Accepted
I-r35 | Tero Kivinen | Self | 69 | 6.4.2.3 | 3 | Remove word "superframe". | I.e., say the new configuration, so this text is not superframe structure specific. | Technical | No | Accepted
I-r36 | Tero Kivinen | Self | 69 | 6.4.2.3 | 4 | Remove word "as described in 10.2.2.6". | The description only applies to superframe structure, but this can be used to change channel etc even when not using superframe structure. | Technical | No | Accepted
I-r37 | Tero Kivinen | Self | 70 | 6.4.3 | 5 | This whole section is only relevant in the superframe structure and needs to be moved to 10.2.x. | Move to section 10.2. | Technical | No
I-r38 | Tero Kivinen | Self | 71 | 6.4.3 | 13 | Is the text about 920 MHz band still needed. We changed the CCA to include LBT, and I think that covers this case too. | Remove first sentence of paragraph. | Technical | No
I-r39 | Tero Kivinen | Self | 71 | 6.4.3 | 14 | There is no way MAC can ensure anything. | Remove last sentence of the paragraph. | Technical | No
I-r40 | Tero Kivinen | Self | 71 | 6.4.4 | 17 | This whole section is only relevant in the superframe structure and needs to be moved to 10.2.x. | Move to section 10.2. | Technical | No
I-r41 | Tero Kivinen | Self | 72 | 6.5.2 | 7 | This whole section is only relevant in the superframe structure and needs to be moved to 10.2.x. | Move to section 10.2. | Technical | No
I-r42 | Tero Kivinen | Self | 73 | 6.5.3 | 18 | This section is about indirect transfer. | Move to 10.19, or remove completely. | Technical | No
I-r43 | Tero Kivinen | Self | 74 | 6.5.4 | 4 | This is about Orphan channel scan, move to 10.17. | Move this to 10.17.1. | Technical | No
I-r44 | Tero Kivinen | Self | 74 | 6.6 | 17 | This is about indirect transmissions. | Move to 10.19 and rename it to Indirect transmissions. | Technical | No
I-r45 | Tero Kivinen | Self | 75 | 6.6 | 14 | Remove TSCH mode sentence. | Remove "TSCH mode indirect behavior is further described in 7.2.2.4". | Technical | No
I-r46 | Tero Kivinen | Self | 75 | 6.7.1 | 26 | There is no point of telling that algorithm for random number is outside this scope of this standard. | Remove ", the algorithm ... this standard". | Technical | No
I-r47 | Tero Kivinen | Self | 75 | 6.7.1 | 33 | There is no point of telling that algorithm for random number is outside this scope of this standard. | Remove ", the algorithm ... this standard". | Technical | No
I-r48 | Tero Kivinen | Self | 75 | 6.7.1 | 40 | There is no point of telling that algorithm for random number is outside this scope of this standard. | Remove ", the algorithm ... this standard". | Technical | No
I-r49 | Tero Kivinen | Self | 76 | 6.7.1 | 3 | Move this note after the DSN, it is not relevant to BSN or EBSN. | Move to P75L32. | Editorial | No | Accepted
I-r50 | Tero Kivinen | Self | 76 | 6.7.1 | 13 | It is assumed to be PAN coordinator only if macImplicitBroadcast is FALSE. | Add macImplicitBroadcast description here. | Technical | No
I-r51 | Tero Kivinen | Self | 76 | 6.7.1 | 18 | Lines 18-20 seems to be about beacon enabled PAN not tracking beacons i.e., most likely not using superframe structure, but still it requires to use macBeaconOrder etc. | Is the current text matching what people are implementing when using beacon-enabled PANs without superframe structure? If not update to match what they are doing. | Technical | No
I-r52 | Tero Kivinen | Self | 77 | 6.7.2 | 2 | First paragraph is some specific ranging feature, thus needs to be moved to 10.30. | Move first paragraph to 10.30. | Technical | No
I-r53 | Tero Kivinen | Self | 77 | 6.7.2 | 42 | Extra "." between "frame" and "and". | Remove "." | Editorial | No | Accepted
I-r54 | Tero Kivinen | Self | 77 | 6.7.2 | 40 | Extra "." between "command" and "and". | Remove "." | Editorial | No | Accepted
I-r55 | Tero Kivinen | Self | 78 | 6.7.2 | 8 | This is first use of AR. | Expand here. | Editorial | No | Accepted
I-r56 | Tero Kivinen | Self | 78 | 6.7.2 | 36 | First use HRP-ERDEV. | Expand here. | Editorial | No | Accepted
I-r57 | Tero Kivinen | Self | 78 | 6.7.2 | 35 | First use of MSDU. | Expand here. | Editorial | No | Accepted
I-r58 | Tero Kivinen | Self | 78 | 6.7.2 | 38 | First use of PHR outside figures. | Expand here. | Editorial | No | Accepted
I-r59 | Tero Kivinen | Self | 78 | 6.7.2 | 36 | First use SP3. | Expand here. | Editorial | No | Accepted
I-r60 | Tero Kivinen | Self | 78 | 6.7.2 | 41 | First use STS. | Expand here. | Editorial | No | Accepted
I-r61 | Tero Kivinen | Self | 79 | 6.7.3.3 | 29 | First use SHR in text. | Expand here. | Editorial | No | Accepted
I-r62 | Tero Kivinen | Self | 80 | 6.7.3.3 | 3 | First use of RFRAME. | Expand here. | Editorial | No | Accepted
I-r63 | Tero Kivinen | Self | 80 | 6.7.3.3 | 3 | The text "shall be contained in an RFRAME" is not clear, I can see how the ACK frame can BE RFFRAME, but I can't see how it can be contained in the RFRAME. | Rewrite to make sense. | Technical | No
I-r64 | Tero Kivinen | Self | 91 | 7.2.11 | 8 | This is first use of HPRF. | Expand here. | Editorial | No | Accepted
I-r65 | Tero Kivinen | Self | 132 | 8.2.6.2 | 26 | This is first use of ERDEV. | Expand here. | Editorial | No | Accepted
I-r66 | Tero Kivinen | Self | 132 | 8.2.6.2 | 24 | First use of RSTU. | Expand here. | Editorial | No | Accepted
I-r67 | Tero Kivinen | Self | 149 | 8.2.10.1 | 6 | First use of MPDU. | Expand here. | Editorial | No | Accepted
I-r68 | Tero Kivinen | Self | 152 | 8.3.1 | 9 | First use of RDEV. | Expand here. | Editorial | No | Accepted
I-r69 | Tero Kivinen | Self | 153 | 8.3.1 | 7 | This is first use of FoM. | Expand here. | Editorial | No | Accepted
I-r70 | Tero Kivinen | Self | 153 | 8.3.1 | 4 | This is first use of RMARKER. | Expand here. | Editorial | No | Accepted
I-r71 | Tero Kivinen | Self | 178 | 9.2.2 | 43 | This is first use of ASN. | Expand here. | Editorial | No | Accepted
I-r72 | Tero Kivinen | Self | 184 | 9.2.10 | 33 | secAllowedSecurityLevels reference seems to be broken. | Fix all sec* reference links. | Editorial | No | Accepted
I-r73 | Tero Kivinen | Self | 185 | 9.3.1 | 16 | Hanging paragraph. | Create new section 9.3.1.1 General, and move all text between 9.3.1 and 9.3.1.1 to that new section. | Editorial | No | Accepted
I-r74 | Tero Kivinen | Self | 187 | 9.3.2.3 | 6 | This is first use of FSCD. | Expand here. | Editorial | No | Accepted
I-r75 | Tero Kivinen | Self | 199 | 10.2.1 | 7 | Section is missing text. | Write overview of the feature. | Technical | No
I-r76 | Tero Kivinen | Self | 204 | 10.3.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r77 | Tero Kivinen | Self | 206 | 10.3.2.3.2 | 34 | This is not first use of ASN. | Do not expand here. | Editorial | No | Accepted
I-r78 | Tero Kivinen | Self | 269 | 10.5.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r79 | Tero Kivinen | Self | 277 | 10.6.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r80 | Tero Kivinen | Self | 281 | 10.6.4 | 17 | First use if I-RIT in text. | Expand here. | Editorial | No | Accepted
I-r81 | Tero Kivinen | Self | 293 | 10.7.3.1 | 2 | This is first use of FEC. | Expand it here. | Editorial | No | Accepted
I-r82 | Tero Kivinen | Self | 293 | 10.7.3.1 | 1 | This is first use of FSK. | Expand it here. | Editorial | No | Accepted
I-r83 | Tero Kivinen | Self | 293 | 10.7.3.1 | 14 | First use of OFDM. | Expand here. | Editorial | No | Accepted
I-r84 | Tero Kivinen | Self | 293 | 10.7.3.1 | 13 | First use of SFD in text. | Expand the second SFD, the first is "SFD Length" which is name of the field. | Editorial | No | Accepted
I-r85 | Tero Kivinen | Self | 304 | 10.7.3.6 | 2 | This is only use of EIRP in the whole standard. | Remove the EIRP from section 3.2 acronym list and remove the acronym from here. | Editorial | No | Accepted
I-r86 | Tero Kivinen | Self | 307 | 10.8.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r87 | Tero Kivinen | Self | 319 | 10.9.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r88 | Tero Kivinen | Self | 324 | 10.10.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r89 | Tero Kivinen | Self | 324 | 10.10.2.1 | 5 | Not first use of MSDU. | Do not expand here. | Editorial | No | Accepted
I-r90 | Tero Kivinen | Self | 327 | 10.10.2.2 | 17 | Not first use of MPDU. | Do not expand here. | Editorial | No | Accepted
I-r91 | Tero Kivinen | Self | 330 | 10.12.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r92 | Tero Kivinen | Self | 336 | 10.13.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r93 | Tero Kivinen | Self | 336 | 10.13.2.1 | 16 | Not first use of NRNSC on line 16, first use is on line 15. | Do not expand on line 16. | Editorial | No | Accepted
I-r94 | Tero Kivinen | Self | 344 | 10.14.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r95 | Tero Kivinen | Self | 354 | 10.15.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r96 | Tero Kivinen | Self | 357 | 10.16.3 | 22 | This is not first use of AR. | Do not expand here. | Editorial | No | Accepted
I-r97 | Tero Kivinen | Self | 359 | 10.17.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r98 | Tero Kivinen | Self | 363 | 10.18.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r99 | Tero Kivinen | Self | 411 | 10.24.1 | 2 | Section is missing text. | Write overview of the feature. | Technical | No
I-r100 | Tero Kivinen | Self | 416 | 10.25.2.6 | 15 | First use of RCPI in text. | Expand here. | Editorial | No | Accepted
I-r101 | Tero Kivinen | Self | 416 | 10.25.2.6 | 16 | Table 10-124 link is broken. | Fix reference link. | Editorial | No | Accepted
I-r102 | Tero Kivinen | Self | 417 | 10.25.2.7 | 11 | First use of RSNI in text. | Expand here. | Editorial | No | Accepted
I-r103 | Tero Kivinen | Self | 418 | 10.25.2.8 | 15 | First use of RSSI in text. | Expand here. | Editorial | No | Accepted
I-r104 | Tero Kivinen | Self | 447 | 10.26.1.1 | 5 | This is not first use of FoM. | Do not expand here. | Editorial | No | Accepted
I-r105 | Tero Kivinen | Self | 447 | 10.26.1.1 | 20 | Not first use of HRP-ERDEV. | Do not expand here. | Editorial | No | Accepted
I-r106 | Tero Kivinen | Self | 447 | 10.26.1.1 | 4 | This is not first use of RDEV. | Do not expand here. | Editorial | No | Accepted
I-r107 | Tero Kivinen | Self | 447 | 10.26.1.1 | 30 | This is not first use of RFRAME. | Do not expand here. | Editorial | No | Accepted
I-r108 | Tero Kivinen | Self | 447 | 10.26.1.1 | 38 | This is not first use of RMARKER. | Do not expand here. | Editorial | No | Accepted
I-r109 | Tero Kivinen | Self | 447 | 10.26.1.1 | 32 | This is not first use of SP3. | Do not expand here. | Editorial | No | Accepted
I-r165 | Kunal Shah | Apple | 448 | 10.26.1.2.2 | 33 | Extra spacing between paragraphs | See comment | Editorial | No | Accepted
I-r110 | Tero Kivinen | Self | 450 | 10.26.1.2.5 | 14 | Not first use of RFID. | Do not expand here. | Editorial | No | Accepted
I-r111 | Tero Kivinen | Self | 454 | 10.26.4 | 23 | This is only use of DCS. | Remove acronym, and expand dynamic channel selection here. | Editorial | No | Accepted
I-r112 | Tero Kivinen | Self | 463 | 10.26.6.8 | 15 | This is first use of CP. | Expand here. | Editorial | No | Accepted
I-r113 | Tero Kivinen | Self | 480 | 10.27.1 | 3 | This is not first use of ERDEV. | Do not expand here. | Editorial | No | Accepted
I-r114 | Tero Kivinen | Self | 480 | 10.27.1 | 10 | This is not first use of RSTU. | Do not expand here. | Editorial | No | Accepted
I-r115 | Tero Kivinen | Self | 480 | 10.27.1 | 4 | Link to figure 10-207 is broken. | Fix reference link. | Editorial | No | Accepted
I-r166 | Kunal Shah | Apple | 575 | 11.1.3.9 | 5 | Equation format does not look correct. | Update the equation. | Technical | No
I-r116 | Tero Kivinen | Self | 589 | 11.2.8 | 39 | This is not first use of HPRF. | Do not expand here. | Editorial | No | Accepted
I-r181 | Tero Kivinen | Self | 593 | 12.3.2 | 2 | Remove the default value from phyCcaDuration. | Replace this text "The recommended value is not specified by the PHY clause the recommended duration of 8 symbols is used". | Technical | No
I-r168 | Kunal Shah | Apple | 606 | 13.2.2 | 12 | Extra space between 25 and 0, it shoud be 250 kbps | See comment | Editorial | Yes | Accepted
I-r169 | Kunal Shah | Apple | 607 | 13.2.5 | 3 | Link for Table 13-1 does not work. | Fix the link. | Editorial | No | Accepted
I-r167 | Kunal Shah | Apple | 608 | 13.27 | 13 | The equation doesn't seem to be placed correctly. | Update the equation. | Technical | No
I-r170 | Kunal Shah | Apple | 610 | 13.3.2 | 4 | Equation needs to be updated. | See comment | Editorial | No
I-r117 | Tero Kivinen | Self | 616 | 15.1.3 | 14 | First use of QPSK in text. | Expand here. | Editorial | No | Accepted
I-r118 | Tero Kivinen | Self | 633 | 16.1 | 6 | This is not first use of HPRF. | Do not expand here. | Editorial | No | Accepted
I-r119 | Tero Kivinen | Self | 649 | 16.2.9 | 10 | Hanging paragraph. | Add 19.2.9.1 General and move text between 16.2.9 and 16.2.9.1 to that new section. | Editorial | No | Accepted
I-r120 | Tero Kivinen | Self | 649 | 16.2.9.1 | 19 | This is first use of AES. | Expand it here. | Editorial | No | Accepted
I-r121 | Tero Kivinen | Self | 669 | 16.5.4 | 5 | First use LCP in text. | Expand here. | Editorial | No | Accepted
I-r122 | Tero Kivinen | Self | 684 | 19.2.1 | 17 | First use of PRF in text. | Expand here. | Editorial | No | Accepted
I-r123 | Tero Kivinen | Self | 687 | 19.2.5 | 12 | Hanging paragraph. | Create new section 19.2.5.1 and move all text between 19.2.5 and 19.2.5.1 to that new section. | Editorial | No | Accepted
I-r124 | Tero Kivinen | Self | 692 | 19.4.6 | 19 | First use of LEIP in text. | Expand here and on the heading of the 19.4.6. | Editorial | No | Accepted
I-r171 | Kunal Shah | Apple | 702 | 20.1 | 4 | Link for Table 20-1 does not work. | Fix the link. | Editorial | No | Accepted
I-r172 | Kunal Shah | Apple | 702 | 20.1 | 5 | Link for Table 20-7 and 20-8 does not work. | Fix the link. | Editorial | No | Accepted
I-r173 | Kunal Shah | Apple | 702 | 20.1 | 6 | Link for Table 20-9 does not work. | Fix the link. | Editorial | No | Accepted
I-r125 | Tero Kivinen | Self | 703 | 20.2.3 | 9 | Hanging paragraph. | Create new section 20.2.3.1 and move all text between 20.2.3 and 20.2.3.1 to that new section. | Editorial | No | Accepted
I-r175 | Kunal Shah | Apple | 710 | 20.3.1 | 3 | Link for Table 20-9 does not work. | Fix the link. | Editorial | No | Accepted
I-r126 | Tero Kivinen | Self | 728 | 21.2.2.2 | 13 | This is not first use of CP. | Do not expand here. | Editorial | No | Accepted
I-r127 | Tero Kivinen | Self | 729 | 21.2.3.1 | 13 | First use of LTF in text. | Expand here. | Editorial | No | Accepted
I-r178 | Kunal Shah | Apple | 780 | 22.5.4 | 14 | Some of the band designation marked as bold in the table. | Make all the table content not bold (Except the header) | Editorial | No | Accepted
I-r128 | Tero Kivinen | Self | 799 | 24.2.1 | 19 | Figure 24-1 number is wrong should be 24-2. | Fix figure number. | Editorial | No | Accepted
I-r129 | Tero Kivinen | Self | 801 | 24.2.5 | 10 | reference to figure 24-5 is broken. | Fix reference, | Editorial | No | Accepted
I-r130 | Tero Kivinen | Self | 801 | 24.2.5 | 12 | reference to figure 24-6 is broken. | Fix reference, | Editorial | No | Accepted
I-r131 | Tero Kivinen | Self | 801 | 24.3.1 | 19 | Table 24-8 number is wrong should be 24-1, and later tables should be renumbered. | Fix table numbers. | Editorial | No | Accepted
I-r132 | Tero Kivinen | Self | 803 | 24.3.2 | 3 | Extra period at the end of line. | Remove extra period. | Editorial | No | Accepted
I-r133 | Tero Kivinen | Self | 807 | 24.3.5.3.1 | 11 | First use of LDPC in text. | Expand here. | Editorial | No | Accepted
I-r134 | Tero Kivinen | Self | 881 | 30.1 | 3 | This is first use of ASK. | Expand it here. | Editorial | No | Accepted
I-r135 | Tero Kivinen | Self | 911 | Annex B.2.1 | 15 | Add reference to 9.3.1 explaining that this annex uses the notation and formats specified in that section. | Add text "This annex uses the notation, and representation of strings, integers and octets as described in section 9.3.1." | Technical | No
I-r136 | Tero Kivinen | Self | 911 | Annex B.2.2 | 17 | This is not first use of AES. | Do not expand it here. | Editorial | No | Accepted
I-r137 | Tero Kivinen | Self | 911 | Annex B.1 | 5 | This is first use of CCM*. | Expand here. | Editorial | No | Accepted
I-r138 | Tero Kivinen | Self | 917 | Annex C | 4 | Hanging paragraph. | Create new section C.1 General and move all text between Annex C and C.1 to that new section. | Editorial | No | Accepted
I-r139 | Tero Kivinen | Self | 917 | Annex C.2.2.1 | 23 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines 23-29 is changes to dashed list. | Update the Annex C.2.2.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r140 | Tero Kivinen | Self | 918 | Annex C.2.2.2 | 2 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 line 2 has been changed to heading removing hanging paragraph. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r141 | Tero Kivinen | Self | 918 | Annex C.2.2.2 | 12 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 line 12 has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r142 | Tero Kivinen | Self | 920 | Annex C.2.2.2.3 | 2 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 line 2 has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r143 | Tero Kivinen | Self | 920 | Annex C.2.2.3 | 4 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r144 | Tero Kivinen | Self | 920 | Annex C.2.2.3 | 14 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r145 | Tero Kivinen | Self | 921 | Annex C.2.2.3.2 | 13 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r146 | Tero Kivinen | Self | 921 | Annex C.2.3.1 | 29 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines 29-35 is changes to dashed list. | Update the Annex C.2.3.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r147 | Tero Kivinen | Self | 922 | Annex C.2.3.2 | 2 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r148 | Tero Kivinen | Self | 922 | Annex C.2.3.2 | 13 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r149 | Tero Kivinen | Self | 924 | Annex C.2.3.2.3 | 7 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r150 | Tero Kivinen | Self | 924 | Annex C.2.3.3 | 10 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r151 | Tero Kivinen | Self | 924 | Annex C.2.3.3 | 21 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r152 | Tero Kivinen | Self | 925 | Annex C.2.3.3.2 | 19 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this line has been changed to heading. | Update this to match the 802.15.4-2020. | Editorial | No | Accepted
I-r153 | Tero Kivinen | Self | 926 | Annex C.3.1 | 3 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines 3-9 is changes to dashed list. | Update the Annex C.2.2.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r154 | Tero Kivinen | Self | 926 | Annex C.3.2 | 17 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines 17-23 is changes to dashed list. | Update the Annex C.2.2.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r155 | Tero Kivinen | Self | 926 | Annex C.3.3 | 31 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines P926L31-P927L6 is changes to dashed list. | Update the Annex C.2.2.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r156 | Tero Kivinen | Self | 927 | Annex C.3.4 | 15 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines 15-19 is changes to dashed list. | Update the Annex C.2.2.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r157 | Tero Kivinen | Self | 927 | Annex C.3.5 | 32 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines P927L32-P928L6 is changes to dashed list. | Update the Annex C.2.2.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r158 | Tero Kivinen | Self | 928 | Annex C.3.6 | 17 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines 17-24 is changes to dashed list. | Update the Annex C.2.2.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r159 | Tero Kivinen | Self | 928 | Annex C.3.7 | 34 | For some reason the Annex C received from the IEEE staff does NOT match the published 802.15.4-2020, but seems to be some older version of the Annex, and matches more closely to the 802.15.4-2015. In 802.15.4-2020 this list between lines P928L34-P929L8 is changes to dashed list. | Update the Annex C.2.2.1 to match the 802.15.4-2020. | Editorial | No | Accepted
I-r160 | Tero Kivinen | Self | 930 | Annex C.3.7 | 1 | Empty page | Remove empty page. | Editorial | No | Revised | Fixed subclause number, and line number of the comment, filled in the comment, comment accepted
I-r161 | Tero Kivinen | Self | 931 | Annex D | 21 | Only use of acronym IANA. | Remove acronym. | Editorial | No | Accepted
I-r162 | Tero Kivinen | Self | 953 | Annex F | 1 | This is normative annex describing optional feature TRLE. Move it to section 10, by creating new 10.34 and move it there. | Move to new section 10.34. | Technical | No
I-r163 | Tero Kivinen | Self | 953 | Annex F | 1 | Is this used? Can we mark this to be deprecated in next revision? | Mark this annex to be deprecated in next revision. | Technical | No
I-r174 | Kunal Shah | Apple | General | General | 1 | Check links to all tables throughput the document and update the link if its broken. | Update the link for Tables if it's broken. | Editorial | No | Accepted
I-r177 | Kunal Shah | Apple | General | General |  | Check the equation format across the document to confirm it aligns with the approved Std/Amendment | Fix the equation format. | Technical | No
I-r176 | Kunal Shah | Apple |  | 20.3.6 | 15 | The format of the equation doesn't seem correct based on the 15.4-2020 Std. | Please correct the equation per approved Std. | Technical | No
I-r179 | Almholt, Thomas | Texas Instruments |  |  |  | We actually do not recommend a new one pulse shape equation (both are in there today), we recommend that regional specifics are removed from the document making both available shaping functions equally valid everywhere and at up to the descression of the system integrator. | Please see comment DCN 15-23-0493-00-04me | Technical | No
I-r180 | Tero Kivinen | Sef |  |  |  | Spell out microsecond if used without numbers. | Spell out microsecond if used without numbers. | Editorial | No |  |  |  |  | New comment

## Statistics
|  | Category |  |  |  | Disposition status
Letter ballot | Total | Editorial | Technical | General | Unknown | Accepted | Revised | Rejected | Unresolved
LB197 | 138 | 115 | 19 | 3 | 1 | 79 | 9 | 29 | 21
LB197_rogue | 181 | 125 | 56 | 0 | 0 | 133 | 2 | 0 | 46
Instructions:
In column B type in the sheet name containing letter ballot comments to get statistics from that sheet. Note, that spaces are not allowed in the sheet names.