## List
Std | Status | Information Motion |  |  | Liaison Motion |  | Adoption Motion |  | STD | Last draft liaised |  | 60-day |  | 5-month |  | Comments resolved
|  | WG | EC | sent | WG | EC | WG | EC | sent |  |  | pre-ballot |  | FDIS ballot
802.15.3 | Completed | [7 empty] | Y |  |  | Passed | 2016-10-01 | Passed | 2017-09-01 | n/a
802.15.3-2016 | No need | - | - |  |  | 7-Jun-2022 |  | 7-Jun-2022 |  | No need | - | No need | - | No need | - | -
802.15.3d-2017 |  | - | 7-Jun-2022 | Y | [5 empty] | Std | Jan 2023 | Waiting | - | Waiting | - | -
802.15.3e-2017 |  | - | 7-Jun-2022 | Y | [5 empty] | Std | Jan 2023 | Waiting | - | Waiting | - | -
802.15.3f-2017 |  | - | 7-Jun-2022 | Y | [5 empty] | Std | Jan 2023 | Waiting | - | Waiting | - | -
802.15.3-2023 |  | 2023-11-16 | 2023-11-17 | ? | 2024-03 |  | 2024-03 |  |  | Waiting | - | Waiting | - | Waiting | - | -
802.15.4 | Completed | [7 empty] | Y |  |  | Passed | 2017-04-01 | Passed | 2018-01-01 | n/a
802.15.4x-2019 | in .4-2020 | - | 7-Jun-2022 | - | - | - | - | - |  | No need | - | No need | - | No need
802.15.4-2020 | In Process | - | - |  | - | 7-Jun-2022 | - | 7-Jun-2022 | Y | Std | Jan 2023 | Passed | 2023-11-12 | Waiting | - | n/a
802.15.4w-2020 |  | - | 7-Jun-2022 | Y | [5 empty] | Std | Jan 2023 | Waiting | - | Waiting | - | -
802.15.4y-2021 |  | 2023-11-16 | 2023-11-17 | ? | 2024-03 |  | 2024-03 |  |  | Waiting | - | Waiting | - | Waiting | - | -
802.15.4z-2020 |  | - | 7-Jun-2022 | Y | [5 empty] | Std | Jan 2023 | Waiting | - | Waiting | - | -
802.15.4aa-2022 |  | - | 7-Jun-2022 | Y | [5 empty] | Std | Jan 2023 | Waiting | - | Waiting | - | -
802.15.6 | Completed | [7 empty] | Y |  |  | Passed | 2016-11-23 |  | 2017-09-07 | 2023-07-19
802.15.6ma | [10 empty] | - |  | - | Waiting | - | -
802.15.7-2018 |  |  | - |  |  | 2022-11-18 |  | 2022-11-18 | ? | Waiting | - | Waiting | - | Waiting | - | -
802.15.7a | [10 empty] | - |  | - |  | - | -
802.15.9-2021 | In Process |  | - |  |  | 7-Jun-2022 |  | 7-Jun-2022 | Y | Std | Jan 2023 | Passed | 2023-11-12 | Waiting | -
802.15.13 |  | 2024-03 | [8 empty] | - |  | - |  | - | -
[11 empty] | - |  | - |  | - | -
[11 empty] | - |  | - |  | - | -
[11 empty] | - |  | - |  | - | -
[11 empty] | - |  | - |  | - | -
[11 empty] | - |  | - |  | - | -

## key
Std | Name of the Standard
Status | Current Status (free form) | Completed | in Progress | No Need - could be due to roll up.
Information Motion | example in motions | sending the STD for information to ISO (prepare them that it will be coming for adoption)
WG | date
EC | date
Liaison Motion | example in motions | sending a liaison statement that we are sending a STD for adoption
WG | date
EC | date
Adoption Motion | example in motions | sending the STD for adoption
WG | date
EC | date
STD | when STD sent to ISO | Y, ? Or date
sent | for adoption
Last draft liaised | What was liaised | STD | waiting for next step
date
60-day | Status | Passed | waiting for next step
pre-ballot | date
5-month | Status | STD | waiting for next step
FDIS ballot | date
Comments resolved | free form. | n/a | date

## schedule
What/When | Do | who | spreadsheet
| Add STD to spreadsheet | 802.15 | Update
| Create a WG motion for Information (motion tab) | 802.15
| Create an EC motion for Information (motion tab) | 802.15
| submit WG and EC motions | 802.15 | Update
STD is sent to ISO |  | ???? | Update | last draft liaised
| Create Liaison statement | 802.15
| Create WG motion for Liaison and Adoption (motion tab) | 802.15
| Create EC motion for Liaison and Adoption (motion tab) | 802.15
30 days after sent to ISO | submit WG and EC liaison/adoption motions | 802.15 | Update
Liaison statement & STD sent to ISO |  | ???? | Update | last draft liaised
60 day from pre-ballot | check for updates | ???? | Update when ready
5 month FDIS ballot | check for updates | ???? | Update when ready

## motions
| WG Motion | EC Motion example | EC Motion example
Informational |  | Approval to forward standard to ISO/IEC JTC1/SC6 for information.
Motion | Move that the IEEE 802.15 WG requests that IEEE 802 EC approve submission of the following project IEEE Std 802.15.3™-2023 to ISO/IEC JTC1/SC6 for information under the PSDO agreement. | IEEE 802.15 WG requests IEEE 802 EC approval to forward IEEE Std 802.15.3™-2023 to ISO/IEC JTC1/SC6, for information under the PSDO agreement.
Liaison |  | IEEE 802.15 Liaison Statement Approval, ISO/IEC JTC1/SC6 | IEEE 802.15 Liaison Statement Approval, ISO/IEC JTC1/SC6
Motion |  | IEEE 802.15 WG requests IEEE 802 EC approval of the liaison statement contained in doc. # 15-22-0314-00-0000 describing the liaison of IEEE Std 802.15.9™-2021 to ISO/IEC JTC1/SC6 under the PSDO agreement. | IEEE 802.15 WG requests IEEE 802 EC approval of the liaison statement contained in doc. # 15-22-0312-00-0000 describing the liaison of IEEE Std 802.15.4™-2020 and published amendments to ISO/IEC JTC1/SC6 under the PSDO agreement.
Adoption |  | IEEE 802.15 Liaison Statement Approval, ISO/IEC JTC1/SC6
Motion |  | IEEE 802.15 WG requests IEEE 802 EC approval to forward IEEE Std 802.15.9™-2021 to ISO/IEC JTC1/SC6 for adoption as an ISO/IEC/IEEE standard under the PSDO agreement
Move that the IEEE 802.15 WG requests that IEEE 802 EC approve submission of the following project IEEE Std 802.15.3™-2023 to ISO/IEC JTC1/SC6 for information under the PSDO agreement.