## List
Std | Status | Information Motion |  | Draft | Adoption Motion |  | STD | Last draft liaised |  | 60-day |  | 5-month |  | Comments resolved
|  | WG | LMSC | sent | WG | LMSC | sent |  |  | pre-ballot |  | FDIS ballot
802.15.3 | Completed | done | done |  | done | done | Y |  |  | Passed | 2016-10-01 | Passed | 2017-09-01 | n/a
802.15.3-2016 | No need | done | 7-Jun-2022 |  | done | 7-Jun-2022 |  | No need | - | No need | - | No need | - | -
802.15.3d-2017 | in .3-2023 | done | 7-Jun-2022 | Y | hold | - | - | Std | Jan 2023 | - | - | - | - | -
802.15.3e-2017 | in .3-2023 | done | 7-Jun-2022 | Y | hold | - | - | Std | Jan 2023 | - | - | - | - | -
802.15.3f-2017 | in .3-2023 | done | 7-Jun-2022 | Y | hold | - | - | Std | Jan 2023 | - | - | - | - | -
802.15.3-2023 |  | 2023-11-16 | 2023-11-17 | Y | 2024-05-16 | 2024-07-19 |  | Std | Feb 2024
802.15.4 | Completed | [5 empty] | Y |  |  | Passed | 2017-04-01 | Passed | 2018-01-01 | n/a
802.15.4x-2019 | in .4-2020 | done | 7-Jun-2022 | - | - | - |  | No need | - | No need | - | No need
802.15.4-2020 | Completed | done | 7-Jun-2022 | Y | done | 7-Jun-2022 | Y | Std | Jan 2023 | Passed | 2023-11-12 | Passed | 2024-07-24 | comments from India
802.15.4w-2020 | in .4-2024 | done | 7-Jun-2022 | Y | hold | - | - | Std | Jan 2023 | - | - | - | - | -
802.15.4y-2021 | in .4-2024 | 2023-11-16 | 2023-11-17 | Y | hold | - | - | Std | Jan 2024 | - | - | - | - | -
802.15.4z-2020 | in .4-2024 | done | 7-Jun-2022 | Y | hold | - | - | Std | Jan 2023 | - | - | - | - | -
802.15.4aa-2022 | in .4-2024 | done | 7-Jun-2022 | Y | hold | - | - | Std | Jan 2023 | - | - | - | - | -
802.15.4-2024 |  | 2024-05-16 | 2024-06-04 |  |  |  |  | D03
802.15.6 | Completed | done | done |  | done | done | Y | Std | Nov 2016 | Passed | 2016-11-23 | Passed | 2017-09-07 | 2023-07-19
802.15.6ma
802.15.7-2018 | In Process |  | 2022-11-18 |  | done | 2022-11-18 | Y | Std | 2024-05-01 | in ballot | 2024-07-24 | Waiting | - | -
802.15.7a |  | 2024-05-16 | 2024-06-04 |  |  |  |  | D7
802.15.9-2021 | In Process |  | 7-Jun-2022 |  | done | 7-Jun-2022 | Y | Std | Jan 2023 | Passed | 2023-11-12 | Waiting | - | Jan 2024
802.15.13 |  | 2024-05-16 | 2024-06-04 |  |  |  |  | Std | - |  | - |  | - | -
[9 empty] | - |  | - |  | - | -
[9 empty] | - |  | - |  | - | -
[9 empty] | - |  | - |  | - | -
[9 empty] | - |  | - |  | - | -
[9 empty] | - |  | - |  | - | -

## key
Std | Name of the Standard
Status | Current Status (free form) | Completed | in Progress | No Need - could be due to roll up.
Information Motion | example in motions | sending the draft or STD for information to ISO (prepare them that it will be coming for adoption)
WG | date
LMSC | date
Draft Sent | when the draft was sent | Y, ? Or date
Adoption Motion | example in motions | sending the STD for adoption
WG | date
LMSC | date
STD | when STD sent to ISO | Y, ? Or date
sent | for adoption
Last draft liaised | What was liaised | STD | waiting for next step
date
60-day | Status | Passed | waiting for next step
pre-ballot | date
5-month | Status | STD | waiting for next step
FDIS ballot | date
Comments resolved | free form. | n/a | date

## schedule
What/When | Do | who | spreadsheet | notes
STD is at least in SA ballot | Add STD to spreadsheet | 802.15 | Update
| Create a WG motion for Information (motion tab) | 802.15 |  | if in SA ballot - submit the name of the draft
| Create an LMSC motion for Information (motion tab) | 802.15
| submit WG and LMSC motions | 802.15 | Update
STD is sent to ISO |  | IEEE Staff | Update | last draft liaised
| Create Liaison statement | 802.15
| Create WG motion for Liaison and Adoption (motion tab) | 802.15
| Create EC motion for Liaison and Adoption (motion tab) | 802.15
30 days after sent to ISO | submit WG and LMSC liaison/adoption motions | 802.15 | Update
Liaison statement & STD sent to ISO |  | IEEE Staff | Update | last draft liaised
60 day from pre-ballot | check for updates | IEEE Staff | Update when ready
5 month FDIS ballot | check for updates | IEEE Staff | Update when ready