## IEEE Cover page
May 2024 |  | 15-24-0289-00
IEEE P802.15
Wireless Specialty Networks
Project | P802.15.4ae
Title | TG4ae project task list
Date Submitted | 2024-05-14
Source | Tero Kivinen | kivinen@iki.fi
Re:
Abstract | Project task list for TG4ae
Purpose | Task list for TG4ae showing current status
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Project process
# | Step | Who | Date completed | Comments or Motions | Notes | Operation manual reference
S1 | Start interest group | Kivinen | 2024-05-13 | optional | WG Chair will create IG if there is enough interest | OM 8
S1.1
S2 | Start study group |  | skipped | optional but recommended |  | OM 6
S2.1 | WG motion to approve formation a SG | SG Chair | skipped | WG Motion 13.1.1 |  | OM 6.2
S2.2 | LMSC motion to approve formation of the SG | WG Chair | skipped
S2.3 | Only for between two planeries, if going on longer, request extension | SG and WG Chairs | skipped | WG motion 13.1.2 |  | OM 6.3
S2.4 | Report SG progress to LMSC in every plenary | WG Chair | skipped |  | SG Chair needs to provide the information to WG chair TODO do we need template for this | OM 6.6.2
S2.5 | Create PAR | SG | 2024-05-14 |  | Project Authorization Request, this is created in the myproject by the SG Chair, and SG Chair then downloads the pdf and stores that to mentor.
S2.6 | SG chair needs to give permissions to edit the PAR in myProject to chair, vice chairs and technical editors of the WG | SG Chair | 2024-05-16
S2.7 | Create CSD | SG | 2024-05-14 | if needed | Criteria for standards development. https://www.ieee802.org/devdocs.shtml
S2.8 | SG approval of PAR and CSD | SG Chair | 2024-05-15 | SG Motion 13.1.3
S2.9 | WG motion to approve PAR and CSD | SG Chair | 2024-05-16 | WG Motion 13.1.4 | CSD can be in the mentor, but the PAR needs to be in two places in the mentor and in the myProject.
S2.10 | The PAR needs to be put to the LMSC agenda 30 days before meeting | WG Chair |  |  |  | LMSC OM 9.3
S2.11 | Receive comments to the PAR | SG |  |  | Comments from other working groups are sent to the LMSC reflector, and WG chair will forward them to SG. Due by Tuesday 18:30 local time plenary week | LMSC OM 9.3
S2.12 | Process comments to the PAR and respond to them | SG
S2.13 | TG motion to approval of comment responses for PAR and CSD | SG |  | SG Motion 13.1.5
S2.14 | WG motion to approval of comment responses for PAR and CSD | SG |  | WG Motion 13.1.6 | Needs to be done in midweek plenary, as responses needs to be sent by Wednesday 18:30 local time
S2.15 | PAR package for LMSC | TG and WG Chairs |  |  | Needs to include all comments received and summary of the responses. There should be powerpoint slides for LMSC, comment resolution database, PAR, CSD, and CAD if applicable. This should be completed by Wednesday 18:30 local time plenary week. See example at https://mentor.ieee.org/802.15/dcn/23/15-23-0183-01-0017-ec-slides-for-privacy-par-and-csd-march-2023.pptx
S2.16 | LMSC approval of the TG | LMSC |  |  |  | LMSC OM 9
S2.17 | NesCom approval of the TG | NesCom |  |  | TG can start its work even before this. | LMSC OM 9
S2.18
S3 | Start task group |  |  |  |  | OM 4
S3.1 | TG chair selection | WG Chair |  |  | Appointed by WG chair, confirmed by a TG | OM 4.2
S3.2 | TG vice chair selection | TG Chair |  | optional | Appointed by TG chair, confirmed by a TG | OM 4.3
S3.3 | TG secretary selection | TG Chair |  |  | Appointed by TG chair | OM 4.4
S3.4 | TG technical editor selection | TG Chair |  |  | Appointed by TG chair, confirmed by a TG | OM 4.5
S3.5
S4 | Task group working
S4.1 | Work on the draft and get it ready. | TG
S4.2 | Create CA Document | TG |  | if needed (the project does not change any radio properties of the existing standard) | Coexistance Assessment | LMSC OM 13
S4.3
S5 | Task group management
S5.1 | WG approval to extend a par | TG Chair |  | WG Motion 13.1.7 | Do this early enough before the actual PAR expires.
S5.2
S6 | Initial letter ballot |  |  |  | Initial ballot is 30 days | OM 3.10
S6.1 | Draft needs to be posted to the private area | WG and TG Chair |  |  | TG technical editor sends the clean version of the draft in PDF format to the WG chair. WG Chair will post it in private area. | OM 3.10.2
S6.2 | Draft needs to be announced in the 802.15 WG reflector | TG Chair |  |  | TG chair needs to send email announcing that draft is posted in the private area. | OM 3.10.2
S6.3 | Verify whether WG chair has assigned TEG (Technical Expert Group) for the TG, and if so send the draft to them 4 weeks before | WG and TG Chair |  |  | TG Chair should save assigned TEG people in the TG web page. | OM 9
S6.4 | WG technical editor review | WG Editor |  |  |  | OM 3.9.2
S6.5 | TG motion when draft completed and ready for letter ballot Or TG motion when draft needs to be editied prior letter ballot | TG Chair |  | TG Motion 13.2.1.1 Or TG Motion 13.2.1.2 | If draft is ready use this motion, if it needs to be edited, use next one. Or If comment resolutions are ready, but not all changes are made to the draft yet.
S6.6 | WG motion when draft completed and ready for letter ballot Or WG motion when draft needs to be editied prior letter ballot | TG Chair |  | WG Motion 13.2.2.1 Or WG Motion 13.2.2.2 | If draft is ready use this motion, if it needs to be edited, use next one. Or If comment resolutions are ready, but not all changes are made to the draft yet.
S6.7 | WG chair or designee starts the letter ballot | WG Chair
S6.8 | WG chair sends a list of ballot pool and template to the TG chair | WG Chair
S6.9 | TG chair will keep track of all votes cast, and marks them up in the ballot pool sheet. | TG Chair |  |  | Can also delegate iit to some of the other officer. There is template for 15-yy-xxxx
S6.10 | TG chair collects all comments submitted during the letter ballot period | TG Chair |  |  | There is templete form it 15-23-0426
S6.11 | After the ballot closes the TG chair will submit current tally of the votes cast to the WG chair, and WG chair confirms and announces it to the 802.15 WG reflector. | WG and TG Chair |  |  | Record results on the “Letter ballot results” tab in this sheet.
S6.12 | TG chair or techincal editor creates a combined sheet of comments received and posts it to mentor | TG Chair |  |  | Remove email addresses, phone numbers etc before posting. There is templete form it 15-23-0426
S6.13 | After ballot closes resolve the comments | TG
S6.14 | TG/CRG motion to approve of comment responses. | TG Chair or CRG Chair |  | TG/CRG Motion 13.2.3.5
S6.15 | Create new version of the draft | TG Editor
S6.16
S7 | Letter ballot recirculations (latest) |  |  |  | Recirculations are 15 days | OM 3.10
S7.1 | TG motion when draft is completed and ready for recirculation letter ballot Or TG motion when draft needs to be editied prior recirculation letter ballot | TG Chair |  | TG Motion 13.2.1.3 Or TG Motion 13.2.1.4 | If draft is ready use this motion, if it needs to be edited, use next one. Or If comment resolutions are ready, but not all changes are made to the draft yet.
S7.2 | Draft needs to be posted to the private area | WG and TG Chair |  |  | TG technical editor sends the clean version of the draft in PDF format to the WG chair. WG Chair will post it in private area. It is recommended to include the redline version showing changes between the this version and previous version.
S7.3 | WG motion when draft is completed and ready for recirculation letter ballot Or WG motion when draft needs to be editied prior recirculation letter ballot | TG Chair |  | WG Motion 13.2.2.3 Or WG Motion 13.2.2.4 | If draft is ready use this motion, if it needs to be edited, use next one. Or If comment resolutions are ready, but not all changes are made to the draft yet.
S7.4 | Form CRG for letter ballot | TG |  |  | OM 5.2, must be voting members, no company or organization can representation 25% or more | OM 5.2
S7.5 | TG motion to create CRG for Letter ballot | TG Chair |  | TG Motion 13.3.1
S7.6 | WG motion to create CRG for Letter ballot | TG Chair |  | WG Motion 13.3.1
S7.7 | WG chair starts the recirculation letter ballot | WG Chair
S7.8 | TG chair will keep track of all votes cast during the recirculation ballot, and marks them up in the ballot pool sheet. | TG Chair |  |  | Can also delegate iit to some of the other officer. There is template for 15-yy-xxxx
S7.9 | TG chair collecs all comments submitted during the letter ballot period | TG Chair |  |  | There is templete form it 15-23-0426
S7.10 | After the ballot closes the TG chair will submit current tally of the votes cast to the WG chair, and WG chair confirms and announces it to the 802.15 WG reflector | WG Chair |  |  | Record results on the “Letter ballot results” tab in this sheet.
S7.11 | TG chair or techincal editor add a new worksheet to the combined sheet of comments received and posts it to mentor | TG Chair |  |  | Remove email addresses, phone numbers etc before posting.
S7.12 | Resolve the comments either in CRG, or during the meeting. | TG or CRG
S7.13 | TG/CRG motion to approval of comment responses. | TG or CRG Chair |  | TG/CRG Motion 13.2.3.5
S7.14 | Create new version of the draft | TG Editor |  |  | For recirculations you need both clean PDF version of the draft and redline PDF version of the draft showing what has changed between recirculations. Make sure the drafts have PDF index.
S7.15 | Repeat S7 as many times as needed | TG
S7.16
S8 | Standard association ballot |  |  |  | Initial ballot is minimum of 30 days
S8.1 | WG chair grants permission for the TG chair or designee (refered here as TG Chair) to run standard association process in the myproject | WG Chair
S8.2 | MEC review | TG Chair |  |  | Can take up to 4 weeks, can be done during the letter ballot phase too. | IEEE SA Standards board OM 5.4.4
S8.3 | Standard association ballot pool formation | WG Chair |  |  | At minimum 30 days, and it is valid for 6 months. | IEEE SA Standards board OM 5.4.2
S8.4 | LMSC package creation | TG and WG Chairs |  |  | Includes letter ballot vote and comment summaries, plus list of unresolved comments from remaining no voters. Use the informaton in “Letter ballot result” tab of this sheet. Template for it is in 15-xx-yyyyy
S8.5 | TG motion when the draft is ready for unconditional submittal for Standards Association ballot Or TG motion when the draft needs conditional submittal for Standards Association ballot | TG Chair |  | TG Motion 13.4.1.2 Or TG Motion 13.4.1.1 | Draft has finished letter ballots and is ready for standard association ballot. Or We still have work to be do, for example fnish editing, or close up the last or second last letter ballot. You can still have one more letter ballot going after getting this permission.
S8.6 | Form CRG for standards association ballot | TG |  |  | OM 5.2, must be voting members, no company or organization can representation 25% or more
S8.7 | TG motion to create CRG for standards association ballot | TG Chair |  | TG Motion 13.3.2
S8.8 | WG motion when the draft is ready for unconditional submittal for Standards Association ballot Or WG motion when the draft needs conditional submittal for Standards Association ballot | TG Chair |  | WG Motion 13.4.2.2 Or WG Motion 13.4.2.1 | Draft has finished letter ballots and is ready for standard association ballot. Or We still have work to be do, for example fnish editing, or close up the last or second last letter ballot. You can still have one more letter ballot going after getting this permission.
S8.9 | WG motion to create CRG for standards association ballot | TG Chair |  | WG Motion 13.3.2
S8.10 | TG chair request a standard association ballot initiation in myproject | TG Chair
S8.11 | PM approves and starts the standard association ballot | IEEE Staff
S8.12 | After the ballot finishes the TG chair will check the results from myproject | TG Chair |  |  | Record results on the “Standard association results” tab in this sheet.
S8.13 | TG chair or technical editor creates a combined sheet of comments received and posts it to mentor | TG Chair |  |  | Remove email addresses, phone numbers etc before posting. There is templete form it 15-yy-xxxx
S8.14 | Resolve the comments either in CRG, or during the meeting. | TG or CRG
S8.15 | TG/CRG motion to approval of comment responses. | TG or CRG Chair |  | TG/CRG Motion 13.4.1.5
S8.16 | Create new version of the draft | TG Editor
S8.17
S9 | Standard association recirculation ballot |  |  |  | Recirculations are minimum of 10 days
S9.1 | TG motion when draft is completed and ready for recirculation Standards Association ballot Or TG motion when draft needs to be editied prior recirculation Standards Association ballot | TG Chair |  | TG Motion 13.4.1.3 Or TG Motion 13.4.1.4 | If draft is ready use this motion, if it needs to be edited, use next one. Or If comment resolutions are ready, but not all changes are made to the draft yet.
S9.2 | WG motion when draft is completed and ready for recirculation Standards Association ballot Or WG motion when draft needs to be editied prior recirculation Standards Association ballot | TG Chair |  | WG Motion 13.4.2.3 Or WG Motion 13.4.2.4 | If draft is ready use this motion, if it needs to be edited, use next one. Or If comment resolutions are ready, but not all changes are made to the draft yet.
S9.3 | Submit responses to all comments to myproject | TG Chair or Editor
S9.4 | Submit new draft and the redline (as an additional document) to the myproject | TG Chair
S9.5 | TG chair request a standard association ballot recirculation initiation | TG Chair
S9.6 | PM approves and starts the standard association ballot recirculation | IEEE Staff
S9.7 | After the ballot finishes the TG chair will check the results from myproject | TG Chair |  |  | Record results on the “Standard association results” tab in this sheet.
S9.8 | TG chair or technical editor adds new worksheet in the combined sheet of comments received and posts it to mentor | TG Chair or Editor |  |  | Remove email addresses, phone numbers etc before posting
S9.9 | Resolve the comments either in CRG, or during the meeting. | TG or CRG
S9.10 | TG/CRG motion to approval of comment responses. | TG or CRG Chair |  | TG/CRG Motion 13.4.1.5
S9.11 | Create new version of the draft | TG Editor
S9.12 | Repeat S9 as many times as needed | TG
S9.13
S10 | Revcom Submission
S10.1 | Create package for going to RevCom | TG and WG Chairs |  |  | 15-21-0624-00-0mag-template-for-ec-to-revcom-presentation.pptx
S10.2 | TG motion for unconditional submittal for revcom Or TG motion for conditional submittal for revcom |  |  | TG Motion 13.5.1.1 Or TG Motion 13.5.1.2 | Draft has finished letter ballots and is ready for RevCom. Or We still have work to be do, for example finish editing, or close up the last or second last standard association ballot. You can still have one more standard association ballot going after getting this permission.
S10.3 | WG motion for unconditional submittal for revcom Or WG motion for conditional submittal for revcom |  |  | TG Motion 13.5.2.1 Or TG Motion 13.5.2.2 | Draft has finished letter ballots and is ready for RevCom. Or We still have work to be do, for example fnish editing, or close up the last or second last standard association ballot. You can still have one more standard association ballot going after getting this permission.
S10.4 | Address any comments received from RevCom | WG Chair
S10.5 | RevCom approval | RevCom
S10.6 | SASB approval | SASB
S10.7 | TG chair sends a list of people who should be rewarded / recognized to WG chair | TG Chair |  |  | The WG chair needs the list of names, addresses, and the reason for the recognizion (position/role abd/or contribution)
S10.8
S11 | IEEE Editor phase
S11.1 | IEEE editor edits the document | IEEE Staff
S11.2 | WG chair sends the list of WG members to IEEE editors to be included in the draft. | WG Chair
S11.3 | IEEE editor sends comments and edits to TG Chair and TG technical editor for approval | TG Chair and TG Editor
S11.4 | IEEE publishes the document | IEEE Staff
S11.5 | Work chair forwards information of the complementary copy to the WG | WG Chair

## Terms
Term | Definition
CAD: | Coexistance Assessment Document
CRG: | Comment Resolution Group
CSD: | Criteria for Standards Development
IG: | Interest group
LMSC: | LAN/MAN standards committee
MEC: | Mandatory Editorial Coordination
Meeting: | A formal gathering of participants as per IEEE 802 rules; i.e. with a published agenda, published minutes, etc
NesCom: | New Standards Committee
OM: | Operations Manual 15-10-0235
PAR: | project authorization request
Plenary Session: | Session where all 802 WGs are present. Plenary sessions usually occur in March, July, and November
PM: | Program Manager (IEEE Staff)
Reflector: | Email mailing lists: https://grouper.ieee.org/groups/802/15/pub/Subscribe.html
RevCom: | Standards Review Committee
SASB: | The Standards Board
Session: | Sequence of consecutive Work Group meetings starting with the opening plenary meeting and ending with the closing plenary meeting. Typically a session starts on a Monday and ends on a Thursday.
SG: | Study group
TEG: | Technical Expert Group
TG: | Task group
WG: | Working group

## Letter ballot results
| Initial | 1st recirc | 1st recirc aggregate | 2nd recirc | 2nd recirc aggregate | 3rd recirc | 3rd recirc aggregate | 4th recirc | 4th recirc aggregate | 5th recirc | 5th recirc aggregate
Voters:
Voted:
Yes:
Abstain:
No:
% Voters:
% Yes:
% Abstain:
Did not vote cumulative:
% Did not vote cumulative:
Ballot start date:
Ballot end date:
Draft version:
# Comments:
# Technical Comments:
# Editorial Comments:

## Sponsor ballot results
| Initial standard association ballot | 1st recirculation | 2nd recirculation | 3rd recirculation | 4th recirculation | 5th recirculation
Ballot start date:
Ballot end date:
Ballot group members:
Return ballots:
Approval rate:
Approve:
Disapprove With MBS Comment(s):
Disapprove Without MBS Comment(s):
Abstentions:
Total Comments: