## Sheet1
Year | Start | End | Location | Group | # | M.1457 | M.2012 | WP 5A related to CRS | Sharing parameters | M.2039 | PPDR | Passive and Active BS Antennas | Other
2012 | 2012-01-16 | 2012-01-19 | Jacksonville, USA | IEEE 802.16 | 77 | - | - | - | - | - | - | - | -
| 2012-01-16 | 2012-01-19 | Jacksonville, USA | IEEE 802.18 |  | - | - | - | - | - | - | - | -
| 2012-01-16 | 2012-01-20 | Geneva, Switzerland | ITU-R RA-12 |  | - | - | - | - | - | - | - | -
| 2012-01-23 | 2012-02-17 | Geneva, Switzerland | ITU-R WRC-12 |  | - | - | - | - | - | - | - | -
| 2012-03-12 | 2012-03-15 | Waikoloa, USA | IEEE 802.16 | 78 | Finalize M.1457-11 Meeting X+2 contribution and liaison statement to WiMAX Forum | Develop and finalize M.2012-1 Meeting Y contribution and liaison statement to WATO | Develop and finalize contribution to WP 5A related to CRS | - | - | - | - | -
| 2012-03-12 | 2012-03-15 | Waikoloa, USA | IEEE 802.18 |  | Review M.1457-11 Meeting X+2 contribution | Review M.2012-1 Meeting Y contribution | Review contribution to ITU-R WP 5A related to CRS | - | - | - | - | -
| 2012-03-12 | 2012-03-16 | Waikoloa, USA | IEEE 802 |  | Approve M.1457-11 Meeting X+2 contribution | Approve M.2012-1 Meeting Y contribution | Approve contribution to ITU-R WP 5A related to CRS | - | - | - | - | -
| 2012-03-14 | 2012-03-17 | Atlanta, USA | IEEE 802.16 | 79 | - | - | - | - | - | - | - | -
| 2012-03-14 | 2012-03-17 | Atlanta, USA | IEEE 802.18 |  | - | - | - | - | - | - | - | -
| 2012-05-22 | 2012-05-31 | Geneva, Switzerland | ITU-R WP 5A | 9 | - | - | - | - | - | - | - | -
| 2012-07-16 | 2012-07-19 | San Diego, USA | IEEE 802.16 | 80 | Finalize plan to submit transposition | Develop and finalize M.2012-1 Meeting Y+1 contribution and liaison statement to WATO | - | - | - | - | - | Review the status of WP 5D #13
Review the outcome of WP 5A #9 (related to CRS etc.)
| 2012-07-16 | 2012-07-19 | San Diego, USA | IEEE 802.18 |  | - | Review M.2012-1 Meeting Y+1 contribution | - | - | - | - | - | -
| 2012-07-16 | 2012-07-19 | San Diego, USA | IEEE 802 |  | - | Approve M.2012-1 Meeting Y+1 contribution | - | - | - | - | - | -
| 2012-07-16 | 2012-07-20 | Geneva, Switzerland | ITU-R WP 5D | 13 | Present M.1457-11 Meeting X+2 contribution | Present M.2012-1 Meeting Y contribution | - | - | - | - | - | -
| 2012-09-17 | 2012-09-20 | Indian Wells, USA | IEEE 802.16 | 81 | - | - | - | Develop response to LS 802.16-12-0516 from WP 5D | Develop response to LS 802.16-12-0517 from WP 5D (“Review of Report ITU-R M.2039”) | - | - | -
| 2012-09-17 | 2012-09-20 | Indian Wells, USA | IEEE 802.18 |  | - | - | - | Approve response to LS 802.16-12-0516 from WP 5D | Develop response to LS 802.16-12-0517 from WP 5D (“Review of Report ITU-R M.2039”) | - | - | -
| 2012-09-20 | 2012-09-25 | E-mail process, 5 day review | IEEE 802 |  | - | - | - | Approve response to LS 802.16-12-0516 from WP 5D | Develop response to LS 802.16-12-0517 from WP 5D (“Review of Report ITU-R M.2039”) | - | - | -
| 2012-09-26 | 2012-09-26 |  | IEEE-SA ITU-R official |  | - | - | - | Submit to response to WP 5D liaison | - | - | - | -
| 2012-10-03 | 2012-10-11 | Woodland Hills, USA | ITU-R WP 5D | 14 | - | Present M.2012-1 Meeting Y+1 contribution (WP 5D/111) | - | Present response to LS 802.16-12-0516 | - | - | - | Represent Contribution ITU-R WP 5D/65 (carried forward from Meeting #13)
Response to LS 802.16-12-0516
| 2012-10-09 | 2012-10-09 | Conference call | IEEE 802 |  | - | - | - | - | - | - | - | -
| 2012-11-05 | 2012-11-15 | Geneva, Switzerland | ITU-R WP 5A | 10 | - | - | - | - | - | - | - | -
| 2012-11-12 | 2012-11-15 | San Antonio, USA | IEEE 802.16 | 82 | Review the M.1457-12 schedule determined at WP 5D Meeting #14. If development has been announced, forward 802.18-12-0070 (inserting reference to announcement); otherwise, move the same reminder to Session #84. [See IEEE 802.16-12-0520 for details.] | - | - | - | - | Develop response to LS from WP 5D 802.16-12-0519 (“Toward a preliminary draft new Report on the use of IMT for broadband PPDR”) | - | -
| 2012-11-12 | 2012-11-15 | San Antonio, USA | IEEE 802.18 |  | - | - | - | - | - | Review response to LS 802.16-12-0519 from WP 5D | - | -
| 2012-11-12 | 2012-11-15 | San Antonio, USA | IEEE 802 |  | - | - | - | - | - | Approve response to LS 802.16-12-0519 from WP 5D | - | -
2013 | 2013-01-14 | 2013-01-17 | Vancouver, Canada | IEEE 802.16 | 83 | - | Develop initial draft of M.2012-1 Meeting Y+2B contribution | - | Develop initial response to IEEE 802.16-12-0630 | Develop liaison statement with corrections and with request for intent to include to IMT-Advanced technologies | Update response to LS 802.16-12-0519 from WP 5D | - | -
| 2013-01-14 | 2013-01-17 | Vancouver, Canada | IEEE 802.18 |  | - | - | - | Review response to IEEE 802.16-12-0630 | Review liaison statement with corrections and with request for intent to include to IMT-Advanced technologies | Review updated response to LS 802.16-12-0519 from WP 5D | - | -
| 2012-01-17 | 2012-01-22 | E-mail process, 5 day review | IEEE 802 |  | - | - | - | Approve response to IEEE 802.16-12-0630 | Approve liaison statement with corrections and with request for intent to include to IMT-Advanced technologies | Approve updated response to LS 802.16-12-0519 from WP 5D | - | -
| 2012-01-23 | 2012-01-23 |  | IEEE-SA ITU-R official |  | - | - | - | Submit to response to WP 5D liaison | Submit to response to WP 5D liaison | Submit to response to WP 5D liaison | - | -
| 2013-01-30 | 2013-02-06 | Geneva, Switzerland | ITU-R WP 5D | 15 | - | - | - | Present initial response to IEEE 802.16-12-0630 | Present liaison statement | Present response to LS 802.16-12-0519 from WP 5D | - | -
| 2013-03-18 | 2013-03-21 | Orlando, USA | IEEE 802.16 | 84 | - | Finalize M.2012-1 Meeting Y+2B contribution and liaison statement to WATO | - | Develop second response to IEEE 802.16-12-0630 | - | - | - | -
| 2013-03-18 | 2013-03-21 | Orlando, USA | IEEE 802.18 |  | - | Review M.2012-1 Meeting Y+2B contribution | - | Review second response to IEEE 802.16-12-0630 | - | - | - | -
| 2013-03-18 | 2013-03-21 | Orlando, USA | IEEE 802 |  | - | Approve M.2012-1 Meeting Y+2B contribution | - | Approve second response to IEEE 802.16-12-0630 | - | - | - | -
| 2013-05-13 | 2013-05-16 | Waikoloa, USA | IEEE 802.16 | 85 | - | - | - | - | - | - | - | -
| 2013-05-13 | 2013-05-16 | Waikoloa, USA | IEEE 802.18 |  | - | - | - | - | - | - | - | -
| 2013-06-04 | 2013-06-04 | Conference call | IEEE 802 |  | - | - | - | - | - | - | - | -
| 2013-07-10 | 2013-07-17 | [TBD] | ITU-R WP 5D | 16 | - | Present M.2012-1 Meeting Y+2B contribution | - | Present second response to IEEE 802.16-12-0630 | - | - | - | -