## Slide 1: 802.16 Project Activity Schedules
17 July 2014

## Slide 2: Contents
P802.16q Schedule
P802.16r Schedule
P802.16.3 Schedule

## Slide 3: P802.16q Schedule (1/2)
July 18 – EC Conditional Approval to Sponsor Ballot
July 30 – Updated draft D2 available
Aug 1 – 15 day Letter Ballot Recirculation A begins
Aug 26 – LB Comment Resolution Teleconference
Sep 5 - 15 day Letter Ballot Recirculation B begins
Sep 23 – LB Recirc B Comment Res Teleconf
Sep 26 – 30 day Sponsor Ballot begins
Nov 3 – IEEE 802.16 WG Session #94
Nov 7 – EC Conditional Approval (RevCom)
Nov 12 – Updated draft D4 available
Nov 14 – 15-day Sponsor Ballot Recirculation A

## Slide 4: P802.16q Schedule (2/2)
2014-12-05 (UTC): Sponsor Ballot Resolution Teleconference
2014-12-19: RevCom submission deadline
2015-01-30: RevCom review teleconference
(backup schedule)
2014 Dec/2015 Jan – 15 day Sponsor Ballot Recirculation B
2015-02-13: RevCom submission deadline
2015-03-27 IEEE SASB/RevCom Approval

## Slide 5: P802.16r Schedule (1/1)
2014-07-16: 802.16 WG Chair meets with 802.15 WG to present summary slides and discuss possible transfer of P802.16r to 802.15
2014-07-17: IEEE 802.16 Closing Plenary agrees on Call for Contributions regarding PAR, Five Criteria, and Architecture and Requirements
2014-08 to 2014-09: teleconferences; possible PAR revision request by 2014-10-04
2014-11-03: Session #94

## Slide 6: P802.16.3 Schedule (1/4)
2014-07-14: IEEE 802.16 Opening Plenary agrees on summary slides
2014-07-16: 802.16 WG Chair meets with 802.15 WG to present summary slides and discuss possible transfer of P802.16.3 to 802.15

## Slide 7: P802.16.3 Schedule (2/4)
2014-07: complete IEEE 802.16.3 Architecture and Requirements for Mobile Broadband Network Performance Measurements
2014-07: call for contributions toward P802.16.3 draft
2014-08, 2014-09, 2014-10: teleconferences
[2014-09 opportunity to meet with 802.15?]
2014-11-03 to 2014-11-06: WG Session
2014-11, 2014-12, 2015-01, 2015-02: teleconferences
2015-03: WG Session

## Slide 8: P802.16.3 Schedule (3/4)
2015-03: WG decision to open WG LB
2015-03 to 2015-04: WG LB
2015-05: comment resolution
2015-06 to 2015-07: WG LB Recirc a
2015-07: EC Conditional Approval (SB)
2015-07: WG LB Recirc b

## Slide 9: P802.16.3 Schedule (4/4)
2015-08 to 2015-09: Sponsor Ballot
2015-09: comment resolution
2015-10 to 2015-11: Sponsor Ballot Recirc a
2015-11: EC Conditional Approval (RevCom)