## Pre_Release comments.csv
Index | Date | SA PIN | Name | Comment | Category | Page Number | Subclause | Line Number | Proposed Change | Must Be Satisfied
1 |  |  | Harry Bims | There are 2 page numbers at the bottom of each TOC page | Editorial | TOC 1 |  |  | Please use a page numbering that is a continuation from the previous section | 1
2 |  |  | Harry Bims | This appears to be a duplicate TOC | Editorial | TOC 49 |  |  | Please delete this duplicate TOC | 1
3 |  |  | Harry Bims | The page header format is inconsistent (see this page and the previous page for example) | Editorial | 10 |  |  | Please make sure the header format is consistent throughout the document | 1
4 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 10 |  |  | Remove the FIPS 46-3 reference | 1
5 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 10 |  |  | Remove the FIPS 74 reference | 1
6 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 10 |  |  | Remove the FIPS 81 reference | 1
7 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 10 |  |  | Remove the FIPS 186-2 reference | 1
8 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 30 |  |  | Remove DES from the list | 1
9 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 117 |  |  | Remove the extra space below "Requested Downlink Burst Profile" | 1
10 |  |  | Harry Bims | Conflicting text for Bit 7. | Editorial | 118 |  |  | Replace "Bit 7: Reserved" in the list with the subsequent sentence "Bit 7: Power down reporting indication." | 1
11 |  |  | Harry Bims | Need space between sentences | Editorial | 118 |  |  | Replace "idle mode.This" with "idle mode. This" | 1
12 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 118 |  |  | Remove the extra space after the "The Paging Controller ID is a logical network ..." paragraph | 1
13 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 120 |  |  | Remove the extra space after the "This TLV is used to request M2MCIDs update." sentence | 1
14 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 123 |  |  | Remove the extra space after the "Identifies reentry process management messages ..." paragraph | 1
15 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 124 |  |  | Remove the extra space after the "The HMAC/CMAC Tuple shall be ... " paragraph | 1
16 |  |  | Harry Bims | Subection heading numbering is wrong throughout Section 6.3.2.3.9, starting with the "M2M Key Request message" header | Editorial | 135 |  |  | Please fix the subsection numbering in subsection 6.3.2.3.9 | 1
17 |  |  | Harry Bims | Section 6.3.2.3.9.31 is out of place | Editorial | 135 |  |  | Please move down to the correct place in subsection 6.3.2.3.9 | 1
18 |  |  | Harry Bims | Section 6.3.2.3.9.33 is out of place | Editorial | 136 |  |  | Please move down to the correct place in subsection 6.3.2.3.9 | 1
19 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 156 |  |  | Remove the extra space after the "Indicates the multicast indication cycle ..." sentence. | 1
20 |  |  | Harry Bims | Many tables float downward in the text at page boundaries. This makes reading the document confusing. | Editorial | 156 |  |  | Please turn off table floating throughout the document, and anchor tables to a fixed location in the text. | 1
21 |  |  | Harry Bims | Sentence "The CIDs to be removed ..." is out of place | Editorial | 159 |  |  | Please move the sentence below "CIDs Removed from Tunnel" above | 1
22 |  |  | Harry Bims | Sentence "Specification of the service flow's traffic characteristics ..." is out of place. | Editorial | 161 |  |  | Please move the sentence below "Service Flow Parameters" above | 1
23 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 745 |  |  | Change "e.g., data encryption standard (DES) key and CBC IV" to "e.g., advanced encryption standard in CCM mode" | 1
24 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 760 |  |  | Remove the paragraph "For SAs using a ciphersuite employing DES-CBC ..." | 1
25 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 780 |  |  | Remove the sentence "For SAs using a ciphersuite employing DES-CBC ..." | 1
26 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 802 |  |  | Remove the section 7.5.1.1 | 1
27 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 809 |  |  | Remove the section 7.5.2.1 | 1
28 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 811 |  |  | Remove the section 7.5.4.1 | 1
29 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document, however this section is used to also describe how to derive AES KEKs | Technical | 811 |  |  | Move the content of section 7.5.4.2 to the beginning of section 7.5.4.5.1 and change the text "DES" and "3-DES" to "AES" | 1
30 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Technical | 811 |  |  | Remove the section 7.5.4.5.2.1 | 1
31 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 974 |  |  | Remove the extra space after the line beginning with "Figure 8-53 ..." | 1
32 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 1001 |  |  | Remove the extra space at the bottom of the page | 1
33 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 1002 |  |  | Remove the extra space at the bottom of the page | 1
34 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 1003 |  |  | Remove the extra space at the bottom of the page | 1
35 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 1021 |  |  | Remove the extra space at the bottom of the page | 1
36 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 1039 |  |  | Remove the extra space at the bottom of the table | 1
37 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 1043 |  |  | Remove the extra space at the bottom of the table | 1
38 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 1062 |  |  | Remove the extra space in the row "ACK Region Index" | 1
39 |  |  | Harry Bims | Figure 8-79 is missing | Editorial | 1241 |  |  | Please restore Figure 8-79 | 1
40 |  |  | Harry Bims | Many tables float downward in the text at page boundaries. This makes reading the document confusing. | Editorial | 1250 |  |  | Please turn off table floating throughout the document, and anchor tables to a fixed location in the text. | 1
41 |  |  | Harry Bims | Figure 8-82 is missing | Editorial | 1256 |  |  | Please restore Figure 8-82 | 1
42 |  |  | Harry Bims | Extra space needs to be removed | Editorial | 1258 |  |  | Remove the extra space after the paragraph "Mini-subchannels can be applied to ..." | 1
43 |  |  | Harry Bims | Numbers are misaligned throughout Table 8-284 | Editorial | 1270 |  |  | Fix alignment of the columns of numbers | 1
44 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1596 |  |  | Remove the Value "Encrypted TEK for DES" from the table in Section 11.9.3 | 1
45 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1597 |  |  | Remove the paragraph at the top of the page. | 1
46 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1597 |  |  | Remove the row from Table 11-42 described as "3-DES EDE with 128-bit key" | 1
47 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1599 |  |  | Remove the paragraph immediately below Table 11-43 | 1
48 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1602 |  |  | Remove the row from Table 11-46 described as "CBC mode, 56-bit DES" | 1
49 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1602 |  |  | Remove the row from Table 11-48 described as "3-DES EDE with 128-bit key" | 1
50 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1602 |  |  | Remove the row from Table 11-48 described as "CBC mode 56-bit DES, no data authentication and 3-DES,128" | 1
51 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1602 |  |  | Remove the row from Table 11-48 described as "CBC mode 56-bit DES, no data authentication and RSA, 1024" | 1
52 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1741 |  |  | Change the default for the Cryptographic-Suite-List from 56-bit DES to 128-bit AES, and remove the text ", and 3-DES EDE with 128-bit key" | 1
53 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1760 |  |  | Remove the cryptographic suite "No data encryption, no data authentication and 3-DES,128" | 1
54 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1760 |  |  | Remove the cryptographic suite "CBC mode 56-bit DES, no data authentication and 3-DES,128" | 1
55 |  |  | Harry Bims | DES has been withdrawn by NIST. Need to remove all references from the document | Editorial | 1760 |  |  | Remove the cryptographic suite "CBC mode 56-bit DES, no data authentication and RSA, 1024" | 1