## Comments
Comment ID | Comment # | Name | Style | Index # | Category | Page | Subclause | Line | Comment | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Proposed Disposition-Editor | Proposed Disposition Detail - Editor | Other3
22877500023 | i-21 | Schrage, Reinhard | Individual | 3 | General | 22 |  | 7 | diagrams blurred, script caption has shadow | No | improve rendering/resolution | Revised | Inserted diagrams in JPEG format for improved rendering/resolution when converted to PDF |  | Diagrams show up well in word but not in PDF, try different format
22877400023 | i-20 | Schrage, Reinhard | Individual | 2 | Editorial | 19 |  | 11 | N x M = 1 X 6: the multiplication 'X' is capital instead of lower case as otherwise used | No | Change 'X' to 'x', i.e. upper to lower case | Accepted | Replaced 'N x M = 1 X 6' with 'N x M = 1 x 6' |  | Change 'X' to 'x'
22877300023 | i-19 | Schrage, Reinhard | Individual | 1 | Editorial | 6 |  | 4 | The rendering of the Generator function is blurred. Pixel image used? | No | Re-enter generator fct not as pixel image | Revised | Re-formatted the equation. Also replaced "X" with "x" consistent with use in 802.16-2012 |  | Re-format equation. Also replace 'X' with lower case 'x' to be consistent with IEEE Std 802.16-2012
22775200023 | i-18 | BUCANEG, DEMETRIO JR | Individual | 12 | Technical | 25 | 12.9 | 6 | Lines 6-8 states that "This subclause defines system profiles for WirelessMAN-OFDMA systems operating with channel bandwidths less than 1.25 MHz, specifically channel bandwidths from 0.100 MHz to 1.200 MHz in step sizes of 50 kHz." Why it does not extend all the way to the upper limit of "1.25 MHz"? | No |  | Rejected | The PAR states 'up to 1.25 MHz'. P802.16s only defines BWs up to 1.20 MHz since 1.25 MHz BW is already defined published standard, IEEE std 802.16-2012 . If we included 1.25 MHz in P802.16s it would conflict with IEEE std 802.16-2012. |  | Add explanation
22775100023 | i-17 | BUCANEG, DEMETRIO JR | Individual | 11 | Technical | 23 | 8.4.14.1.1 | 1 | In "Table 8-357," the "5/6 Coding Rate" was added in "64QAM Modulation." Will there be expanded 'sequence application' for "S64-QAM" or will it remain unchanged? | No |  | Rejected | No, S64-QAM remains the same. A new sequence is not required for the 5/6 Coding Rate. |  | S64-QAM remains the same, no change necessary
22775000023 | i-16 | BUCANEG, DEMETRIO JR | Individual | 10 | General | 12 | 8.4.5.3.1 | 19 | Are there corresponding descriptions of listed "DIUC" values from "Table 8-115a"? | No |  | Rejected | Yes, there are corresponding descriptions of "DIUC" values in 802.16-2012 as amended |  | No changes necessary since there are corresponding descriptions in 802.16
22774900023 | i-15 | BUCANEG, DEMETRIO JR | Individual | 9 | Technical | 10 | 8.4.5.2 | 17 | Is "(TF ms)" or "(Tf ms)" for the "OFDMA frame duration" symbol? | No |  | Revised | Replaced "TF ms" with "Tf ms" to be consistent with IEEE Std 802.16-2012. |  | Change to Tf as in 802.16-2012
22774800023 | i-14 | BUCANEG, DEMETRIO JR | Individual | 8 | Technical | 10 | 8.4.5.1 | 11 | Countercheck "The frame number is incremented by 1 MOD 216 each frame." Confirm that "1 MOD 216" is correct and not "1 MOD 224", right? | No |  | Rejected | MOD 2^24 is specified for channel BW greater than or equal to 1.25 MHz, 'MOD 2^16 is specified in 802.16s for BW less than 1.25 MHz. |  | 16' is necessary for BW less than 1.25 MHz, '24' is specified for larger BW
22774700023 | i-13 | BUCANEG, DEMETRIO JR | Individual | 7 | Technical | 10 | 8.4.5.1 | 3 | Countercheck "Table 8-112a, Frame Number bit size" to be "16" and not "24", correct? | No |  | Rejected | Yes, this is correct, Frame number bit size of "16" is correct for channel BW less than 1.25 MHz. "24" applies to channel BWs greater than or equal to 1.25 MHz. |  | 16' is necessary for BW less than 1.25 MHz, '24' is specified for larger BW
22774600023 | i-12 | BUCANEG, DEMETRIO JR | Individual | 6 | Editorial | 7 | 8.1.5.3.7 | 26 | Second sentence is very long. Suggest segmentation as shown. | No | Modify as: "For channel BWs greater than or equal to 1.25 MHz, QPSK shall be supported, while with 16-QAM and 64-QAM. are optional for channel BWs greater than or equal to 1.25 MHz and For channel BWs less than 1.25 MHz, QPSK, 16-QAM, and 64QAM shall be supported. for channel BWs less than 1.25 MHz, with the In both applications, mappings of bits to symbols shall be identical to those described in 8.1.4.4.7." | Revised | Modified sentence at line 26 as follows: "QPSK shall be supported, while 16-QAM and 64-QAM are optional for channel BWs greater than or equal to 1.25 MHz. QPSK, 16-QAM, and 64QAM shall be supported for channel BWs less than 1.25 MHz, with the mappings of bits to symbols identical to those described in 8.1.4.4.7" |  | Break this long sentence into two sentences for better readability
22774500023 | i-11 | BUCANEG, DEMETRIO JR | Individual | 5 | Editorial | 5 | 6.3.3.5.3 | 29 | Minor edit and combined statements in Lines 29 and 31 in a paragraph as shown. | No | Rewrite as: "For DL-MAP and UL-MAP messages with channel bandwidths less than 1.25 MHz The CRC8 shall be used For for DL-MAP and UL-MAP messages with channel bandwidths less than 1.25 MHz. The data Data (input) bytes shall not be flipped as in OFDM mode." | Revised | Modified sentence as follows: "CRC8 shall be used for DL-MAP and UL-MAP messages with channel bandwidths less than 1.25 MHz" |  | CRC8 shall be used for DL-MAP and UL-MAP messages with channel bandwidths less than 1.25 MHz
22774400023 | i-10 | BUCANEG, DEMETRIO JR | Individual | 4 | Editorial | 5 | 6.3.3.5.2 | 23 | Minor edit as shown. | No | Rewrite as: "For DL-MAP and UL-MAP messages with channel bandwidths greater than or equal to 1.25 MHz The CRC32 shall be used Ffor DL-MAP and UL-MAP messages with channel bandwidths greater than or equal to 1.25 MHz." | Revised | Modified sentence at Line 23 as follows: "CRC32 shall be used for DL-MAP and UL-MAP messages with channel bandwidths greater than or equal to 1.25 MHz." |  | CRC32 shall be used for DL-MAP and UL-MAP messages with channel bandwidths greater than or equal to 1.25 MHz.
22774300023 | i-9 | BUCANEG, DEMETRIO JR | Individual | 3 | Editorial | 4 | 6.3.2.3.2 | 32 | Minor edit as shown. | No | Revise as: "For channel bandwidth below 1.25 MHz, a BS shall generate DL-MAP messages in..." | Revised | Modified sentence at Line 32 as follows: "For channel bandwidth below 1.25 MHz a BS shall generate DL-MAP messages in the format shown in Table 6-57a." |  | For channel bandwidth below 1.25 MHz a BS shall generate DL-MAP messages in the format shown in Table 6-53a, including all of the following parameters:
22774200023 | i-8 | BUCANEG, DEMETRIO JR | Individual | 2 | Editorial | 2 | 3 | 1 | Minor edit on the definition as shown. | No | Revise as: "Adjacent subcarrier permutation: A permutation scheme in which symbol data within a subchannel is assigned to adjacent subcarriers and where the pilot and data subcarriers are assigned fixed positions in the frequency domain within an OFDMA symbol." | Accepted | Modified sentence at Line 1 as follows: "Adjacent subcarrier permutation: A permutation scheme in which symbol data within a subchannel is assigned to adjacent subcarriers and where the pilot and data subcarriers are assigned fixed positions in the frequency domain within an OFDMA symbol." |  | Add the word "where" to the definition as proposed
22774100023 | i-7 | BUCANEG, DEMETRIO JR | Individual | 1 | Technical | iii | Abstract | 2 | Just for clarification of phrase as "...spectrum with channel bandwidth from 100 kHz up to 1.20 MHz..." This "1.20 MHz" upper limit should match the document's "1.25 MHz" higher end, shouldn't be? | No |  | Rejected | The PAR states 'up to 1.25 MHz'. P802.16s only defines BWs up to 1.20 MHz since 1.25 MHz BW is already defined published standard, IEEE std 802.16-2012 . If we included 1.25 MHz in P802.16s it would conflict with IEEE std 802.16-2012. |  | As per comment 5 above
22764100023 | i-6 | Nikolich, Paul | Individual | 3 | General | 18 | 8.4.6.1.2 | 15 | I am unfamiliar with the term "boosted BPSK modulation". Is this a well known term of art, or does it need a definition in this amendment? | No |  | Rejected | The term "boosted BPSK modulation " is already used extensively in 802.16-2012, clause 8.4.6.1.1 and in several other places in IEEE Std 802.16 and described there as well. We are not modifying the usage in this document from what has been used in 802.16-2012. |  | The term "boosted BPSK modulation " is already used extensively in 8..4.6.1.1 and in several other places in P802.16Rev4 and described there as well. We are not modifying the usage in this document from what has been used in 802.16-2012.
22764000023 | i-5 | Nikolich, Paul | Individual | 2 | General | 7 | 8.1.3 | 8 | Does Table 8.2 reflect the PHY Type defined in this amendment? This amendment doesn't specify amending Table 802. | No |  | Rejected | Yes, Table 8-2 does reflect the PHY type defined in this document. It is not necessary to amend Table 8-2. |  | No action required
22763900023 | i-4 | Nikolich, Paul | Individual | 1 | General | 2 | 3 | 4 | Is "AMC", which I assume is an acronym for Adaptive Modulation & Coding, defined in the base standard? If not, it should be defined in this amendment. | No |  | Revised | In IEEE 802.16-2012, the acronym "AMC" is used extensively in connection with permutation as in "Band AMC" but the acronym 'AMC' has never been defined in this context. Have modified in P802.16s to connect 'AMC' with 'Band' as in "Band AMC" for better distinction between its use as a 'permutation scheme' as opposed to 'Adaptive Modulation and Coding (AMC)'. |  | In IEEE 802.16-2012, the acronym "AMC" is used extensively in connection with permutation as in "Band AMC" but the acronym 'AMC' has never been defined in this context. Propose editing in this document to always connect with 'Band' as in 'Band AMC' for better distinction between its use as a permutation scheme as opposed to 'Adaptive Modulation and Coding (AMC)'.
22538300023 | i-3 | Marks, Roger | Individual | 2 | Editorial |  |  |  | Comment from Lisa Perry of IEEE-SA: "The equation on page 6 looks like a blurry image" | No |  | Revised | Re-formatted the equation, checked in PDF now OK |  | Equation OK in Word format not OK in PDF format, try reformatting the equation.
22538200023 | i-2 | Marks, Roger | Individual | 1 | Editorial |  |  |  | Comment from Lisa Perry of IEEE-SA: "1) Table 8-174a appears beyond the right margin" | No |  | Revised | Re-formatted Table 8-174a to fit within the right margin |  | Re-format the table
22508800023 | i-1 | Perry, Lisa | Editorial Coordination | 1 | General |  |  |  | This draft meets all editorial requirements. | No |  |  | No action required |  | No action required

## Vote Report
Recirculation #1
Ballot Open Date: | 22-Mar-2017
Ballot Close Date: | 01-Apr-2017
Draft #: | D2.1
Recirc Ballots Received: | 5
Recirc Vote Changes: | 2
Recirc Comments: | 10
affirmative votes: | 86
negative votes with comments | 3 | Grow, Robert (all initial ballot comments resolved satisfactorily) | Hamilton, Mark (no response following initial ballot) | Roy, Richard (no response following initial ballot)
negative votes with new comments: | 0
negative votes without comments: | 0
abstention votes: | 4
votes received: | 93
return rate: | 80%
abstention rate: | 4%
APPROVAL RATE: | 96%