## Sheet 1
Table 1
Comment ID | Date | Comment # | Name | Email | Phone | Style | Index # | Classification | Vote | Affiliation | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Proposed Disposition - Editor | Disposition Status | Disposition Detail | Other1 | Other2 | Other3
23716200023 | 04-Sep-2017 10:38:15 ET | i-9 | Thomas, Angela |  |  | RAC Coordination Coordination | 3 |  |  |  | Technical | 147 |  | 19 | RAC comment: The expansion should not use all lower case. |  | Yes | Internet Assigned Numbers Authority should be used here | Change to "Internet Assigned Numbers Authority" (capitalize) | unreviewed
23716100023 | 04-Sep-2017 10:36:11 ET | i-8 | Thomas, Angela |  |  | RAC Coordination Coordination | 2 |  |  |  | Technical | 1601 | 11.1.5 | 6 | RAC comment: The text refers to a 3-byte organizationally unique identifier. Because the text also indicates it is associated with a MAC address, presumably this is expected to be an OUI obtained from the IEEE Registration Authority. There is no easily determined reason why this should be restricted to OUI and not also allow the Vendor ID to be based on either an Organizationally Unique Identifier or a Company ID. Please note that first time customers require a special exemption from IEEE RA policy to buy an MA-L with its included OUI, but rather are told to buy a smaller address block and a Company ID. Therefore, it is also incorrect to assume that the first three octets of a received Source Address are an OUI, because for smaller address blocks (MA-M and MA-S), the base first three octets are assigned to the IEEE Registration Authority and would be the same first three octets for assignments made to multiple companies. Most standards include an indication of where to get the OUI or Company ID. Most standards also include Organizationally Unique Identifier (OUI) in the definitions, and add Company ID also as it is added to the specifications, though the limited uses may not justify doing this. The RAC notes that the abbreviation of CID is used extensively in the draft for connection identifier, so the recommendation would be to use the name Company ID and not create a second abbreviation expansion for CID in the draft. |  | Yes | The standard should allow the vendor to use either an OUI or Company ID. "The value field contains the vendor identification specified by a 3-byte, vendor-specific unique identifier. This vendor-specific unique identifier may be either an Organizationally Unique Identifier or Company ID." Footnote the above text: 1. Organizationally Unique Identifier or Company ID may be obtained from the IEEE Registration Authority (www.standards.ieee.org/regauth). 2. The IEEE Registration Authority uses the abbreviation CID for Company ID but that abbreviation is used in this standard for connection identifier. The above change also requires parallel changes on P. 1993, though footnotes need not be repeated, but could be as is done for Operator ID footnotes on page 231 and 351. |  | unreviewed
23716000023 | 04-Sep-2017 09:38:39 ET | i-7 | Thomas, Angela |  |  | RAC Coordination Coordination | 1 |  |  |  | Technical | 2222 | 13.2.4 | 22 | RAC comment: The draft uses both Ethertype and EtherType. Today, the RA consistently uses Ethertype on the tutorial and product pages. The RAC is not currently trying to enforce either of the capitalizations, but does ask that a document be internally consistent in which form it uses. (The use of ethertype in variable names and other syntax content is acceptable, and need not be changed.) |  | Yes | Please pick one capitalization form and apply consistently (either 12 or 24 changes required depending on which form is selected). | Change instances of "EtherType" to "Ethertype" | unreviewed
23695200023 | 30-Aug-2017 14:32:19 ET | i-6 | Marks, Roger |  |  | Individual | 5 | Consulting | Approve | EthAirNet Associates | Technical | 1626 | 11.3.1 | 20 | In about 6 places in Table 11-16, the language "This TLV is used in NBR-ADV" is used, whereas the current standard says "This TLV shall be used in NBR-ADV". I see no justification for the change. |  | No | Throughout Table 11-16, change "This TLV is used in NBR-ADV" to "This TLV shall be used in NBR-ADV". | Throughout Table 11-16, change "This TLV is used in NBR-ADV" to "This TLV shall be used in NBR-ADV". | unreviewed
23695100023 | 30-Aug-2017 14:13:55 ET | i-5 | Marks, Roger |  |  | Individual | 4 | Consulting | Approve | EthAirNet Associates | Editorial | 1752 | 11.12 | 10 | There are four instances on pp. 1752-1753 of "Bits 15-8 are only sent if length = 2" (in two cases, marked as a NOTE). However, on p. 1751, the language is "Bits 15-8 shall only be sent if length = 2." |  | No | On pp. 1752-1753, change "Bits 15-8 are only sent if length = 2" (two cases) and "NOTE- Bits 15-8 are only sent if length = 2" (two cases) to "Bits 15-8 shall only be sent if length = 2." | On pp. 1752-1753, change "Bits 15-8 are only sent if length = 2" (two cases) and "NOTE- Bits 15-8 are only sent if length = 2" (two cases) to "Bits 15-8 shall only be sent if length = 2." | unreviewed
23695000023 | 30-Aug-2017 14:08:01 ET | i-4 | Marks, Roger |  |  | Individual | 3 | Consulting | Approve | EthAirNet Associates | Editorial | 1751 | 11.12 | 20 | There are several references on pp. 1751-1753 to "Bits 15-8". This is confusing in the context since, in the remainder of the cell, the bits are discussed in increasing order. |  | No | On pp. 1751-1753, change "Bits 15-8" to "Bits 8-15" (7 instances). | On pp. 1751-1753, change "Bits 15-8" to "Bits 8-15" (7 instances). | unreviewed
23694800023 | 30-Aug-2017 13:32:46 ET | i-3 | Marks, Roger |  |  | Individual | 2 | Consulting | Approve | EthAirNet Associates | Editorial | 2695 | E | 0 | The incorrect footer "Copyright (C)2016. All rights reserved." appears here, and elsewhere (5 places). |  | No | Change to "Copyright (C) 2017 IEEE. All rights reserved." Don't forget the "IEEE". | Change to "Copyright (C) 2017 IEEE. All rights reserved." Don't forget the "IEEE". | unreviewed
23694700023 | 30-Aug-2017 13:30:33 ET | i-2 | Marks, Roger |  |  | Individual | 1 | Consulting | Approve | EthAirNet Associates | Editorial | 2695 | E.3 | 0 | The incorrect label "IEEE P802.16RevX/March2016" appears here, and elsewhere (8 places). |  | No | Replace throughout with "IEEE P802.16Rev4/D4 September 2017" [or other appropriate draft number and month] | Replace throughout with "IEEE P802.16Rev4/D4 September 2017" [or other appropriate draft number and month] | unreviewed
23648100023 | 20-Aug-2017 03:20:40 ET | i-1 | Freedman, Avraham |  |  | Individual | 1 | Producer - Component | Approve | Satixfy | General | 791 | 6.3.20.2.10 | 11 | The reference to previous amendments (16e here, but also 16f, ,16g in other places) is not clear, especially in the context of a revision which should consolidate all previous amendments. A reference to a previous revision (802.16-2009 for example) or a reference to sections within this document would probably be better. |  | No | Review the indications of previous amendments and replace with references to previous revisions, or to the body of the document itself. | References to "16f" and "16g" are spelled out and often specifically mention deprecated material. 16e in the cited cases appear to refer to "Legacy" devices. The closest I can find to "Legacy" definition is 7.2.2.2.11 "Legacy mobiles. To handle legacy mobiles and base stations that were developed in accordance with IEEE Std 802.16e-2005/Cor1...". Two possible solutions: 1) "16e" is changed to "Legacy" in the following locations: page 791 line 11, page 791 line 13, page 1612 line 11, page 1766 line 15, and page 1803 line 3. Define "Legacy" as shown above from 7.2.2.2.11. or 2) change "16e" to "IEEE Std 802.16e-2005" in the cited locations. | unreviewed