IEEE P802.19

Wireless Coexistence

| Project | IEEE P802.19 Coexistence TAG |  |
| --- | --- | --- |
| Title | Procedure for Development of the “Recommended Practice on Methods of Assessing Coexistence of Wireless Networks” |  |
| Date Submitted | [May 15, 2006] |  |
| Source | [Stephen J. Shellhammer] [Qualcomm, Inc.] [5775 Morehouse Drive] [San Diego, CA 92121] | Voice: [(858) 658-1874] Fax: [(858) 651-3004] E-mail: [shellhammer@ieee.org] |
| Re: | [PAR – Recommended Practice on Methods for Assessing Coexistence of Wireless Networks] |  |
| Abstract | [The is for development of the 802.19 Recommended Practice] |  |
| Purpose | [] |  |
| Notice | This document has been prepared to assist the IEEE P802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. |  |
| Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.19. |  |

- Introduction

The 802.19 PAR [1] is for a Project to develop a Recommended Practice on Methods for Assessing Coexistence of Wireless Networks.  The call-for-submissions [2] for contribution for the Recommended Practice was distributed after the approval of the PAR by NesCom.

This document describes the process that the 802.19 TAG will use to evaluate the contributions and develop the Recommended Practice.

- Contribution: Presentation

Initial contributions will consist of a presentation on one of the following categories:

- Coexistence scenarios

- Coexistence metrics

- Methods for evaluating coexistence metrics

The presentation will be given at an 802.19 TAG session.  More information about the submission can be found in [2].

After the submission has been presented the TAG will review the presentation and give the presenter feedback as to whether there is support for this contribution. Since the recommended practice will include multiple coexistence scenarios, coexistence metrics and methods of evaluation the TAG will accept multiple contributions.  So there will be no down-select vote since acceptance of one contribution does not preclude acceptance of any other contribution.

The TAG will hold a straw poll to decide if the presentation if there is enough interest in the proposal.  If there is sufficient interest then the proposers should prepare a detailed technical word document.

- Contribution: Technical Specification

The technical specification document will include a detailed description of the text intended to be included in the recommended practice.  The technical specification should cover one of the following areas of contribution,

- Coexistence scenarios

- Coexistence metrics

- Methods for evaluating coexistence metrics

The TAG will also accept contributions of text that include other general description to be included in the recommended practice.  These contributions will be driven by the need to develop a complete draft which will be ready for letter ballot.

The format of the technical specification should conform to the formatting guidelines X.

After a review of the technical specification the TAG will vote whether to include the text from the technical specification into the “working document.”  The working document consists of all accepted contributions.  Once the TAG has agreed that the “working document” is sufficiently complete it will be handed over to the technical editor, who will perform the necessary editorial changes so that the document is in “draft form” and is ready for letter ballot.

The vote on whether to accept the technical specification and include it into the “working document” will be held at either a plenary session or an interim session at which a quorum is present.  The vote is a technical vote and requires a 75% approval to pass.

- Schedule

The TAG will begin hearing submissions at the May 2006 Wireless Interim Session.

The plan is for the TAG to agree first on the classes of coexistence scenarios, then to agree on the coexistence metrics and then finally to agree on methods for evaluating coexistence metrics.  The anticipated schedule for hearing submissions is as follows

Submission Schedule

| Types of Submission | Dates for Presentation of Submissions |
| --- | --- |
| Classes of Coexistence Scenarios | May 2006 Wireless Interim July 2006 Plenary |
| Coexistence Metrics | September 2006 Wireless Interim |
| Methods for Evaluation of Coexistence Metrics | November 2006 Plenary January 2007 Wireless Interim |

This schedule is to be used as a guideline and is not binding.  The final decision of whether the  TAG will hear a presentation or review a technical specification is the decision of the TAG.  The decision of whether to hear a presentation or review a technical specification during a TAG session is based on the approval of the agenda.  The vote to approve the agenda requires a simple majority.

- References

- IEEE 802.19 PAR – Recommended Practice on Methods for Assessing Coexistence of Wireless Networks, March 30, 2006, http://standards.ieee.org/board/nes/projects/802-19.pdf

- S. Shellhammer, Call for Submissions – Contributions for a Recommended Practice on Methods for Assessing Coexistence of Wireless Networks, IEEE 802.19-06/0011r4, April 4, 2006