IEEE P802.19
Wireless Coexistence

|  |
| --- |
| Timeline Document |
| Date: 2010-03-17 |
| Author(s): |
| Name | Company | Address | Phone | email |
| Mika Kasslin | Nokia Research Center | Itämerenkatu 11-13, 00180 Helsinki, Finland | +358-50-4836294 | mika.kasslin@nokia.com |
|  |  |  |  |  |

Abstract

This document contains target timeline for standard development process in 802.19 Task Group 1.

**Notice:** This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|   | 2010 | 2011 | 2012 | 2013 |
|   | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 |
| Task Group formed | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| System Design Document completed |   | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Call for Proposals issued |   | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Notification of intent from proposers |   | x | x | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Contribution presentations with straw polls |   |   | x | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Proposal presentations |   |   |   | x | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Round of votes on proposals in clause order |   |   |   |   |   | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Create candidate draft document |   |   |   |   |   | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Comment ballot on the candidate draft |   |   |   |   |   | x | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Comment resolutions on the candidate draft |   |   |   |   |   |   | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Confirmation vote for creation of a draft normative text (Draft 1.0) |   |   |   |   |   |   | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |
| Adoption of draft normative text |   |   |   |   |   |   | x |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |   |