## IEEE_Cover
2011-09-14 |  | IEEE P802.19.1-11/0091r02
IEEE P802.19.1
Project | IEEE P802.19.1
Title | P802.19.1 Task Group Review 1 Comments List
Date Submitted | September, 2011
Source | Tuncer Baykas | Voice:
| NICT | Fax: [ ]
E-mail: tbaykas@ieee.org
Re:
Abstract
Purpose | [This document provides contains the commets and resolutions for Task Group Review 1. ]
Notice | This document has been prepared to assist the IEEE P802.19.1. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Revision 0 | Initial List of comments received during the task group review 1
Revision 1 | Includes list of assigned people during Monday PM1 time slot
Revision 2 | Includes resolved comments during Monday PM2 time slot

## Comment entry
CID | Name | Email | Affiliation | Vote | Clause | Subclause | Page | Line | Type | PartOfNoVote | Comment | SuggestedRemedy | Response | Status | Category | AssignedTo | E status | T status | First Discussion Time
6 | Mika Kasslin |  |  | Nokia | 3 | 3.3.2 | 5 | 28 | T |  | What does an intra-CM neighbor mean? | Specify it |  | A |  | Kang |  | A | Monday PM2
55 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.1 | 173 | 14 | T |  | What is target protection service contour? | Please specify |  | A |  | Sato |  | A | Monday PM2
56 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.1 | 173 | 15 | T |  | What is a prioritized TVBD network or device? Who does the prioritization and how is it done? | Please clarify |  | A |  | Sato |  | A | Monday PM2
60 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.3 | 174 | 6 | T |  | The paragraph is hard to read and understand. It would be good to rewrite it. It also misuses "shall". | Consider replacing the paragraph with the following: "If one considers the mutual in-block/out-of-block interference effects among TVBDs, one selection criterion is to choose the closest point for each TVBD in the protected contour of the protection service. This is illustrated in Figure 191." |  | A |  | Sato |  | A | Monday PM2
61 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.4 | 174 | 41 | T |  | Slave and master TVBDs should be specified | Please specify |  | A |  | Sato |  | A | Monday PM2
62 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.4 | 174 | 41 | T |  | What target TVBD is? | Please specify |  | A |  | Sato |  | A | Monday PM3
63 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.5.1 | 175 | 29 | T |  | I suppose the assumption is that a CM runs this algorithm. The first sentence seems to state that the CM needs to know which channel is used by the victim receiver. How the CM knows that? | Please clarify |  | A |  | Sato |  | A | Monday PM2
65 | Mika Kasslin |  |  | Nokia | 9 | 9.4.4.1 | 166 | 9 | T |  | Misuse of "will" | Replace "...it will make..." with "...makes..." | Agree | C |  | Sato |  | C | Monday PM2
66 | Mika Kasslin |  |  | Nokia | 9 | 9.4.4.1 | 166 | 10 | T |  | Misuse of "shall" | Replace "...method shall enable..." with "...method enables..." | Agree | C |  | Sato |  | C | Monday PM2
67 | Mika Kasslin |  |  | Nokia | 9 | 9.4.4.1 | 166 | 21 | T |  | This paragraph and the following two bullet points seem to be misplaced since they look like giving very common rules for all the algorithms. I wonder if that's the intention. | Please clarify and consider deleting the common rules since they are stated in the beginning of the claues 9. | Principal, delete the paragraph | C |  | Sato |  | C | Monday PM2
84 | Jari Junell |  |  | Nokia | 4 | 2.2.3.3 | 24 | 14 | T |  | ACLR and ACS is not used anywhere in a document? | Remove if not used. |  | A |  | Sato |  | A | Monday PM2
110 | Stanislav Filin |  |  | NICT | 3 | 3.2 | 4 | Figure 1 | T |  | Interface A is not shown in Figure 1 | Show interface A in Figure 1 | Agree | C |  | Filin |  | C | Monday PM2
111 | Stanislav Filin |  |  | NICT | 4 | 4.1 | 14 | 27 | T |  | 802.19.1 does not require modification of TVBD standards | Delete the sentence "A 1-to-1 mapping might be highly desirable to ..." |  | A |  | Filin |  | A | Monday PM2
113 | Stanislav Filin |  |  | NICT | 4 | All | All |  | T |  | Contribution 11-70r1 used ASN.1 notation for data type definitions in the tables. For example, in Table 13 (number from the draft) it was "REAL" not "Real" and "SEQUENCE OF INTEGER OPTIONAL" not "Sequence of integers optional" | Switch back to ASN.1 notations. If needed/desired reference to ASN.1 should be provided. |  | A |  | Filin |  | A | Monday PM2
115 | Stanislav Filin |  |  | NICT | 5 | 5 | 41 | 1 | T |  | Title of clause 5 is "procedures and protocols", but it does not contain protocol description. | Chage title of clause 5 to "Procedures and messages" | Agree | C |  | Filin |  | C | Monday PM2
127 | Junyi Wang |  |  | NICT | 3 | 3.5.3 | 9 | 8 | T | NO | the inter-CM and intra-CM neighbor shall be clarified. |  |  | A |  | Kang |  | A | Monday PM2
154 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.2 | 168 | 42--45 | T |  | "The obligation interference ... In the other classes." will not be necessary here. | Remove this sentence. | Agree | C |  | Sato |  | C | Monday PM2
41 | Mika Kasslin |  |  | Nokia | 9 | 9.4.7 | 182 | 44 | T |  | The draft has no description on master / slave CM selection. Such description needs to be provided in order to have unified manner to run such a procedure. We need to also agree on what's mandatory and what's optional from this procedure perspective. | Add a new subclause to this clause of "Other algorithms of coexistence management" to address master/slave selection and management. One possibility is to have a subclause to deal with "Topology management" in general and have master/slave selection as one item within. |  | A |  | Yi |  | A | Thursday PM1
47 | Mika Kasslin |  |  | Nokia | 4 | 4.2.2.5.1 | 31 | 15 | T |  | I would challenge the current description that states that a CM can request a TVBD to perform measurements. At the end there will be typically measurements done in the TVBDs but more precise wording here would be to require measurement reports. | Revise the description to state that one requires measurement reports. |  | A |  | Yi |  |  | Thursday PM1
94 | Jari Junell |  |  | Nokia | 9 | 4 |  |  | T |  | Nowhere is specified a decision making algorithm in distributed topology, where the fairness is taken into account, when considering amount of requested resources and also how to minimize the rate of resource changes. | Specify an algorithm |  | A |  | Yi |  | A | Thursday PM1
239 | Bonghoe Kim |  |  | LGE | 7.2.1.1 |  |  |  | T |  | I think two messages from CM should be added: CM_Reconfiguration_Request, CM_Reconfiguration_Response as those messages can be exchange between CMs regardless of its status | Please add two messages and add description sections as well |  | A |  | Yi |  | A | Thursday PM1
243 | Bonghoe Kim |  |  | LGE | General |  |  |  | T |  | It will be very helpful if we can add some flow diagram at least for initial system setup (e.g., how TVBD joins CE & CM, how CM joins CDIS, etc) in appendix |  |  | A |  | Yi |  | A | Thursday PM1
8 | Mika Kasslin |  |  | Nokia | 3 | 3.3.2 | 5 | 20 | T |  | This is stated to be a list of main functions but it contains such functions that are not necessarily needed in all the CMs. This looks more like an extensive list of possible functions than the main functions. | Please clarify |  | A |  | Kasslin |  | A | Tuesday AM2
22 | Mika Kasslin |  |  | Nokia | 3 | 3.6.2.3 | 10 | 51 | T |  | This subclause doesn't deal with an algorithm but gives very basic guidelines for all the algorithms we have agreed on and that are stated in clause 9.3. | Consider adding a short separate subclause earlier to the clause 3.6 to introduce to the basic rules stated in clause 9.3 and delete this subclause from the list of algorithm examples. |  | A |  | Kasslin/Kang |  | A | Tuesday PM1
32 | Mika Kasslin |  |  | Nokia | 4 | 4.2.2.4.9 | 30 | 3 | T |  | This should be an indication primitive instead | Update the primitive accordingly |  | A |  | Lee |  | A | Tuesday PM1
33 | Mika Kasslin |  |  | Nokia | 5 | 5.1.6.4 | 49 | 29 | T |  | The primitive from a CE to a TVBD is incorrect and should be an indication instead | Fix it |  | A |  | Lee |  | A | Tuesday PM1
71 | Mika Kasslin |  |  | Nokia | 9 | 9.4.7.1 | 178 | 29 | T |  | One shouldn't use "shall" with open sentences. Now there is etc at the end of the sentence that has "shall" in. | Replace "shall" with "may" |  | A |  | Kang |  | A | Tuesday PM1
114 | Stanislav Filin |  |  | NICT | 4 | 4.3 | All |  | T |  | Data type definition in 4.3 is almost the same as data type definition in 5.3. | Merge two data type definitions and move to normative annex. |  | A |  | Filin |  | A | Tuesday PM1
119 | Stanislav Filin |  |  | NICT | 5 | 5.3 | All |  | T |  | 5.3 needs to be merged with 4.3 and moved to the normative annex. | See my comment to 4.3. |  | A |  | Filin |  | A | Tuesday PM1
120 | Stanislav Filin |  |  | NICT | 5 | 5.2 |  |  | T |  | Subclause 5.2 defines messages, but message encoding is not specified. | Create an annex specifiing encoding of messages specified in 5.2. |  | A |  | Filin |  | A | Tuesday PM1
122 | Stanislav Filin |  |  | NICT | 7 | All | All |  | T |  | It is not clear how CM operation uses algorithms described in clause 9. | Clarify this point. |  | A |  | Filin |  | A | Tuesday PM1
123 | Stanislav Filin |  |  | NICT | 8 | All | All |  | T |  | It is not clear how CDIS operation uses algorithms described in clause 9. | Clarify this point. |  | A |  | Filin |  | A | Tuesday PM1
132 | Junyi Wang |  |  | NICT | 4 | 4.2.2.4.9 | 29 | 44 | T | NO | the title of this section shall be ChannelClassification.announcement | as indicated |  | A |  | Lee |  | A | Tuesday PM1
162 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.6.5.2 | 175--178 | 42 | T |  | Unclear | Replace it to the revised text in "Section94652..docx". |  | A |  | Sato |  | A | Tuesday PM1
49 | Mika Kasslin |  |  | Nokia | 9 | 9.4.7.2 | 181 | 46 | T |  | The first sentence of the paragraph doesn't read very well. Could you please clarify it? I think it would be really valuable to start by defining what is meant with un-configuration. It is not clear at all now what the algorithm is about. | Please provide an introduction of few sentences describing what is meant with un-configuration. |  | A |  | Kasslin |  | A | Tuesday PM2 | ?
51 | Mika Kasslin |  |  | Nokia | 9 | 9.4.7.2 | 181 | 53 | T |  | What is CMS? | Please specify |  | A |  | Kasslin |  | A | Tuesday PM2
52 | Mika Kasslin |  |  | Nokia | 9 | 9.4.7.2 | 181 | 44 | T |  | The whole subclause is quite unclear and hard to read. It requires a complete rewrite. Actually it looks like the only issue discussed in the clause is measurement process and how CM requests TVBDs to measure. Consequently I wonder if we could have this covered by some text in the measurements clause at the end of the draft. | Please consider a complete rewrite |  | A |  | Kasslin |  | A | Tuesday PM2
116 | Stanislav Filin |  |  | NICT | 5 | 5.1 | 41 | 4 | T |  | Subclause 5.1 does not have introduction part, while it is very important. | Provide introduction at the beginning of subcluase 5.1. It is important to show the relationship between 5.1 and 6, 7, 8. Procedures described in 5.1 illustrates several typical procedures described in the entity protocols in 6, 7, and 8. |  | A |  | Filin |  | A | Tuesday PM2
117 | Stanislav Filin |  |  | NICT | 5 | 5.1 | All |  | T |  | Procedures in 5.1 is very difficult to understand because there is no description, just figures. | Provide description to all procedures. |  | A |  | Filin |  | A | Tuesday PM2
121 | Stanislav Filin |  |  | NICT | 6 | All | All |  | T |  | Clause 6 description of message processing is incomplete. | It is better to describe how interface A primitives are converted into interface B1 messages and other direction. |  | A |  | Filin |  | A | Tuesday PM2
23 | Mika Kasslin |  |  | Nokia | 3 |  | 12 | 51 | T |  | The system description clause doesn't deal with different decision making topologies and their implications to CMs. That's one of the most important aspects of the whole system and the reader should be given a clear overview on different topologies already here in the system description clause. | Please provide a new clause that provides an introduction to different decision making topologies. The clause should describe the topologies with illustrative examples and figures and one shouldn't forget mixed cases either. |  | A |  | Kasslin |  | A | Wednesday AM2
40 | Mika Kasslin |  |  | Nokia | 9 | 9.3.1 | 146 | 36 | T |  | There is nothing about how CMs that apply different decision making topologies intearct with each other when they serve neighbors. How, as an example, a master CM takes into account a network that is a neighbor of a network it serves but that is served by a CM that applies distributed decision making? | Specify such rules and provide corresponding description in a suclause within a subclause dealing with "Other algorithms of coexistence management". |  | A |  | Kasslin |  | A | Wednesday AM2
1 | Mika Kasslin |  |  | Nokia | 1 | 1.1 | 1 | 33 | T |  | Inconsistent use of phrase "TV Band Device (TVBD) networks or dissimilar TV Band devices" throughout the whole draft. The most typical phrase is "TVBD network or device" that doesn't sound too good. We should come up with one good phrase that is used throughout the whole spec when talking e.g. about user of a coexistence service. | Use "TVBD network or TVBD" instead of "TVBD network or device". |  | O
3 | Mika Kasslin |  |  | Nokia | 3 | 3.2 | 4 | 50 | T |  | What is a neighbor TVBD network or device? We need to come up with a clear definition for a neighbor. Can we say that networks are neighbors or should we limit this only to devices? | Specify neighborhood |  | O
4 | Mika Kasslin |  |  | Nokia | 3 | 3.3.1 | 5 | 13 | T |  | What are the TVBD-specific reconfiguration requests and where they are specified? How do they relate to the SAP defined for the interface between a CE and a TVBD? | Please clarify and possibly specify the commands |  | O
5 | Mika Kasslin |  |  | Nokia | 3 | 3.3.1 | 5 | 16 | T |  | What is a coexistence message? | Specify what's meant with a coexistence message |  | O
10 | Mika Kasslin |  |  | Nokia | 3 | 3.3.3 | 5 | 46 | T |  | What does an inter-CM neighbor mean? | Specify it |  | O
12 | Mika Kasslin |  |  | Nokia | 3 | 3.4.1 | 6 | 5 | T |  | Is the list intended to be complete covering all the information carried in the interface from a TVBD to a CE? Or is there some more information that is transmitted in the interface? Similar comment applies to all the interface sub clauses (3.4.1 through 3.4.5). | If the intention is to have a complete list, make it complete since it doesn't contain now all the information of the interface. I prefer, however, an incomplete list and a related clarification to the introduction before the list by adding "example" to the sentence. |  | O
14 | Mika Kasslin |  |  | Nokia | 3 | 3.5.2 | 8 | 40 | T |  | Is this limitation to a TVBD or restriction of the coexistence system? If the intention is to say that a CM shall not provide more than one service to a CE at a time I think we should say it like that instead. | Please clarify |  | O
15 | Mika Kasslin |  |  | Nokia | 3 | 3.5.2 | 8 | 46 | T |  | "The TVBD network or device needs to provide information to the coexistence system..." Does this mean to say that when one uses the information service, no information needs to be provide to the system? I hope not since already in authentication and registration one needs to provide some information. | Please clarify or delete the sentence |  | O
16 | Mika Kasslin |  |  | Nokia | 3 | 3.5.2 | 8 | 47 | T |  | "...needs to perform measurements according to requests..." I think that's not true. A CM may issue measurement requests but these don't mandate actual measurements at least always. This can be too easily read like a CM is in control of actual measurements and that's not the intention. | Please revise to state e.g. that "...needs to provide measurement reports according to the requests..." |  | O
20 | Mika Kasslin |  |  | Nokia | 3 | 3.6.2.2 | 10 | 1 | T |  | I don't believe this should be classified as a coexistence decision making algorithm since this doesn't deal with any decision making but the intention is to classify channels and the classification is possibly used as an input for decision making. | Create a new subclause 3.6.3 called "Other algorithms of coexistence management", move this subclause under it and update the subsequent heading numbering accordingly. |  | O
24 | Mika Kasslin |  |  | Nokia | 5 | 5.1.1.2 | 41 | 32 | T |  | Can the registration from a CM to the CDIS fail and if so will the CE know it? | Please consider revising the figure or adding some more text to the paragraph before the figure about error case handling. |  | O
26 | Mika Kasslin |  |  | Nokia | 5 | 5.1.3.1 | 44 | 32 | T |  | This procedure should be performed only upon successful TVBD subscription procedure. | Clarify that the procedure is performed after a successful TVBD subscription procedure. |  | O
28 | Mika Kasslin |  |  | Nokia | 2 | 2.1 | 2 | 4 | T |  | Neighbor list definition missing | Define |  | O
29 | Mika Kasslin |  |  | Nokia | 2 | 2.1 | 2 | 4 | T |  | Neighbor report definition missing | Define |  | O
30 | Mika Kasslin |  |  | Nokia | 2 | 2.1 | 2 | 4 | T |  | Available channel list definition missing | Define |  | O
35 | Mika Kasslin |  |  | Nokia | 5 | 5.1.11.2 | 54 | 25 | T |  | This procedure applies only when the the reconfiguration applies to a TVBD served by another CM. This should be stated in the paragraph. | State that the procedure is applied only when the TVBD is served by another CM. |  | O
39 | Mika Kasslin |  |  | Nokia | 9 | 9.3.1 | 146 | 34 | T |  | There are no rules or procedures specified for decision making topology changes even though so claimed. They are needed in order to have interoperability. | Specify the rules and procedures. |  | O
42 | Mika Kasslin |  |  | Nokia | 3 | 3.2 | 4 | 11 | T |  | How is it ensured that a CM becomes aware of all the neighboring TVBDs that are using services of the coexistence system regardless of the CDIS instance the CM uses? I believe the specification should provide such a guarantee but can't do that at the moment. So, some further work is needed and the proposal is to define a new entity that is available for CDISs and provides means for the CDISs to find out neighbors registered to other CDISs. | Please consider adding a new entity to the system architecture with a logical interface to CDIS. |  | O
43 | Mika Kasslin |  |  | Nokia | 9 | 9.5.2 | 183 | 19 | T |  | Neighbor detection algorithm should not be based on statistical analysis as described in the current draft. For more information see Nokia contributions on the issue. We should have one mechanism only that doesn't require any "simulations" on fly but it should build upon analysis of simulation results. | Please replace the current algorithm description with the one provided as a separate submission. |  | O
44 | Mika Kasslin |  |  | Nokia | 2 | 2.1 | 2 | 4 | T |  | Definition of coexistence protocol data unit is missing | Define |  | O
45 | Mika Kasslin |  |  | Nokia | 4 | 4.2.2.2.3 | 21 | 41 | T |  | It is unclear what is the response after which the CE generates the primitive. It would be better to use the same statement as with the GetAuthInfo.confirm primitive description. | Replace the sentence with the following: "This primitive is generated by the CE after an attempt to subscribe to the coexistence system." |  | O
46 | Mika Kasslin |  |  | Nokia | 4 | 4.2.2.1.1 | 19 | 31 | T |  | Why there is nothing about the receiving side of the primitive? I'm used to having descriptions for both the transmitting side and the receiving side. They could be defined in separate subclauses. Now it is left open what is expected to happen in the receiving side. This comment applies throughout this clause dealing with the MEDIA_SAP. | Consider describing actions in both the transmitting side and the receiving side. |  | O
50 | Mika Kasslin |  |  | Nokia | 2 | 2.1 | 2 | 4 | T |  | Definition of mis-located TVBD is missing | Define |  | O
53 | Mika Kasslin |  |  | Nokia | 9 | 9.4.5 | 171 | 9 | T |  | This should be split into pieces since the description covers multiple issues and not only decision making algorithm. This subclause provides a good description of master/slave selection and that text should be moved to the corresponding new subclause if created. | Please consider moving a lot of the text especially on the master CM selection to a new clause addressing that issue specifically. |  | O
54 | Mika Kasslin |  |  | Nokia | 9 | 9.4.2 | 153 | 32 | T |  | I believe we should apply the following rule in all the decision algorithm descriptions: Information gathering doesn't belong to decision making but we should assume that to be a separate process that happens in the CM to support the decision making. In the decision making algorithm descriptions we should focus on processing of the information and decisions made based on the processed information. In my mind the description is currently too much implementation oriented. | Please consider a complete rewrite |  | O
57 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.1 | 173 | 18 | T |  | This is one of the potential algorithms and functions of a coexistence system. We shouldn't mandate this as it is now by stating that "...coexistence system shall support..." | Replace "shall" with "may" |  | O
69 | Mika Kasslin |  |  | Nokia | 9 | 9.4.7.1 | 178 | 44 | T |  | This paragraph seems to deal with a decision making algorithm while this clause describes channel classification and channel set transition. | Delete the paragraph |  | O
70 | Mika Kasslin |  |  | Nokia | 9 | 9.4.7.1 | 178 | 25 | T |  | I believe channel classification is unique for each CE / TVBD and if that is correct I would recommend us to make that clear in the introduction. Now it is a bit unclear what is the scope of classification in term of TVBDs. | Please clarify that classification is unique for CE |  | O
76 | Reinhard Gloger |  |  | NSN |  |  | 5 | 16 | T |  | What is a coex. Message? | clarify/define |  | O
77 | Reinhard Gloger |  |  | NSN |  |  |  | 45 | T |  | "store" doesn`t describe function | use "management" of reg. Info |  | O
81 | Reinhard Gloger |  |  | NSN |  |  | 146 | 34 | T |  | rules&procedures - where defined? |  |  | O
82 | Reinhard Gloger |  |  | NSN |  |  | 181 | 53 | T |  | CMS - what does it mean? | CM Server/system?! |  | O
83 | Reinhard Gloger |  |  | NSN |  |  | 183 | 19 | T |  | does this require "simulation"? | should be an alternative solution, which is more efficient |  | O
86 | Jari Junell |  |  | Nokia | 4 | 3.2. | 35-40 | all | T |  | Which parameters are mandatory, optional or exclusive? This is not consistently done. | Specify |  | O
88 | Jari Junell |  |  | Nokia | 5 | 3 | 77-82 | all | T |  | Which parameters are mandatory, optional or exclusive? This is not consistently done | Specify |  | O
90 | Jari Junell |  |  | Nokia | 9 | 3.1. | 146 | 12 | T |  | What is the relationship of different topologies in the same area? How do they interoperate? | Please clarify relationships |  | O
91 | Jari Junell |  |  | Nokia | 9 | 3.1. | 146 | 24 | T |  | If at least 2 CMs are calculating resources to at least one common TVBD network, how this conflict situation is handled in distributed topology? | Specify conflict handling algorithm |  | O
93 | Jari Junell |  |  | Nokia | 9 | 4.1.1. | 147 | 17 | T |  | Is somewhere decision making algorithm 1? | Please clarify? |  | O
124 | Junyi Wang |  |  | NICT | 3 | 3.2 | 4 | 33 | T | NO | interface A is missing | revise the figure | Principal, resolve as comment 110 | O
125 | Junyi Wang |  |  | NICT | 3 | 3.2 | 4 | 37 | T | NO | In figure 1, TVBD or TVBD network is not compliant to the contex | change the term to TVBD or TVBD network anywhere in the text |  | O
126 | Junyi Wang |  |  | NICT | 3 | 3.5.2 | 8 | 37 | T | NO | Remove "and " since a TVBD network or device can only subscribes either information service or management service | As indicated, also modify the next sentence to be as follows:a TVBD or TVBD network can dynamically switch between information service and management service, but is subscribed to only one service at a given time |  | O
128 | Junyi Wang |  |  | NICT | 3 | 3.6.2.4 |  |  | T | NO | CM negotiation protocol and algorithzm need to be defined. |  |  | O
129 | Junyi Wang |  |  | NICT | 4 |  |  |  | T | NO | It is not clear which primitives are corresponding to which messages, and the payloads of primitives are not 100% compliant to the the payload of the messages. |  |  | O
130 | Junyi Wang |  |  | NICT | 4 | 4.2.2 | 17 | 43 | T | NO | The term "information service" here is the difference concept of the information servcie defined in chapter 3. | Use different name for the information service here, e.g., data service |  | O
131 | Junyi Wang |  |  | NICT | 4 | 4.2.2 | 19 | 13 | T | NO | ResourceReconfiguration shall be in reconfiguration service? | change from measurement service to reconfiguration service |  | O
134 | Junyi Wang |  |  | NICT | 4 | 4.2.2.6.2 | 33 | 10 | T | NO | A TVBD network or device cannot perform partial reconfiguration, remove "failedParameters" does not provide enoough information for CM to make a reasonable new decision, instead the reason of failure shall be given | as indicated |  | O
136 | Junyi Wang |  |  | NICT | 4 | 4.3 | 39 | 11 | T | NO | BER can not be measured | change to FER |  | O
137 | Junyi Wang |  |  | NICT | 9 | 9.5 | 184 | 15 | T | NO | All parameters in Figure 195 shall be removed. |  |  | O
139 | Junyi Wang |  |  | NICT | 9 | 9.1 | 145 | 17 | T | No | Indicate that implementation of all management algorithms are not mandatory. | Indicate that" Implementation of all algorithms are nor mandatory. |  | O
167 | Donghun Lee |  |  | ETRI | General | General |  |  | T |  | Some announcement messages have a confirm messages, but other announcement messages have not. | Keep consistent |  | O
212 | Hyunduk Kang |  |  | ETRI | 7 | 7.2.1.1.2 | 110 | 25 | T |  | Why CM shall send a NeighorInformation_Announcement message to all CMs that serve a neighbor TVBD network or device? | Add more detailed explanation on this. |  | O
218 | Padam Kafle |  |  | Nokia | 2.1 |  | 2 | 5 | T |  | Adding definition for TVBD and TVBDN (TVBD networks) is recommended. Also, using abbreviation TVBDN throughout the draft may be useful. | As per the comment. |  | O
222 | Padam Kafle |  |  | Nokia | 3 | 3.3.1 | 5 | 16 | T |  | Without any definition of terms or expalnation in earlier part of the draft, it is very hard to interpret the functions of these logical entities. For example, what is a coexistence message? | Specify what's meant with a coexistence message |  | O
223 | Padam Kafle |  |  | Nokia | 3 | 3.3.2 | 5 | 20 | T |  | This subclasue lists the main functions for CM, but it contains many functions that are not necessarily needed in all the CMs. The list appears to include all possible features someone may imagine. it is recommended to only include basic functions mandatory for CM. | Please clarify |  | O
224 | Padam Kafle |  |  | Nokia | 3 |  | 12 | 51 | T |  | The system description clause doesn't provide details on different decision making topologies and their implications to CMs. Since this is one of the most important aspects of the whole system, recommend to provide details here with overview on different topologies in the system description clause. | Please include a new clause that provides an introduction to different decision making topologies. |  | O
225 | Padam Kafle |  |  | Nokia | 9 | 9.3.1 | 146 | 36 | T |  | The description about how CMs that apply different decision making topologies intearct with each other when they serve neighbors is completely missing. For example, how a master CM can take into account a network that is a neighbor of a network it serves but that is served by a CM that applies distributed decision making? | Specify such rules and provide corresponding description in a suclause within claues 9.3.1. |  | O
226 | Padam Kafle |  |  | Nokia | 5 | 5.1 | 41 | 4 | T |  | The details provided here in this clause looks like skeleton, without any clue what these procedures are required, or actually what information is being passed. For example, it is not clear how a TVBD network can be authenticated? For a TVBD itself, there can be some credentials the device might be able to send to CE. It can not be understood how a network generates such information. | Include sufficient details or clarify. |  | O
227 | Padam Kafle |  |  | Nokia | 5 | 5.2.5 | 64 | 41 | T |  | In Table 48, the parameters for available channel request contain country specific content such as DeviceFCCID. Since the procedures from 802.19.1 are supposed to be applicable to multiple regualtory domains, recommend using generic parameter structure that then can have country-sepcific values. | Use general name for paramters like "DeviceID" and allow multiple formats for different regualtory domains. |  | O
233 | Bonghoe Kim |  |  | LGE | 4.2.2.4.3 |  |  |  | T |  | what's the major difference between NeighborReport.response and NeighborReport.indication? Are these two required separately? | Assume NeighborReport.indication is used when a CE has neighbor report to send whereas NeighborReport.response is used when a CE has received NeighborReport.request, it would be needed to describe the difference. |  | O
2 | Mika Kasslin |  |  | Nokia | 3 | 3.2 | 4 | 42 | E |  | Spell out the CE (and all the other abbreviations/acronyms like CM and CDIS) when appearing first time. | Spell out abbreviations/acronym. |  | A |  | Gilb | A
7 | Mika Kasslin |  |  | Nokia | 3 | 3.3.2 | 5 | 39 | E |  | The sentence doesn't read very well. I have a bit hard time to udnerstand whether I should do load balancing during decision making or whether I should balance decision makig processing load. | Please clarify. |  | A |  | Gilb | A
9 | Mika Kasslin |  |  | Nokia | 3 | 3.3.3 | 5 | 45 | E |  | Storing information doesn't sound like a main function. | Delete the line or rewrite it |  | A |  | Gilb
11 | Mika Kasslin |  |  | Nokia | 3 | 3.4.1 | 6 | 11 | E |  | What does "information required for coexistence" contain? How is it different from the other information listed here? Are they not needed for coexistence? | Delete the line |  | A |  | Gilb
13 | Mika Kasslin |  |  | Nokia | 3 | 3.4.2 | 6 | 35 | E |  | What does "information required for coexistence" contain? How is it different from the other information listed here? Are they not needed for coexistence? | Delete the line |  | A |  | Gilb
17 | Mika Kasslin |  |  | Nokia | 3 | 3.5.2 | 8 | 48 | E |  | The sentence doesn't read very well. | Replace it with the following, as an example: "The measurement reports may be used by the coexistence system to make coexistence decisions." |  | A |  | Gilb
18 | Mika Kasslin |  |  | Nokia | 3 | 3.5.3 | 9 | 3 | E |  | The second sentence should be extended to have requirements about authentication like in the previous subclause on services to TVBDs. | Extend the sentence with the following: "...once it has successfully authenticated to the CDIS and subscribed to a coexistence service." |  | A |  | Gilb
19 | Mika Kasslin |  |  | Nokia | 3 | 3.6.2.1 | 9 | 30 | E |  | Algorithm name doesn't make sense since I believe all the algorithms use the neighbor and radio environment information. Let's come up with a more descriptive name. Actually there is not too much sense in many other algorithm titles either. I would challenge the group to consider labeling the algorithms simply as "Algorithm 1", "Algorithm 2", etc. | Rename the algorithm and revise the heading accordingly. |  | A |  | Gilb
21 | Mika Kasslin |  |  | Nokia | 9 | 9.4.7 | 178 | 18 | E |  | This subclause doesn't belong under coexistence decision making algorithms but needs to be brought further up in the hierarchy. | Make the subclause to be 9.5 and update the dependent subclauses accordingly. |  | A |  | Gilb
25 | Mika Kasslin |  |  | Nokia | 5 | 5.1.2.4 | 42 | 53 | E |  | Reference to the figure missing. | Fix and refer to figure 15 |  | A |  | Gilb
27 | Mika Kasslin |  |  | Nokia | 5 | 5.1.4.4 | 46 | 29 | E |  | Reference to the figure missing. | Fix and refer to figure 22. |  | A |  | Gilb
31 | Mika Kasslin |  |  | Nokia | 4 | 4.2.2.4.9 | 29 | 43 | E |  | This should be an indication primitive instead | Update the heading accordingly |  | A |  | Gilb
34 | Mika Kasslin |  |  | Nokia | 5 | 5.1.11.2 | 54 | 24 | E |  | Reference to the figure missing. | Fix and refer to figure 43. |  | A |  | Gilb
36 | Mika Kasslin |  |  | Nokia | 9 | 9.1 | 145 | 9 | E |  | Phrase "This mechanism is specified in" is to be deleted. | Delete the phrase |  | A |  | Gilb
37 | Mika Kasslin |  |  | Nokia | 9 | 9.1 | 145 | 12 | E |  | Wrong clause reference at the end of the paragraph. | Refer to 9.5 instead of 7.3 |  | A |  | Gilb
38 | Mika Kasslin |  |  | Nokia | 9 | 9.1 | 145 | 17 | E |  | Wrong clause reference at the end of the paragraph. | Refer to 9.6 instead of 7.4 |  | A |  | Gilb
48 | Mika Kasslin |  |  | Nokia | 4 | 4.2.2.5.3 | 32 | 3 | E |  | Wrong heading type and numering | Fix it |  | A |  | Gilb
58 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.2 | 173 | 33 | E |  | Could is not a proper verb here. | Replace "could be" with "is" |  | A |  | Gilb
59 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.2 | 173 | 47 | E |  | DTT is not spelled out or specified | Spell it out and specify |  | A |  | Gilb
64 | Mika Kasslin |  |  | Nokia | 9 | 9.4.6.5.2 | 176 | 38 | E |  | Incorrect clause reference since there is no annex. | Please fix |  | A |  | Gilb
68 | Mika Kasslin |  |  | Nokia | 9 | 9.4.4 | 166 | 4 | E |  | Looks like "3" is a typo in the heading | Please fix and delete "3" |  | A |  | Gilb
72 | Mika Kasslin |  |  | Nokia | 9 | 9.4.1.1 | 147 | 14 | E |  | Replace "comments" with "commands" | Replace "comments" with "commands" |  | A |  | Gilb
73 | Reinhard Gloger |  |  | NSN |  |  | 2 | 13 | E |  | Spelling error televison, a.o. | correct words |  | A |  | Gilb
74 | Reinhard Gloger |  |  | NSN |  |  |  | 16 | E |  |  |  |  | A |  | Gilb
75 | Reinhard Gloger |  |  | NSN |  |  |  | 34 | E |  |  |  |  | A |  | Gilb
78 | Reinhard Gloger |  |  | NSN |  |  | 46 | 29 | E |  | illustrated in ….(missing) | add Fig. Number |  | A |  | Gilb
79 | Reinhard Gloger |  |  | NSN |  |  | 145 | 12 | E |  | wrong reference (7.3) | correct reference |  | A |  | Gilb
80 | Reinhard Gloger |  |  | NSN |  |  | 146 | 16 | E |  | spelling error aut… | correct "autonomous" |  | A |  | Gilb
85 | Jari Junell |  |  | Nokia | 4 | 2.2.3.3 | 24 | 16 | E |  | ACS has wrong description | ACS is adjacent channel selectivity of a receiver |  | A |  | Gilb
87 | Jari Junell |  |  | Nokia | 5 | 2.3.1. | 59 | 11 | E |  | CE_Reistration_Request | CE_Registration_Request |  | A |  | Gilb
89 | Jari Junell |  |  | Nokia | 9 | 1 | 145 | 9 | E |  | Sentence not understandable: "This mechanism..." | Please clarify the sentence |  | A |  | Gilb
92 | Jari Junell |  |  | Nokia | 9 | 4 | 147 |  | E |  | Within this chapter group algorithms based on topology and name them more anonymously | Please regroup and rename |  | A |  | Gilb
95 | Naotaka Sato |  |  | Sony Corporation |  |  | iii, v, vii, ix, xi, xiii, | Header | E |  | "WIRELESS MAC AND PHY SPECIFICATIONS FOR LR-WPANS" is not for P802.19.1. | Change to "TV WHITE SPACE COEXISTNCE METHODS". |  | A |  | Gilb
96 | Naotaka Sato |  |  | Sony Corporation |  |  | iv, vi, viii, x, xii,xiv | Header | E |  | "LOCAL AND METROPOLITAN AREA NETWORKS-PART 15.4" is not for P802.19.1. | Change to "TV WHITE SPACE COEXISTNCE METHODS". |  | A |  | Gilb
97 | Naotaka Sato |  |  | Sony Corporation |  |  | ix, x, xi, xii,xiii, xiv | Header | E |  | "Draft P802.14.4REVi/D09, April, 2011" is not for this document. | Change to "Draft P802.19.1/DF0, August, 2011". |  | A |  | Gilb
98 | Naotaka Sato |  |  | Sony Corporation |  |  | v | 22 | E |  | "P802.15" has to be "P802.19". | Change to "P802.19". |  | A |  | Gilb
99 | Naotaka Sato |  |  | Sony Corporation |  |  | v | 27 | E |  | Secretary name is wrong. | Change to "Junyi Wang". |  | A |  | Gilb
100 | Naotaka Sato |  |  | Sony Corporation |  |  | vii | 45 | E |  | Not approve yet. | Use the original template. |  | A |  | Gilb
101 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.1 | 145 | 12 | E |  | The mechanism is not specified in 7.3 but 9.5. | Change to "9.5". |  | A |  | Gilb
102 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.1 | 145 | 17 | E |  | The TVBD network or device mesurements are not discribed in 7.4, but 9.6. | Change to "9.6". |  | A |  | Gilb
103 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.3.3.2 | 147 | 1 | E |  | Typo | Remove "1" between "the" and "management". |  | A |  | Gilb
104 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.4.4 | 166 | 4 | E |  | Typo | Remove "3" between "geometry" and "classification". |  | A |  | Gilb
105 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.4.4.3 | 168 | 47 | E |  | Typo | Remove "1" between "Algorithm" and "description". |  | A |  | Gilb
106 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.4.4.3 | 169 | 21 | E |  | Typo | Remove "1" between "for" and "the". |  | A |  | Gilb
107 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.4.4.3 | 169 | 30 | E |  | Procedures show in chapter 5 now. | Change from "chapter 6" to "chapter 5". |  | A |  | Gilb
108 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.4.4.3 | 169 | 37 | E |  | Typo | Change from " co21 channel" to "co-channel". |  | A |  | Gilb
109 | Naotaka Sato |  |  | Sony Corporation | 9 | 9.4.6.5.2 | 176 | 38 | E |  | There is no "A.1" in this document. | Change from "Annex A.1" to "9.4.6.2". |  | A |  | Gilb
112 | Stanislav Filin |  |  | NICT | 4 | All | All |  | E |  | Some table headings include "primitive parameters" like Table 2 and some table heading do not include these words like Table 4. | Use consistent manner for table headings in clause 4. |  | A |  | Gilb
118 | Stanislav Filin |  |  | NICT | 5 | 5.2 | All |  | E |  | Table heading are inconsistent, e.g., Table 49 uses "message format", Table 50 and many other tables use "message payload", Tables 52 and 52 have none of these words. | Use consistent manner for table headings in subclause 5.2. |  | A |  | Gilb
133 | Junyi Wang |  |  | NICT | 4 |  | 32 | 3 | E | NO | 5.2.2.1.10.3 shall be 4.2.2.5.3 | as indicated |  | A |  | Gilb
135 | Junyi Wang |  |  | NICT |  |  |  |  | E | NO | Combined all data type specifications and put them into normative annex. |  |  | A |  | Gilb
138 | Junyi Wang |  |  | NICT | 9 | 9.1 | 145 | 12 | E | No | Check the references in the section. '7.3' should be '9.3' | Check all refrences. |  | A |  | Gilb
140 | Junyi Wang |  |  | NICT | 9 | 9.4.1.2 | 152 | 7 | E | No | Change "no channel 1" to "no channel". | As indicated. |  | A |  | Gilb
141 | Junyi Wang |  |  | NICT | 9 | 9.5.22 | 184 | 47 | E | No | Change " network Bare " to "network B are" | As indicated. |  | A |  | Gilb
142 | Junyi Wang |  |  | NICT | 9 | 9.5.2.2 | 185 | 7 | E | No | Change " are 1 assumed " to "are assumed" | As indicated. |  | A |  | Gilb
143 | Junyi Wang |  |  | NICT | Introduction | Participants | v | 22 | E | No | Change "802.15" to "802.19" | As indicated. |  | A |  | Gilb
144 | Junyi Wang |  |  | NICT | Introduction | Participants | v | 27 | E | No | State that "Junyi Wang is the secretary of the group | As indicated. |  | A |  | Gilb
145 | Junyi Wang |  |  | NICT | Introduction | Participants | v | 27 | E | No | State that "Mika Kasslin is the vice chair of the group | As indicated. |  | A |  | Gilb
146 | Junyi Wang |  |  | NICT | 3 | 3.51 | 7 | 7 | E | No | Change " ntroduction " to "Introduction" | As indicated. |  | A |  | Gilb
147 | Junyi Wang |  |  | NICT | 3 | 3.51 | 7 | 7 | E | No | Change " Coexistence decision algorithms " to "Coexistence decision making algorithms" | As indicated. |  | A |  | Gilb
148 | Ryo Sawai |  |  | Sony corporation | 3 | 3.5.1 | 7 | 44 | E |  | "3.5.1 ntroduction" seems to be a typo. | Change it to "3.5.1 Introduction", accordingly |  | A |  | Gilb
149 | Ryo Sawai |  |  | Sony corporation | 3 | 3.6.2.6 | 12 | 22 | E |  | There is no space between "classification" and "algorithm" | Modify it, accordingly |  | A |  | Gilb
150 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4 | 166 | 4 | E |  | In "9.4.4. ... geometry 3 classification ...", "3" seems to be a typo. | Remove the "3" in this sentence |  | A |  | Gilb
151 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.2 | 166 | 38 | E |  | In "Figure 185..", "." seems to be a typo. | Remove the "." in this sentence |  | A |  | Gilb
152 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.2 | 168 | 3--12 | E |  | "If the acceptable interference ... Class #3b(2)." is unclear | Change it to "If the acceptable interference level for each network is defined using its own network requirement such as the required SINR at the edge point of the expected network coverage and the value is larger than the value of the aggregated interference power from the other network, these networks will be able to share the channel each other. On the other hand, if the value is smaller than the value of the aggregated interference power from the other network, these networks may be uable to share the channel each other. In this case, if the resource sharing and the synchronized operation are possible via backhaul connection,these networks may be able to share the channel each other in accordance with the required guranteed QoS in conducting the coexistence management via the backhaul. On the other hand, if the resource sharing and the synchronized operation is impossible via backhaul connection in this case because of its capability and latency problem and so on, these networks will be uable to share the channel each other." |  | A |  | Gilb
153 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.2 | 168 | 35 | E |  | In "... as shown in Efigure 188.", "E" of "Efigure" seems to be a typo. | Remove the "E" in this sentence |  | A |  | Gilb
155 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.3 | 168 | 47 | E |  | In "9.4.4.3. Algorithm 1 description", "1" seems to be a typo. | Remove the "1" in this sentence |  | A |  | Gilb
156 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.3 | 169 | 21 | E |  | "(DS#2) ... allocation for 1 the" seems to be a typo. | Change it to "allocation for the.", accordingly |  | A |  | Gilb
157 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.3 | 169 | 36 | E |  | "Network Technology and addNetworkTechnology" seems to be a typo. | Change it to "Network Technology.", accordingly |  | A |  | Gilb
158 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.3 | 169 | 37 | E |  | "(P#2)... not co21 channel ..." seems to be a typo. | Change it to "not co-channel.", accordingly |  | A |  | Gilb
159 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.3 | 169 | 49 | E |  | "(P#4) ... There will be ... TVBD network." will not be necessary here. | Remove this sentence. |  | A |  | Gilb
160 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.4.3 | 170 | 45--48 | E |  | Bullet sign of (BC#2) is missing | Change it to "not co-channel.", accordingly |  | A |  | Gilb
161 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.6.2 | 173 | 31--49 | E |  | The section 9.4.6.2 will not be necessary here. | Remove the section 9.4.6.2. |  | A |  | Gilb
163 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.6.5.2 | 176 | 1 | E |  | Definition of SM in Table 82 is missing | Include the definition of SM should be included in the Table 82 as follows: "Parameter" -> SM, "Input/Output/Estimated values in CM" -> Estimated value in CM, and "Notes" -> Safety margin which shall be set for the (shadow) fading margin in considering the path loss. |  | A |  | Gilb
164 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.6.5.2 | 176 | 1 | E |  | Some notation of parameters in Table 82 does not fit to the notation of parameters in equations in section 9.4.6.5.1. | Replace it to the revised text in "Table82.docx". |  | A |  | Gilb
165 | Ryo Sawai |  |  | Sony corporation | 9 | 9.4.6.5.2 | 176 | 26-33 | E |  | Parameters M, N and O in Table 82 are not being used in the equations in section 9.4.6.5.1. | The definision of these parameters should be removed from Table 82 in section 9.4.6.5.1. Instead, these parameters shold be noted in section 9.4.6.5.2 |  | A |  | Gilb
166 | Donghun Lee |  |  | ETRI | General | General |  |  | E |  | Figures in clause 6,7,8 is broken | Black circle of figures might be redrawed in clause 6,7,8. |  | A |  | Gilb
168 | Donghun Lee |  |  | ETRI | 5 | 5.2.6.3 | 66 | 36 | E |  | The message name of 'CE_ChannelClassification_Request' in message subclause is different from its procedure. | The message name of 'CE_ChannelClassification_Request' might be changed into 'ChannelClassification_Request' in message subclause. |  | A |  | Gilb
169 | Donghun Lee |  |  | ETRI | 5 | 5.2.6.4 | 66 | 52 | E |  | The message name of 'CE_ChannelClassification_Response' in message subclause is different from its procedure. | The message name of 'CE_ChannelClassification_Response' might be changed into 'ChannelClassification_Response' in message subclause. |  | A |  | Gilb
170 | Donghun Lee |  |  | ETRI | 5 | 5.2.6.4 | 67 | 5 | E |  | The message name of 'CE_ChannelClassification_Response' in Table 54 is different from its procedure. | The message name of 'CE_ChannelClassification_Response' might be changed into 'ChannelClassification_Response' in message subclause. |  | A |  | Gilb
171 | Donghun Lee |  |  | ETRI | 5 | 5.2.6.5 | 67 | 20 | E |  | The text of 'The destinationIdentifier =CM_ID or CE_ID' might be wrong. | The text of 'The destinationIdentifier =CM_ID or CE_ID' might be changed into 'the destinationIdentifier shall be set to CM_ID or CE_ID. |  | A |  | Gilb
172 | Donghun Lee |  |  | ETRI | 5 | 5.3 | 77 | 40 | E |  | Missing mode I type. | It might include mode I type. |  | A |  | Gilb
173 | Donghun Lee |  |  | ETRI | 6 | 6.2.1 | 85 | 22 | E |  | Bullets of the text 'Primitives from the TVBD network or device' and 'NewRegInfo.indication' are the same. | Bullets of the text 'Primitives from the TVBD network or device' might be different from 'NewRegInfo.indication'. |  | A |  | Gilb
174 | Donghun Lee |  |  | ETRI | 6 | 6.2.1 | 85 | 30 | E |  | Bullets of the text 'Messages from the CM' and 'NeighborReport_Announcement' are the same. | Bullets of the text 'Messages from the CM' might be different from 'NeighborReport_Announcement'. |  | A |  | Gilb
175 | Donghun Lee |  |  | ETRI | 6 | 6.2.2 | 92 | 28 | E |  | Bullets of the text 'Primitives from the TVBD network or device' and 'NewRegInfo.indication' are the same. | Bullets of the text 'Primitives from the TVBD network or device' might be different from 'NewRegInfo.indication'. |  | A |  | Gilb
176 | Donghun Lee |  |  | ETRI | 6 | 6.2.1 | 92 | 43 | E |  | Bullets of the text 'Messages from the CM' and 'AvailableChannels_Request' are the same. | Bullets of the text 'Messages from the CM' might be different from 'AvailableChannels_Request'. |  | A |  | Gilb
177 | Hyunduk Kang |  |  | ETRI | 3 | 3.2 | 4 |  | E |  | Figure 1 is broken. | Fix the figure. |  | A |  | Gilb
178 | Hyunduk Kang |  |  | ETRI | 4 | 4.1 | 13 |  | E |  | Figure 4 is broken. | Fix the figure. |  | A |  | Gilb
179 | Hyunduk Kang |  |  | ETRI | 4 | 4.1 | 13 |  | E |  | Figure 5 is broken. | Fix the figure. |  | A |  | Gilb
180 | Hyunduk Kang |  |  | ETRI | 4 | 4.1 | 14 |  | E |  | Figure 6 is broken. | Fix the figure. |  | A |  | Gilb
181 | Hyunduk Kang |  |  | ETRI | 4 | 4.1 | 15 |  | E |  | Figure 7 is broken. | Fix the figure. |  | A |  | Gilb
182 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1 | 86 |  | E |  | Figure 49 is broken. | Fix the figure. |  | A |  | Gilb
183 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.1.1 | 86 |  | E |  | Figure 50 is broken. | Fix the figure. |  | A |  | Gilb
184 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.1.2 | 87 |  | E |  | Figure 51 is broken. | Fix the figure. |  | A |  | Gilb
185 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.1.3 | 87 |  | E |  | Figure 52 is broken. | Fix the figure. |  | A |  | Gilb
186 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.1.4 | 88 |  | E |  | Figure 53 is broken. | Fix the figure. |  | A |  | Gilb
187 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.1.5 | 88 |  | E |  | Figure 54 is broken. | Fix the figure. |  | A |  | Gilb
188 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.2.1 | 89 |  | E |  | Figure 56 is broken. | Fix the figure. |  | A |  | Gilb
189 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.2.2 | 89 |  | E |  | Figure 57 is broken. | Fix the figure. |  | A |  | Gilb
190 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.2.3 | 90 |  | E |  | Figure 58 is broken. | Fix the figure. |  | A |  | Gilb
191 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.2.4 | 90 |  | E |  | Figure 59 is broken. | Fix the figure. |  | A |  | Gilb
192 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.2.5 | 90 |  | E |  | Figure 60 is broken. | Fix the figure. |  | A |  | Gilb
193 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.1.2.6 | 91 |  | E |  | Figure 61 is broken. | Fix the figure. |  | A |  | Gilb
194 | Hyunduk Kang |  |  | ETRI | 6 | 6.2.2 | 93 |  | E |  | Figure 65 is broken. | Fix the figure. |  | A |  | Gilb
195 | Hyunduk Kang |  |  | ETRI | 7 | 7.2.1.1 | 108 |  | E |  | Figure 93 is broken. | Fix the figure. |  | A |  | Gilb
196 | Hyunduk Kang |  |  | ETRI | 7 | 7.2.3 | 128 |  | E |  | Figure 137 is broken. | Fix the figure. |  | A |  | Gilb
197 | Hyunduk Kang |  |  | ETRI | 8 | 8.1 | 140 |  | E |  | Figure 162 is broken. | Fix the figure. |  | A |  | Gilb
198 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.1.1 | 148 |  | E |  | Figure 173 is broken. | Fix the figure. |  | A |  | Gilb
199 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.2 | 154 |  | E |  | Figure 175 is broken. | Fix the figure. |  | A |  | Gilb
200 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.2 | 155 |  | E |  | Figure 176 is broken. | Fix the figure. |  | A |  | Gilb
201 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.2 | 156 |  | E |  | Figure 177 is broken. | Fix the figure. |  | A |  | Gilb
202 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.2 | 157 |  | E |  | Figure 178 is broken. | Fix the figure. |  | A |  | Gilb
203 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.2 | 158 |  | E |  | Figure 179 is broken. | Fix the figure. |  | A |  | Gilb
204 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.3 | 159 |  | E |  | Figure 180 is broken. | Fix the figure. |  | A |  | Gilb
205 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.4.2 | 167 |  | E |  | Figure 185 is broken. | Fix the figure. |  | A |  | Gilb
206 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.4.2 | 167 |  | E |  | Figure 186 is broken. | Fix the figure. |  | A |  | Gilb
207 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.4.2 | 168 |  | E |  | Figure 187 is broken. | Fix the figure. |  | A |  | Gilb
208 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.4.2 | 169 |  | E |  | Figure 188 is broken. | Fix the figure. |  | A |  | Gilb
209 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.4.3 | 170 |  | E |  | Figure 189 is broken. | Fix the figure. |  | A |  | Gilb
210 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.5.2 | 190 |  | E |  | Figure 190 is broken. | Fix the figure. |  | A |  | Gilb
211 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.7.2 | 181 | 43 | E |  | typo | Delete " ' " in front of "Un-configuration" |  | A |  | Gilb
213 | Hyunduk Kang |  |  | ETRI | 7 | 7.2.3.1.9 | 132 | 31 | E |  | typo | Delete "v" |  | A |  | Gilb
214 | Hyunduk Kang |  |  | ETRI | 2 | 2.2 | 2 | 34 | E |  | typo | Correct "telvision" to "television" |  | A |  | Gilb
215 | Hyunduk Kang |  |  | ETRI | 9 | 9.4.4.2 | 168 | 35 | E |  | typo | Fix "EFigure 188" to "Figure 188" |  | A |  | Gilb
216 | Hyunduk Kang |  |  | ETRI | 4 | 4.2.2.4.9 | 29 | 44 | E |  | typo | Fix "ChannelClassification.request" to "ChannelClassification.announcement" |  | A |  | Gilb
217 | Hyunduk Kang |  |  | ETRI | 6.7.8 |  |  |  | E |  | Chapter 6, 7, and 8 describe entities operation which are interconnected each other. It looks better if they are all in one chapter. | Combine Chapter 6, 7, and 8 together |  | A |  | Gilb
219 | Padam Kafle |  |  | Nokia | 2.1 |  | 2 | 6 | E |  | The draft contains too many spelling and other editorial errors that should be fixed, such as "teleision", "telvision" etc for television. Through editorial review is recommended. | Fix them. |  | A |  | Gilb
220 | Padam Kafle |  |  | Nokia | 2.2 |  | 2 | 34 | E |  | I believe "Television White Spaces" is more commonly used instead of "… Space" for abbreviation "TVWS" . | As per the comment. |  | A |  | Gilb
221 | Padam Kafle |  |  | Nokia | 3.6.2 | 3.6.2.1 | 9 | 36-37 | E |  | In "neighbors of neighbors of the selected TVBD networks…", "neighbors" is repeated. | remove the duplicate. |  | A |  | Gilb
228 | Bonghoe Kim |  |  | LGE | General |  |  |  | E |  | Figures are broken (in particular, figs in ch6,7,and 8) | fix the figures |  | A |  | Gilb
229 | Bonghoe Kim |  |  | LGE | General |  |  |  | E |  | In terms of readability, it would be better to combine ch6, 7 and 8 into one chapter | Combine ch6,7 and 8. |  | A |  | Gilb
230 | Bonghoe Kim |  |  | LGE | 3.5.1 |  |  |  | E |  | typo | change to Introduction |  | A |  | Gilb
231 | Bonghoe Kim |  |  | LGE | 2.1 |  |  |  | E |  | Add definition of "TVBD networks" |  |  | A |  | Gilb
232 | Bonghoe Kim |  |  | LGE | 4.2.2.4.1 |  |  |  | E |  | typo in primitive | change from "NeighborReport.indication" to "NeighborReport.request" |  | A |  | Gilb
234 | Bonghoe Kim |  |  | LGE | 4.2.2.4.9 |  |  |  | E |  | wrong section title | change "ChannelClassification.request" to "ChannelClassification.announcemnet" |  | A |  | Gilb
235 | Bonghoe Kim |  |  | LGE | 5.2.2.1 |  |  |  | E |  | This message is also used in subscription update (5.1.2.2) | add description "This message is used for initial subscription as well as updating subscription" |  | A |  | Gilb
236 | Bonghoe Kim |  |  | LGE | 5.2.2.1.10.3 |  |  |  | E |  | wrong section number and inconsistent style |  |  | A |  | Gilb
237 | Bonghoe Kim |  |  | LGE | 5.1.2.4 |  |  |  | E |  | missing a reference to figure | add "Figure 15" following "illustrated in" |  | A |  | Gilb
238 | Bonghoe Kim |  |  | LGE | 5.1.10.1 |  |  |  | E |  | missing a reference to figure | add "Figure 38" following "illustrated in" |  | A |  | Gilb
240 | Bonghoe Kim |  |  | LGE | 6.2.2.1.11 |  |  |  | E |  | typo in figure 76 | change from "Send Reconfguration_Reponse to CM" to "Send Reconfiguration_Request to CM" |  | A |  | Gilb
241 | Bonghoe Kim |  |  | LGE | 6.2.2.11 |  |  |  | E |  | typo in figure 87 | change from "ResourceReconfiguration.request" to "ResourceReconfiguration.response" |  | A |  | Gilb
242 | Bonghoe Kim |  |  | LGE | 7.2.1.1.6 |  |  |  | E |  | type in figure 99 | change from "Send Deautentication_Response" to "Send Registration_Response" |  | A |  | Gilb
244 | Bonghoe Kim |  |  | LGE | 9.4.1.2 |  |  |  | E |  | a few arrows in Figure 173 are drawn in wrong direction | Fix the figure |  | A |  | Gilb
Note on A1: An integer, starting with 1, incrementing by one.
Note on E1: Affiliation of the voter
Note on J1: Enter T for technical, E for editorial
Note on N1: Do not make entries, to be filled out in comment resolution
Note on O1: Do not make entries, to be filled out in comment resolution
Note on P1: Do not make entries, to be filled out in comment resolution

## Status
Technical comments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 35 | 85.37%
Closed | C | 6 | 14.63%
Written | W | 0 | 0%
Total |  | 41
Editorial comments |  |  | Percent complete
Open | O | 0 | 0%
Assigned | A | 2 | 100%
Closed | C | 0 | 0%
Written | W | 0 | 0%
Total |  | 2
Total # comments |  |  | Percent complete
Open | O | 59 | 24.18%
Assigned | A | 179 | 73.36%
Closed | C | 6 | 2.459%
Written | W | 0 | 0%
Total |  | 244
Initial tally
Technical | T | 101
Editorial | E | 143
Total |  | 244

## Commenter summary
Commenter name | # comments | Vote | Affiliation | File name | 1st CID | Last CID
Mika Kasslin | 71 |  | Nokia | TGR1-KASSLIN-MIKA.xls | 1 | 71
Reinhard Gloger | 12 |  | NSN | 80219_TGR1_Comments-GLOGER-REINHARD.xls | 72 | 83
Jari Junell | 11 |  | Nokia | TGR1_JUNELL_JARI.xls | 84 | 94
Naotaka Sato | 15 |  | Sony | 80219_TGR1_Comments_Sato_final.xls | 95 | 109
Stanislav Filin | 14 |  | NICT | 80219_TGR1_Comments_SFilin.xls | 110 | 123
Junyi Wang | 24 |  | NICT | 80219_TGR1_Comments-wang-submit.xls | 124 | 147
Ryo Sawai | 18 |  | Sony | 80219_TGR1_Comments_Sawai.xls | 148 | 165
Donghun Lee | 11 |  | ETRI | 80219_TGR1_Comments.xls | 166 | 176
Hyunduk Kang | 41 |  | ETRI | 80219_TGR1_Comments_Hyunduk_Kang.xls | 177 | 217
Padam Kafle | 10 |  | Nokia | TGR1-KAFLE-PADAM.xls | 218 | 227
Bonghoe Kim | 17 |  | LGE | 80219_TGR1_Comments (LGE) Final.xlsx | 228 | 244
Total # comments | 244
Total # commenters | 0
Total # approve | 0
Total # disapprove | 0