## Title
2011-11-01 |  | IEEE P802.19.1-11/125r07
IEEE P802.19.1
Project | IEEE P802.19.1
Title | P802.19.1 Task Group Review 2 Comments List
Date Submitted | January, 2012
Source | Tuncer Baykas | Voice:
| NICT | Fax: [ ]
E-mail: tbaykas@ieee.org
Re:
Abstract
Purpose | This document provides contains the commets and resolutions for Task Group Review 2.
Notice | This document has been prepared to assist the IEEE P802.19.1. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Revision 0 | Initial List of comments received during the task group review 2
Revision 1 | CID numbers and tracking tools are added
Revision 2 | Categories are added.
Revision 3 | Updated accroding to comment resolutions during Atlanta meeting
Revision 4 | Updated according to comment resolutions received until Jacksonville meeting (Monday)
Revision 5 | Updated according to comment resolutions received until Jacksonville meeting Monday PM2 time slot
Revision 6 | Updated according to comment resolutions received until Jacksonville meeting until Thursday AM1
Revision 7 | Updated according to comment resolutions received during Jacksonville meeting

## Comments
CID: | Commenter | Affiliation | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Response | Status | Category | AssignedTo | Discussion Day | Time Slot | E Status | T Status | G Status
1 | Stanislav Filin | NICT | T | 35 | 4.3.1 | 25 | COEX_TR_SAP data types are not defined accroding to ASN.1 rules | See contribution 802.19-11/121r0 | Resolve as indicated in 121r0 | C | Data type |  |  |  |  | C
2 | Stanislav Filin | NICT | T | 35 | 4.3.2 | 35 | COEX_MEDIA_SAP data types are not defined according to ASN.1 rules | See contribution 802.19-11/122r0 | Resolve as indicated in 122r2 | C | Data type |  |  |  |  | C
3 | Stanislav Filin | NICT | T | 77 | 5.4 | 4 | Coexistence protocol data types are not defined according to ASN.1 rules | See contribution 802.19-11/123r0 | Resolved with the approval of 12/12r1 | C | Data types |  |  | Tuesday AM1 |  | C
4 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 12 | neighbor was not considered as a good term, e.g. a coexistence set or coexistence list may be better terms - proposed that CDIS forms list, and CM set for a coexistence system user. | Modify: coexistence discovery and information server: An entity that is responsible for determining a coexistence list for a coexistence system user and providing it for the coexistence manager (CM) of the coexistence system user. The entity also supports the discovery of CMs by other CMs in order to open interfaces between them. |  | O | Terminology | [5 empty] | O
5 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 16 | coexistence system user would be more generic term than TVBD network or device. | Modify: coexistence enabler: An entity that enables communication between a coexistence system user and a coexistence manager that serves the coexistence system user. | Resolved with the approval of 12/27r1 | C | Terminology | [5 empty] | C
6 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 19 | neighbor was not considered as a good term, e.g. a coexistence set or coexistence list may be better terms - proposed that CDIS forms list, and CM set for a coexistence system user. | Modify: coexistence manager: An entity that is responsible for making coexistence decisions related to reconfiguration of coexistence system users to enhance the coexistence within a coexistence set. (Decision making includes determining the coexistence set for the coexistence system user based on the coexistence list.) | Resolved with the approval of 12/27r1 | C | Terminology | [5 empty] | C
7 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 22 | coexistence system user would be more generic term than TVBD network or device. | Modify: coexistence services: Services provided by the coexistence system to coexistence system users, as well as services provided by the entities of the coexistence system to other entities of the coexistence system. | Resolved with the approval of 12/27r1 | C | Terminology | [5 empty] | C
8 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 25 | coexistence system user would be more generic term than TVBD network or device. | Add: coexistence system user: A TVBD which uses the coexistence services of the coexistence system. | Resolved with the approval of 12/27r1 | C | Terminology | [5 empty] | C
9 | Paivi Ruuska | Nokia | G |  |  |  | A term for possible interference relations provided by CDIS. | Add: coexistence list: The list coexistence system users which CDIS has calculated to cause interference in the same geo-location area with a coexistence system user. |  | O | Discovery Algorithm | [5 empty] | O
10 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 25 | A term for interference relations, replaces neighbors. | Add: coexistence set: The coexistence system users which CM has categorized to be interference sources, interference victims or both for a coexistence system user. (The coexistence set is a subset of coexistence system users from the coexistence list.) | Resolved with the approval of 12/27r1 | C | Terminology | [5 empty] | C
11 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 25 | A term for interference relations, replaces a neighbor. | Add: coexistence set member: A coexistence system user which belongs to the coexistence set. It is interference source, interference target or both for another coexistence system user. | Resolved with the approval of 12/27r1 | C | Terminology | [5 empty] | C
12 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 25 | A term for interference relations needed | Add interference source: A coexistence system user that CM is evaluated to be able to cause interference to another coexistence system user. |  | O | Terminology | [5 empty] | O
13 | Paivi Ruuska | Nokia | G | 2 | 2.1 | 25 | A term for interference relations needed | Add:interference target: A coexistence system user that CM is evaluated to potentially be interfered by another coexistence system user. |  | O | Terminology | [5 empty] | O
14 | Paivi Ruuska | Nokia | E | 4 | 3.2 | 36 | Change TVBD or TVBD network | Replace TVBD or TVBD network with Coexistence system user | Resolved with a motion. New Term is WSO (White Space Object). | C | Terminology |  |  |  | C
15 | Paivi Ruuska | Nokia | E | 4 | 3.2 | 30 | In figure, the lower coexistence manager should be coexistence enabler. | Fix figure according the comment |  | O |  |  |  |  | O
16 | Paivi Ruuska | Nokia | E | 4 | 3.2 | 41 | Coexistence system user would be clearer term to be used instead of TVBD network or device throughout the document. This comment applies to whole draft related to using TVBD network or device. | Replace: television band device (TVBD) network and device and TVBD network and device with coexistence system user | Resolved with a motion. New Term is WSO (White Space Object). | C |  |  |  |  | C
17 | Paivi Ruuska | Nokia | E | 4 | 3.2 | 50 | Use new terms and modify. | Replace first sentence with: The CDIS is responsible for calculating a coexistence list for a coexistence system user and providing it for the coexistence manager (CM) of the coexistence system user. |  | O |  |  |  |  | O
18 | Paivi Ruuska | Nokia | G | 5 | 3.3.2 | 26, 27, 29, 31 36 & 38 | All these relate to coexistence decision making and management - group them better; perform channel classification, generating coexistence white space map (note that white space map not defined), make coexistence decisions related to TVBD network or device reconfiguration, request reconfiguration of the TVBD network or device according to the decisions, maintain information required for making coexistence decisions and provide this information to TVBD network or device as needed, AND perform TVBD network or device output power level management | Replace the bullets with: Coexistence decision making, including maintaining information on spectrum resource use status, managing the operating parameters for coexistence system users, and providing information on spectrum resource use status to coexistence system users. |  | O | Editorial Imp. | [5 empty] | O
19 | Paivi Ruuska | Nokia | G | 5 | 3.3.2 | 28 | calculate intra-CM neighbor TVBD networks or devices. Note that CM calculates coexistence set (=all CM evaluated neighbors), and CDIS calculates coexistence list (either inter/intra). CM may not request coexistence list from CDIS for intra-CM users. CM can include intra-users to coexistence set without having received them from the list. | Replace with: Calculate coexistence set for coexistence system users. |  | O | Terminology | [5 empty] | O
20 | Paivi Ruuska | Nokia | G | 5 | 3.3.2 | 32 | Define available channel information or modify in a way that can be understood to be incumbent/primary free, i.e. available for all secondary users. | Replace: Obtain information of channels where TVBDs are allowed to operate from TVWS database directly or via coexistence system users. / Or define in definitions: available channel = channel that is not user by primary or incument user. / channel that is available for TVBD operation. |  | O | Terminology | [5 empty] | O
21 | Paivi Ruuska | Nokia | G | 5 | 3.3.2 | 34&39 | Selecting master CM and balancing processing load seem to relate - combine them. Note that this is also on CDIS section (row 49). Should it be either in CDIS or CM or both. | Combine and modify: select the master CM to support balancing the processing load required to make coexistence decisions |  | O | Master CM S. | [5 empty] | O
22 | Paivi Ruuska | Nokia | E | 5 | 3.3.3 | 46 | calculate neighbor TVBD networks or devices for inter-CM and intra-CM, | Replace with: Calculate coexistence list for coexistence system users for inter-CM and intra-CM use. |  | O |  |  |  |  | O
23 | Paivi Ruuska | Nokia | G | 5 | 3.3.3 | 51 | I think geometry classification relates to calculating the coexistence list. Consider combining these bullets. Also clarify what geometry classification means. | Define geometry classification, and possibly add this in the bullet in row 46. |  | O | Terminology | [5 empty] | O
24 | Paivi Ruuska | Nokia | E | 6 | 3.4.1 | 13 | neighbor was not considered as a good term. | Replace with: coexistence set requests |  | O |  |  |  |  | O
25 | Paivi Ruuska | Nokia | G | 6 | 3.4.1 | 16 | Event request does not tell anything to reader if not explained already in this phase. | Delete event request, or define better. |  | O | Editorial Imp. | [5 empty] | O
26 | Paivi Ruuska | Nokia | E | 6 | 3.4.1 | 21 | neighbor was not seen as good term. What does radio information mean here? Coexistence set should include neighbors and also some information of them, e.g. radio technology. If radio information refers to radio environment, that should be in channel classification? | Replace with coexistence set. |  | O |  |  |  |  | O
27 | Paivi Ruuska | Nokia | E | 6 | 3.4.2 | 37 | neighbor was not considered as a good term. | Replace with: coexistence set requests |  | O |  |  |  |  | O
28 | Paivi Ruuska | Nokia | G | 6 | 3.4.2 | 39 | Event request does not tell anything to reader if not explained already in this phase. | Delete event request, or define better. |  | O | Editorial Imp. | [5 empty] | O
29 | Paivi Ruuska | Nokia | E | 6 | 3.4.2 | 44 | neighbor was not seen as good term. What does radio information mean here? Coexistence set should include neighbors and also some information of them, e.g. radio technology. If radio information refers to radio environment, that should be in channel classification? | Replace with coexistence set. |  | O |  |  |  |  | O
30 | Paivi Ruuska | Nokia | E | 7 | 3.4.3 | 1 | Neighbor was not seen as good term. CDIS gives coexistence list, including the "neighbors" evaluated by CDIS | Replace with coexistence list requests. |  | O |  |  |  |  | O
31 | Paivi Ruuska | Nokia | E | 7 | 3.4.3 | 7 | Neighbor was not seen as good term. CDIS gives coexistence list, including the proposed "neighbors" evaluated by CDIS. | Replace with coexistence list. |  | O |  |  |  |  | O
32 | Paivi Ruuska | Nokia | G | 7 | 3.4.3 | 14 | Information required for coexistence is too generic - all information should be shared because of this purpose. | Replace with: information of the same coexistence set members, including resource allocations, capabilities, and characteristics of the coexistence system user. |  | O | Editorial Imp. | [5 empty] | O
33 | Paivi Ruuska | Nokia | G | 7 | 3.4.3 | 19 | CM negotiation messages is too generic. And there is no actual negotiation among all CMs, only information exchange. Real negotiation may occur only between CMs which use the same algorithm to manage TVBDs belonging to same coexistence set. | Replace with: Decision making algorithm specific negotiation and information messages. |  | O | Editorial Imp. | [5 empty] | O
34 | Paivi Ruuska | Nokia | T | 157- | 9.4.3 | all | From the algorithms I focused on this deciosion making algorithm and tried to understand it. It seems that it mostly describes a protocol among CMs which use this algorithm, but does not explain how the CMs decice the parameters they negotiate. How to decide the parameters would be big part of the decision making algorithm in a CM. | Separate contribution with modifications and questions planned to be submitted for the meeting. |  | O | Decision Making Algorithms |  |  |  |  | O
35 | Mika Kasslin | Nokia | G |  |  |  | What is the way a CDIS becomes aware of those TVBD newtorks or devices that are not registered to it but that should be considered in the neighbor discovery? | Modify the CDIS as per a submission about discovery system. |  | O | Discovery Algorithm | [5 empty] | O
36 | Mika Kasslin | Nokia | E | 4 | 3.2 | 28-29 | The Coexistence Enabler entity box has become a Coexistence Manager | Change back to Coexistence Enabler | Accept | C |  |  |  |  | C
37 | Mika Kasslin | Nokia | G |  |  |  | How to ensure that a Coexistence Manager receives required information from a TVBD network or device that it needs for its algorithm on coexistence decisions? Currently the design assumes the parameters to be provided in the TVBD registration but many of them are optional. This relates also to a question what are the requirements of a CM in terms of coexistence decision algorithm support. If it is possible to have only one algorithm implemented, how to ensure that the CM gets all the data it needs from the TVBD network or device? |  |  | O | Decision Making Algorithms | [5 empty] | O
38 | Mika Kasslin | Nokia | G |  |  |  | It is not clear what are the requirements on interconnections and interactions between CMs. | Adopt text in a submission on CM interconnections and interactions into the candidate draft. |  | O | CM to CM communication | [5 empty] | O
39 | Mika Kasslin | Nokia | G |  |  |  | It is not clear what is mandatory in each entity to be compliant with the specification. | Have a PICS added to the draft and specify there mandatory and optional features. | Resolved with the approval of 12/27r1 | C | PICS | [5 empty] | C
40 | Bonghoe Kim | LG | T | 8 | 3.5.3 |  | It is not clear whether CM can have both information and management serviced TVBD networks and devices. Moreover, the functionality that each service provides is not clearly stated. | Add "functionality per each service" ; add necessary procedures and messages to support both information and management services by a CM at one time |  | O | Editorial Imp. |  |  |  |  | O
41 | Bonghoe Kim | LG | T | 41 | 5.2.1.1 |  | Add some more information how authentication works | Add the following after the first sentence: "NOTE- It is recommended that each TVBD network or device has a dedicated CE serving it. Authentication uses ID/password pairs to log on to CM (by a CE) or CDIS (by a CM). ID/password distribution is out of the scope of this specification. " |  | O | Editorial Imp. |  |  |  |  | O
42 | Bonghoe Kim | LG | T | 41 | 5.2.1.2 |  | Not clear how deauthentication and de-registration works (or de-registrationw orks) | Add the following after the first sentence: Deauthentication procedure includes both deauthentication and de-registration. Once CM receives Deauthentication_Request from a CE, it initiates de-registration process to remove the registration information from CDIS. Change “CM_Registration_Request” to “CM_DeRegistration_Request”. Change “CM_Registration_Response” to CM_DeRegistration_Response”. |  | O | Editorial Imp. |  |  |  |  | O
43 | Bonghoe Kim | LG | T | 56 | 5.3 |  | Messages are missing a few important fields such as packet type, etc | Revise message format (5.3) to be completed |  | O | Message Format |  |  |  |  | O
44 | Bonghoe Kim | LG | T | 185 | 9.5.3 |  | The subclause needs to be filled. | add master CM selection algorithm |  | O | Discovery Algorithm |  |  |  |  | O
45 | Hyunduk Kang | ETRI | E | 17 | 4.2.2 | 42 | Typo "exchane" | Replace "exchane" to "exchange" | Accept | C |  |  |  |  | C
46 | Hyunduk Kang | ETRI | E | 187 | A.1 | 43 | Figure A.1 is broken. | Fix it. |  | O |  |  |  |  | O
47 | Hyunduk Kang | ETRI | T | 10 | 3.6.2.1 | 10 | I would like to know the phrase, "The neighbors of the immediate neighbors", is revised based on which CID in the 1st comments. I do not understand its meaning. | Declare the corresponding CID and explain why this revision has been made. Back to the original sentence. TG discussion is required if this revision is needed. | Resolve as indicated in 145r0 | C | Editorial Imp. |  |  |  |  | C
48 | Hyunduk Kang | ETRI | T | 8 | 3.5.3 | 48 | I would like to know the phrase, "The measurement reports ", is revised based on which CID in the 1st comments. I think it different from the original sentence. The information and measurement results are supposed to be used for coexistence decision making | Declare the corresponding CID and explain why this revision has been made. Back to the original sentence. TG discussion is required if this revision is needed. | Resolve as indicated in 145r0 | C | Editorial Imp. |  |  |  |  | C
49 | Hyunduk Kang | ETRI | T | 41 | 5 | 4 | Tile of clause 5 is not supposed to be changed. We had have the motion for it during Okinawa meeting. | Restore to the original title of clause 5, "Procedures and protocols" | Resolve as indicated in 145r0 | C | Editorial Imp. |  |  |  |  | C
50 | Hyunduk Kang | ETRI | T | 41 | 5.1 | 9~11 | The paragraph "This clauses ~ the CDIS" is needed to be revise to introduce clause 5 more appropriately. | Revise the paragraph. | Resolve as indicated in 137r0 | C | Editorial Imp. |  |  |  |  | C
51 | Hyunduk Kang | ETRI | T | 9 | 3.5.4 | 36 | The meaning of Intra-CM neighbor and inter-CM neighbor need to be explained | Add definitions of Intra-CM neighbor and inter-CM neighbor on sub-clause 2.1 | Withdrawn by commenter | C | Editorial Imp. |  |  |  |  | W
52 | Hyunduk Kang | ETRI | T | 42 | 5.2.2 |  | It is difficult to how the coexistence service subscription procedures works with the current description. More explanation will be helpful to understand. | Revise the paragraph. | Resolve as indicated in 138r0 | C | Editorial Imp. |  |  |  |  | C
53 | Hyunduk Kang | ETRI | T | 45 | 5.2.4 |  | It is difficult to how the obtaining neighbor information procedures works with the current description. More explanation will be helpful to understand. | Revise the paragraph. | Resolve as indicated in 139r0 | C | Editorial Imp. |  |  |  |  | C
54 | Hyunduk Kang | ETRI | T | 48 | 5.2.6 |  | It is difficult to how the channel classification information procedures works with simple description. More explanation will be helpful to understand. | Revise the paragraph. | Resolve as indicated in 140r0 | C | Editorial Imp. |  |  |  |  | C
55 | Hyunduk Kang | ETRI | T | 50 | 5.2.7 |  | It is difficult to how the obtaining information procedures works with the current description. More explanation will be helpful to understand. | Revise the paragraph. | Withdrawn by commenter | C | Editorial Imp. |  |  |  |  | C
56 | Hyunduk Kang | ETRI | T | 51 | 5.2.8 |  | It is difficult to how the requesting and obtaining measurement procedures works with simple description. More explanation will be helpful to understand. | Revise the paragraph. | Withdrawn by commenter | C | Editorial Imp. |  |  |  |  | C
57 | Hyunduk Kang | ETRI | T | 51 | 5.2.9 |  | It is difficult to how the negotiation between CMs procedures works with simple description. More explanation will be helpful to understand. | Revise the paragraph. | Withdrawn by commenter | C | Editorial Imp. |  |  |  |  | C
58 | Hyunduk Kang | ETRI | T | 55 | 5.2.12 |  | It is difficult to how the sending event indication procedures works with simple description. More explanation will be helpful to understand. | Revise the paragraph. | Withdrawn by commenter | C | Editorial Imp. |  |  |  |  | C
59 | Hyunduk Kang | ETRI | T | 187 | A.1 |  | More use cases is needed to explain how each procedures is interconnected each other based on various use cases. | Add more use cases. | Resolved with 12/25r1 | C | Editorial Imp. |  |  | Wednesday PM1 |  | C
60 | Hyunduk Kang | ETRI | T | 190 | 9.7 |  | All sub-clauses are TBD. It should have normative text to cover each type of measurement. | Add normative text. |  | O | Measurement |  |  |  |  | O
61 | Hyunduk Kang | ETRI | T | 2 | 2.1 |  | There is no definition of interference which is important concept of the standard. | Add definitions. | Withdrawn by commenter | C | Terminology |  |  |  |  | C
62 | Hyunduk Kang | ETRI | T | 2 | 2.1 |  | There is no definition of neighbor which is important concept of the standard. | Add definitions. | Withdrawn by commenter | C | Terminology |  |  |  |  | C
63 | Hyunduk Kang | ETRI | T | 2 | 2.1 |  | There is no definition of coexistence which is important concept of the standard. | Add definitions. | Withdrawn by commenter | C | Terminology |  |  |  |  | C
64 | Donghun Lee | ETRI | E | ix,xi,xiii |  | 1 | The term, " WIRELESS MAC AND PHY SPECIFICATION FOR LR-WPANS", is wrong | The term might be " TV WHITESPCE COEXISTENCE METHOD" | Accept | C |  |  |  |  | C
65 | Donghun Lee | ETRI | E | x |  | 1 | The term, " LOCAL AND METROPOLITAN AREA NETWORK-PART 15.4" is wrong | The term might be " LOCAL AND METROPOLITAN AREA NETWORK-PART 19.1" | Accept | C |  |  |  |  | C
66 | Donghun Lee | ETRI | E | xii,xiv |  | 1 | The term, "WIRELESS MAC AND PHY SPECIFICATION FOR LR-WPANS" is wrong | The term might be " LOCAL AND METROPOLITAN AREA NETWORK-PART 19.1" | Accept | C |  |  |  |  | C
67 | Donghun Lee | ETRI | E | x,xii,xiv |  | 1 | The term, "WIRELESS MAC AND PHY SPECIFICATION FOR LR-WPANS" is wrong | The term might be " LOCAL AND METROPOLITAN AREA NETWORK-PART 19.1" | Accept | C |  |  |  |  | C
68 | Donghun Lee | ETRI | T | x |  | 10 | The sub-title of section 5 is wrong | The sub-title of section 5 might be "Procedures and protocols" | Resolve as indicated in 145r0 | C | Editorial Imp. |  |  |  |  | C
69 | Donghun Lee | ETRI | E | 17 | 4.2.2 | 42 | The term, " exchane" is wrong | The term might be " exchange" | Accept | C |  |  |  |  | C
70 | Donghun Lee | ETRI | E | 26 | 4.2.2.4 | 26 | The term, " exchane" is wrong | The term might be " exchange" | Accept | C |  |  |  |  | C
71 | Donghun Lee | ETRI | E | 49 | 5.2.6.4 | 29 | The dot at ChannelClassification.indication primitive is missing in Fig 30 | The primitive in Fig 30 might be "ChannelClassificaiton.indication" | Accept | C |  |  |  |  | C
72 | Donghun Lee | ETRI | T | 51 | 5.2.9 | 45 | Description of negotiation between CMs procedure is not enough | Additional description of the negotiation procedure is necessary | Withdrawn by commenter | C | Editorial Imp. |  |  |  |  | C
73 | Donghun Lee | ETRI | T | 68 | 5.3.7.1 | 5 | CE ID of TVBD network or device is missing in InfoAcquiring_Request message payload when CM is sent it to another CM | CE ID of TVBD network of device might be added in InfoAcquiring_Request message payload as an optional parameter | Resolve as indicated in 141r0 | C | CM to CM communication |  |  |  |  | C
74 | Donghun Lee | ETRI | T | 68 | 5.3.7.2 | 20 | CE ID of TVBD network or device is missing in InfoAcquiring_Response message when CM is sent it to another CM | CE ID of TVBD network of device might be added in InfoAcquiring_Response message payload as an optional parameter | Resolve as indicated in 141r0 | C | CM to CM communication |  |  |  |  | C
75 | Donghun Lee | ETRI | T | 80 | 5.4 | 8,18 | CM needs subscribed service information (i.e. information service or management service) of neighbor TVBD network of device which is registered to another CM | Data type of subscribed service of ReqInfoDescr and ReqInfoValue might be added in section 5.4 | Resolve as indicated in 142r0 | C | CM to CM communication |  |  |  |  | C
76 | Donghun Lee | ETRI | E | 83104 | 6,7 | 54 | The page number is wrong | It might be corrected | Accept | C |  |  |  |  | C
77 | Donghun Lee | ETRI | E |  | 6,7 |  | Some figures are duplicated | It should be corrected | Accept | C |  |  |  |  | C
78 | Naotaka Sato | Sony | E | 4 | 3.2 | 16 | Figure 1 doesn't have "Coexistence Enabler" | Change from "Coexsitence Manager" to "Coexsitence Enabler" between Interface B1 and Interface A. | Accept | C |  |  |  |  | C
79 | Naotaka Sato | Sony | T | 182 | 9.6.2.2 | 35 | Where 90% comes from? It seems there is one of example to choose 90% to get some simulation results. | There are no reason to use 90%, there should not be in nomative, remove this section 9.6.2.2 or move this section to informative annex. |  | O | Discovery Algorithm |  |  |  |  | O
80 | Naotaka Sato | Sony | T | 184 | 9.6.2.2 | 11 | Where 90% comes from? It seems there is one of example to choose 90% to get some simulation results. | There are no reason to use 90%, there should not be in nomative, remove this section 9.6.2.2 or move this section to informative annex. |  | O | Discovery Algorithm |  |  |  |  | O
81 | Naotaka Sato | Sony | T | 184 | 9.6.2.2 | 23 | It is not enough to calculate CDF for only 100 realizations. | There are no reason to use 100 realizations, there should not be in nomative, remove this section 9.6.2.2 or move this section to informative annex. |  | O | Discovery Algorithm |  |  |  |  | O
82 | Naotaka Sato | Sony | T | 184 | 9.6.2.2 | 23 | It is not enough to calculate CDF for only 100 realizations. | There are no reason to use 100 realizations, there should not be in nomative, remove or move this section 9.6.2.2 to informative annex. |  | O | Discovery Algorithm |  |  |  |  | O
83 | Naotaka Sato | Sony | T | 185 | 9.6.2.3 | 15 | Where 90% comes from? It seems there is one of example to choose 90% to get some simulation results. | There are no reason to use 90%, there should not be in nomative, remove this section 9.6.2.3 or move this section to informative annex |  | O | Discovery Algorithm |  |  |  |  | O
84 | Naotaka Sato | Sony | T | 185 | 9.6.2.3 | 23 | Where more than 100 realizations comes from? It seems there is example to choose more than 100 realizations. Shall provide reason to use more than 100 realizations. | There are no reason to use more than 100 realizations, there should not be in nomative, remove this section 9.6.2.2 or move this section to informative annex. |  | O | Discovery Algorithm |  |  |  |  | O
85 | Naotaka Sato | Sony | T | 185 | 9.6.2.3 | 26 | Where 90% potentical interference comes from? It seems there is one of example to choose 90% to get some simulation results. | There are no reason to use 90% potential interference, there should not be in nomative, remove this section 9.6.2.3 or move this section to informative annex. |  | O | Discovery Algorithm |  |  |  |  | O
86 | Naotaka Sato | Sony | T | 185 | 9.6.2.3 | 47 | What is the relationship with Prx and RSSI. Prx is simulation value, but RSSI is measurement value. There is no discription this relationship. | Shall provide the relationship with Prx and RSSI, remove this section 9.6.2.3, or move this section to informative annex. |  | O | Discovery Algorithm |  |  |  |  | O
87 | Naotaka Sato | Sony | T | 185 | 9.6.2.4 | 53 | "Interference direction" will be estimated from 90% interference level, how confidence this estimataion of "Interference direction". If the level of interference is provided by CDIS, CM or TVBD or TVBD network don't need to use "interference direction". | Shall provide confidence level of "intereference direction", or remove this section 9.6.2.4, page 61 line 21, page 62 line 11, page 62 line 41, page 63 line 40, page 78 line21 and page 78 line27. |  | O | Discovery Algorithm |  |  |  |  | O
88 | Junyi Wang | NICT | T | 20 | 4.2.2.1.3 | 39 | It is better to keep CM related information in the device. | Add parameters of Serverd ID of CM, Server Password of CM, IP address of CM Port number of CM and CMID to the parameters in GetAuthInfo.response | Resolve as indicated in 143r0 | C | [5 empty] | C
89 | Junyi Wang | NICT | T | 36 | 4.3.2 | 6 | Use only one method to indicate geolocation | Change parameters of CoordinateX,CoordinateY,Coordinate Z to lattitude longtitude and altitude |  | O | Reference Model |  |  | Tuesday PM2 |  | O
90 | Junyi Wang | NICT | T | 36 | 4.3.2 | 12 | Antennagain cannot be specified by one value | Change it to Maxantennagain or include antennapattern in the description | Resolve as indicated in 12/18r5 | C | Reference Model |  |  | Tuesday PM2 |  | C
91 | Junyi Wang | NICT | T | 44 | 5.2.2.5 | Fig 16 | Typo, "SubscriptionChange" | Change it to "ChangeSubscription" | Resolve as indicated in 143r0 | C | Editorial Imp. |  |  |  |  | C
92 | Junyi Wang | NICT | T | 41 | 5.2.1.2 | Fig 9 | Typo, "CM_Registration_Request " | Change it to "Registration_Request " | Resolve as indicated in 143r0 | C | Editorial Imp. |  |  |  |  | C
93 | Junyi Wang | NICT | E | 109 | 7.2.1.1 | 12 | Typo, "CM_Registration_Request " | Change it to "Registration_Request " | Accept | C |  |  |  |  | C
94 | Junyi Wang | NICT | E | 81 | 5.4 | 25,43 | Typo, "StartFeq" | Change it to "StartFreq " | Resolve as indicated in 143r0 | C |  |  |  |  | C
95 | Junyi Wang | NICT | T | 23 | 4.2.2.3.2 | 45 | At the moment CM needs to have device FCCID and deviceSN to obtain available channels for a Device. | Add parameters of deviceFCCID and deviceSN in getreginfor.response | Resolve as indicated in 143r0 | C | Reference Model |  |  |  |  | C
96 | Junyi Wang | NICT | T | 37 | 4.3.2 | 35 | "Expected load" should be clarified | Indicate that it is in Mbps | Resolve as indicated in 12/18r5 | C | Reference Model |  |  | Tuesday PM2 |  | C
97 | Junyi Wang | NICT | T | 36 | 4.3.2 | 27 | "Occupancy and total occupancy" should be clarified | Indicate that they show percentage of time operating in the channel | Resolve as indicated in 12/18r5 | C | Reference Model |  |  | Tuesday PM2 |  | C
98 | Junyi Wang | NICT | T | 37 | 4.3.2 | 32 | There is no indication of how long the channels are available. | Add availabilitystarttime and availibiltyduration to availablechannelist | Resolve as indicated in 12/18r5 | C | Reference Model |  |  | Tuesday PM2 |  | C
99 | Junyi Wang | NICT | E | 20 | 4.2.2.1.3 | 32 | Userid and userpassword mismatches with client id and client password | Change UserID to ClientID and userpassword to ClientPW | Resolve as indicated in 143r0 | C |  |  |  |  | C
100 | Junyi Wang | NICT | E | 56 | 5.3.1.2 | 35 | Typo "clientPassword" | Change it to ClientPW | Resolve as indicated in 143r0 | C |  |  |  |  | C
101 | Junyi Wang | NICT | E | 15 | 4.2.1.1 | 44 | transportPref shows Transport protocol type not the preference | Change it to transportType | Resolve as indicated in 143r0 | C |  |  |  |  | C
102 | Junyi Wang | NICT | E |  | general |  | Use spelling rules of American English, e.g. change all "neighbour" to "neighbor" |  | Resolve as indicated in 143r0 | C |  |  |  |  | C
103 | Junyi Wang | NICT | T | 61 | 5.3.4.1 | Table 43 | For a CM to communicate with other CM, the IP address and portnumber should be included in neighbor list | Add Neighbor list IP address of Cm and its port number | Resolve as indicated in 143r0 | C | CM to CM communication |  |  |  |  | C
104 | Junyi Wang | NICT | T | 77 | 5.4 | 13 | The option "add" for operationcode is not necessary | Remove "add" | Resolve as indicated in 143r0 | C | Editorial Imp. |  |  |  |  | C
105 | Ryo Sawai | Sony | E | 167-168 | 9.4.4.2 | 46--2 | Agreement in CID152 of task group review1 is not being reflected here. | Change it, according to the aggreement in CID 152 of task group review1. | Accept | C |  |  |  |  | C
106 | Ryo Sawai | Sony | E | 168 | 9.4.4.2 | 33--35 | Agreement in CID154 of task group review1 is not being reflected here. | Change it, according to the aggreement in CID 154 of task group review1. | Accept | C |  |  |  |  | C
107 | Ryo Sawai | Sony | E | 169 | 9.4.4.3 | 40-43 | Agreement in CID159 of task group review1 is not being reflected here. | Change it, according to the agreement in CID 159 of task group review1. | Accept | C |  |  |  |  | C
108 | Ryo Sawai | Sony | E | 177 | 9.4.6.4.2 | 26-36 | Agreement in CID162 of task group review1 is not being reflected precisely. | Change it, according to the agreement in CID 162 of task group review1. | Accept | C |  |  |  |  | C
109 | Ryo Sawai | Sony | E | 169 | 9.4.4.3 | 49 | "If the network geometry class is class#1/class#2/class#3, go to BC#2". The ".../class #3" is a typo. | Change "If the network geometry class is class#1/class#2/class#3 to "If the network geometry class is class#1/class#2/class#4, go to BC#2". | Accept | C |  |  |  |  | C
110 | Ryo Sawai | Sony | E | 168 | 9.4.4.2 | 3--22 | Index of the parameter (I_secondary) in Figure 187 is a typo. | Change the parameter (I_secondary) to the parameter (I_TVBD) in the figure 187, accordingly | Accept | C |  |  |  |  | C
111 | Ryo Sawai | Sony | E | 167 | 9.4.4.2 | 4 4 | The word "two" of the first sentence "… where two different TVBD network" in line 44 of page 167 is unnecessary. | Remove the word "two" in the first sentence in line 44 of page 167, accordingly | Accept | C |  |  |  |  | C
112 | Ryo Sawai | Sony | E | 169 | 9.4.4.3 | 31-35 | It may be necessary to add some example of the calculation method of potential aggregated interference power level in the step of "(P#3) Interference power level check process". | Insert the calculation example in the statement of the step of (P#3) of Section 9.4.4.3, if necessary. |  | O |  |  |  |  | O

## Status
Editorial comments |  |  | Percent complete
Open | O | 11 | 28.95%
Assigned | A | 0 | 0%
Closed | C | 27 | 71.05%
Total |  | 38
Technicalcomments |  |  | Percent complete
Open | O | 17 | 34%
Assigned | A | 0 | 0%
Closed | C | 33 | 66%
Total |  | 50
General comments |  |  | Percent complete
Open | O | 16 | 69.57%
Assigned | A | 0 | 0%
Closed | C | 7 | 30.43%
Total |  | 23
Total # comments |  |  | Percent complete
Open | O | 44 | 39.29%
Assigned | A | 0 | 0%
Closed | C | 68 | 60.71%
Total |  | 112
Initial tally
Technical | T | 54
Editorial | E | 35
General | G | 23
Total |  | 112

## Commenter Summary
Commenter name | # comments | Vote | Affiliation | 1st CID | Last CID
Stanislav Filin | 3 |  | NICT | 1 | 3
Paivi Ruuska | 31 |  | Nokia | 4 | 34
Mika Kasslin | 5 |  | Nokia | 35 | 39
Bonghoe Kim | 5 |  | LGE | 40 | 44
Hyunduk Kang | 19 |  | ETRI | 45 | 63
Donghun LEE | 14 |  | ETRI | 64 | 77
Naotako Sato | 11 |  | Sony | 78 | 88
Junyi Wang | 16 |  | NICT | 89 | 104
Ryo Sawai | 8 |  | Sony | 105 | 112
112