## Slide 1: 802.19 TG 1 May Session Closing Report
Notice: This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Author:

## Slide 2: Abstract
This document is prepared to summarize activities of 802.19 TG1 during May 2012 meeting

## Slide 3
Goals for May meeting
Review of the draft.
Comment resolution.
Contributions.

## Slide 4
Letter Ballot
Letter ballot failed
  Yes 17
  No 15
  Abstain 2
273 Comments received
  185 Technical comments
  5 General comments
  83 Editorial comments

## Slide 5
Comment Resolution Progress
273 Comments received
  158 Resolved
185 Technical comments
  101 resolved
5 General Comments
  3 resolved
83 Editorial Comments
  54 resolved
Motion to approve resolutions stated in IEEE 802.19-12/58r0
  By Mika Kasslin
  Seconded by Stanislav Filin
    Motion passed with unanimous consent

## Slide 6
Cognitive Testbed Contribution
Mika Kasslin presented Radio system coexistence in a cognitive radio testbed 802.19-12/21r0.

## Slide 7
Teleconferences before July Session
May 30 2012
June 6 2012
June 20 2012
June 27 2012
July 4 2012
July 11 2012
All teleconferences will be at 1:00 AM Eastern Time for the duration of 2 Hours

## Slide 8
Goals for July Session
Finalizing comment resolution
Forwarding draft standard to WG for letter ballot.

## Slide 9: Timeline
 | 2010 |  |  |  |  |  | 2011 |  |  |  |  |  | 2012 |  |  |  |  |  | 2013 |  |  |  |  | 
 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11
Task Group formed | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
System Design Document completed |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Call for Proposals issued |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Contribution presentations with straw polls |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Proposal presentations |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Round of votes on proposals in clause order |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Create candidate draft document |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment ballot on the candidate draft |  |  |  |  |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  | 
Comment resolutions on the candidate draft |  |  |  |  |  |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  | 
Adoption of draft normative text |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  | 
Letter ballot Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  | 
Letter Ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  | 
Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |