## Slide 1: TG1 Closing Report for January 2013
Notice: This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Date: 2013-01-17
Authors:

## Slide 2: Abstract
This is TG1 closing report from January 2013 interim meeting in Vancouver, BC, Canada

## Slide 3: Agenda and Results
The TG focused on comment resolutions with 110 technical and 9 general comments open
The TG heard several contributions related to the comments and many of them were accepted as comment resolutions
  56 technical comments resolved
This leaves the TG with 63 technical and general comments open
Draft meeting minutes available in 19-13/0016r3
Approved comment resolutions available in 19-12/0204r7

## Slide 4: Teleconferences
The TG will have teleconferences before the March 2013 plenary on the week of March 18 as follows
  January 30, 2013, 01:00-02:00 AM EST
  February 13, 2013, 01:00-02:00 AM EST
  February 20, 2013, 01:00-02:00 AM EST
  February 27, 2013, 01:00-02:00 AM EST
  March 13, 2013, 01:00-02:00 AM EST
In the agenda we’ll have at least the following topics
  Profile dependent entity operations
  Profile indpendent CM-CM communication
  Coexistence discovery, CDIS description
  Messages and data types

## Slide 5: March 2013 Plenary Objectives
Continue comment resolutions and resolve all the remaining comments
  After this meeting we have still 63 technical and general comments open
Have the draft prepared for a recirculation WG LB after the March 2013 meeting so that the ballot closes before the May 2013 interim
Decide on whether the 802.19.1 draft is ready to be made available for IETF PAWS

## Slide 6: Targeted TG1 Timeline
Second Working Group Letter Ballot: October 2012
Recirculation Letter Ballot: March 2013
Recirculation Letter Ballot: July 2013
Form Sponsor Ballot Pool: July 2013
Initial Sponsor Ballot: November 2013
Recirculation Sponsor Ballot: March 2014
Final WG/EC Approval: July 2014
RevCom/Standards Board Approval: September 2014