## Slide 1: TG1 Opening Report for May 2013
Notice: This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Date: 2013-05-13
Authors:

## Slide 2: Current Status
A WG LB 1st re-circulation on DF3.03 was hold from late April until early May
  Approval rate: 72% (Approves: 23, Disapproves: 9)
Now the TG has 82 comments to resolve
  General comments: 1
  Editorial comments: 22
  Technical comments: 59

## Slide 3: This week
This week is dedicated to comment resolutions
  Comments and resolutions are available in file 19-12/0057r0
  The TG needs to address and resolve each comment
  The result of LB 1st re-circulation is not determined yet
TG1 agenda can be found in 19-13/0058r0
Let’s start comment review and discussion per topic and based on contributions
Let’s try to close every single comment

## Slide 4: Tentative TG1 Timeline
Second Working Group Letter Ballot: October 2012
Recirculation Letter Ballot: March 2013
Recirculation Letter Ballot: July 2013
Form Sponsor Ballot Pool: July 2013
Initial Sponsor Ballot: November 2013
Recirculation Sponsor Ballot: March 2014
Final WG/EC Approval: July 2014
RevCom/Standards Board Approval: September 2014