## Slide 1: TG1 Opening Report for September 2013
Notice: This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Date: 2013-09-16
Authors:

## Slide 2: 2nd WG Letter Ballot Recurculation Results
Votes
  25 Yes votes (+2)
  7 No votes (-2)
  78% approval rate
Comments
  101 technical comments
  1 general comment
  28 editorial comments

## Slide 3: Results of the Teleconferneces
TG1 had 3 teleconferences
  August 21
  August 28
  September 4
Results
  Technical comments
    11 comments are left open for discussion in F2F
    59 comments are assigned
    31 comments are closed (subject to approval in F2F)
  General comment
    1 comment is assigned

## Slide 4: Plans for the F2F
Resolve all comments
Ask WG Chair to start recirculation

## Slide 5: Intended Timeline
2012 October: Second WG Letter Ballot
2013 April: 1st Recirculation
2013 August: 2nd Recirculation
2013 October: 3rd Recirculation
November 2013: Sponsor Ballot
2014 March: 1st Recirculation
2014 July: Final WG and IEEE 802 EC Approval
2014 September: RevCom/Standards Board Approval
2014 October: Publication