## Title Page
2013-11-13 |  | IEEE P802.19.1-13/0139r0
IEEE P802.19.1
Project | IEEE P802.19.1
Title | Comments associated with No votes
Date Submitted | 2013
Spurce | Stanislav Filin | Voice:
| NICT | Fax: [ ]
E-mail: sfilin@nict.go.jp
Abstract
Purpose | This document contains comments and related resolutions for outstanding No votes.
Notice | This document has been prepared to assist the IEEE P802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.

## Comments
CID | Name | Vote (Y/N/A) | Comment | Category | Page Number | Subclause | Line Number | Proposed Change | Must Be Satisfied | Response
| Ivan Reede | N | To change my vote from Disapprove to Approve, include a behavioural model of the coexistence conflict resolution process in the form of algorithms or procdeures or flow charts or state diagrams or other with accompnaying text and provide demonstration via simulation that a standards compliant coexistence system converges toward a stable resolution who's outcome (although it may not be perfect and always converge) demonstrates that coexistence of transceivers/networks implementing such is significantly improved and that such networks do not abdict to other devices not implementing the coexistence standard... i.e. the reason for which one would want to comply rather than not comply. | Technical | iv | 1 | 1 | The difference between the AmeriSys proposal and the current draft makes that I cannot envision a converging solution at this time with the defined protocols and algorithms. Therefore, I expect that when a converging proposal is made, many protocoland algorithm alterations may be required to make a coexistence system that demonstrably improves the coexistnce situation of devices implementing the standard in comparison to devices not implementing the standard. I therefore leave the resolution of this comment and the required changes open to the proponents of the proposed protocols in the task group for lack of technical expertise in the use of what is propsed in the draft. | 1 | Accept in principle More work is needed
| Jari Junell | N | Section 7 is broken. | Technical |  |  |  | Update section to match with the content of other sections. | 1 | Accept in principle Modify the draft as described in 19-13/0046r1, 19-13/0024r2 and 19-13/0042r0
| Jari Junell | N | Procedure description of a method of handling at least 2 concurrent resource allocations by different CMs to the same WSO missing | Technical | 75 | 6.3 | 7 | See document 19-12/0196r0 | 1 | Accept in principle This has to be resolved.
| Jari Junell | N | Message definitions are very unclear and hard to read. There are also some amount of errors and missing messages. The order of messages needs som changes. | Technical | 75 | 6.4 |  | Modify the message definitions as proposed in 19-12/0199r0 | 1 | Accept in principle See contributions on message definitions 19-13/0048r0 and 19-13/0041r0.
| Jari Junell | N | Data type definitions are very unclear and hard to read. The order of data types do es not follow the order of messages. Some data types are missing, some do not belong to certain messages. | Technical | 91 | 6.5 |  | Modify the data type definitions as proposed in 19-12/0199r0 | 1 | Accept in principle See contributions on data type definitions 19-13/0050r0 and 19-13/0039r0.
| Jari Junell | N | Text missing in this sub-clause | T | 112 | 7.1 | 5 | add text | Yes | Accepted in principle. Refer response in CID 15.
| Jari Junell | N | Coexistence discovery is broken | Technical | 228 | 10.5.6 |  | See document 19-12/0200r0 | 1 | Accept in principle See contributions 19-13/0044r0, 19-13/0043r0 and 19-13/0047r1.
| Jari Junell | N | Are CDIS states for each CM separately or is the whole CDIS in one state at a time? In principle Inactive state refers to latter one but at least couple of last state transitions to the first option. If CDIS is always in one state it means e.g. that simultaneous requests from CM or CMs serving far away WSOs not in a same coexistence set can not be served simultaneously. | T | 76 | 6.2.2.1 | 1-34 | Clarify coverage of states (for each CM separately or CDIS has only one state at a time) | Y | Reject. Coverage of states depends on implementation which is outside of the scope of the draft.
| Jari Junell | N | What is connection request? Same as connection establishment in p.62? | T | 76 | 6.2.2.1 | 20 | Clarify the term and make a reference to appropriate page. | Y | Accepted in principle. Add the following sentense after the sentence "- The active state goes to the engaged state if CDIS receives connection request from CM and sends connection response to CM"; "Connection request and response are for connection establishement between two entities as described in sub-clause 6.1.1.1."
| Jari Junell | N | Flow chart in figure 57 is implementation description. CDIS internal processing behavior is not needed in spec. According to this flow chart e.g. If CDIS receives coexistence information request from CM and it is at that time in checking ""one or more subscribed CM are existed?"" CDIS has to make many decisions before it can start to solve the request from CM. | T | 77 | 6.2.2.1 | 1 | Remove flow chart or modify it to match with input to CDIS and related output to CM | Y | Reject. Flow chart in figure 57 is not implementation description. A profile describes a required procedures and messages to operate. Profile do not describe how to generate coexistence information for the CM. it depends on implementation.
| Jari Junell | N | Are CDIS states for each CM separately or is the whole CDIS in one state at a time? In principle Inactive state refers to latter one but at least couple of last state transitions to the first option. If CDIS is always in one state it means e.g. that simultaneous requests from CM or CMs serving far away WSOs not in a same coexistence set can not be served simultaneously. | T | 57 | 6.2.2.1 | 3-35 | Clarify coverage of states (for each CM separately or CDIS has only one state at a time) so that standard unambiguously defines the principle of operation or remove states. | Y | Reject. Coverage of states depends on implementation which is outside of the scope of the draft. Also, this comment was responded to during the 2nd recircualation.
| Jari Junell | N | CDIS states in the text are not visible in CDIS operations in figure 52. | T | 57 | 6.2.2.1 | 3-35, Figure 52 | Match together | Y | Reject. CDIS states description and flowchart complement each other to specify CDIS operation.
| Jari Junell | N | Flow chart in figure 58 is implementation description. | T | 97 | 6.3.1.1 | 1 | Change figure to more like spec type of description | Y | Reject. The comment is superseded by CID 47.
| Jari Junell | N | In figure 58 there is a decision ""Measurement is required"". If the answer is no still the flow goes to another measurement decision leading to ""obtaining X measurement procedure"" | T | 97 | 6.3.1.1 | 1 | If there is an error correct it. | Y | Reject. Obtaining measurement procedure may required if the CE received the measurement request by the CM previously. The requirement of current measurement is nothing to do with the past measurement request.
| Jari Junell | N | Figure 13 missing? | T | 56 | 6.3.2.1 | 2 | Add figure | Yes | Accepted
| Jari Junell | N | Organise section 6.3.4 to be consistent | Technical | 55 | 6.3.4 |  | Change section 6.3.4.3 as section 6.3.4.2, make a new section 6.3.4.3 Obtaining coexistence set element information (request/response between CMs), shift section 6.3.7.3 as 6.3.4.4 Providing coexistence set element information, shift section 6.3.4.2 as section 6.3.4.5 and shift section 6.3.4.4 as section 6.3.4.6. | 1 | Accept in principle See 19-12/0197r1
| Jari Junell | N | CM-CM procedure in 6.3.4 missing | Technical | 55 | 6.3.4 |  | See document 19-12/0197r0 | 1 | Accept in principle See 19-12/0197r1
| Jari Junell | N | Shift section 6.3.7.3 to section 6.3.4 as a subsection. There is missing in that section a CM to CM communication to inform relevant information of coexistence elements, their capabilities etc and also the environment view of reported CE. | Technical | 64 | 6.3.7.3 | 6 | Shift section 6.3.7.3 as a subsection of 6.3.4 | 1 | Accept in principle See 19-12/0197r1
| Jari Junell | N | Shift of algorithm based on balanced sharing from clause 7.2.2.7 to appendix not justified | T | 242 | 7.2.2.7 | 10 | Cancel move of the algorithm | Y | Reject. Two algorithms that are currently in Annex E were supposed to be supported by profile 3. As long as there is no profile 3 in the draft, these two algorithms were moved to the Annex E.
| Jari Junell | N | CDIS operation for profile O missing | T | 133 | 7.2.3 | 19 | Add CDIS operation for profile O | Yes | Accepted in principle.
| Jari Junell | N | CM operation for profile E missing | T | 134 | 7.3.1 | 2 | Add CM operation for profile E | Yes | See CID 26
| Jari Junell | N | CM operation for profile N missing | T | 134 | 7.3.2 | 3 | Add CM operation for profile N | Yes | See CID 22
| Jari Junell | N | CM operation for profile O missing | T | 134 | 7.3.3 | 4 | Add CM operation for profile N | Yes | Accepted in principle.
| Jari Junell | N | Value of the coexistence discovery threshold for network technologies is not defined anywhere. The algorithm can not be used by others because formula to define this value is unknown. | T | 256 | 7.4.1.2 | 36 | Add formula to calculate the value. | Y | Accept in principle. Add explanation of coexistence discovery threshold.
| Jari Junell | N | Add coexistence discovery algorithm for profile O | T | 269 | 8.4.1.2 | 20 |  | Yes | Rejected due to lack of contribution.
| Jari Junell | N | In algorithm in 8.4.2.5 make modifications according to responses in previous letter ballot | T | from p.305 | 8.4.2.5 | 9 | See responses in previous letter ballot | Yes | Accepted
| Jari Junell | N | Improve explanations (especially in Introduction) of clause 8.4.2.5 | T | from 305 | 8.4.2.5 | 9 |  | Yes | Accepted in principle. Request technical editor do improve the introduction
| Jari Junell | N | Add data type definitions to profile O. | T | 357 | A.3 | 11 | Define data types to profile O | Yes | Accepted in principle. Update the draft as shown in the contribution 19-13/0073r1
| Jari Junell | N | PICS incomplete | Technical | 241 | Annex B |  | Specify which features and protocols are mandatory and which are optional | 1 | Accept in principle Remove annex B on PICS
| Jari Junell | N | Remove "primitives" of profile O: actually they are data types | T | 369 | B.3 | 11 | Remove the whole clause B.3 | Yes | Accepted
| Jari Junell | N | Update messages in Annex C.3 for profile O | T | 390 | C.3 | 36 | Update messages of profile O (document ...) |  | Accepted in principle. Update the draft as shown in the contribution 19-13/0074r2
| Jari Junell | N | Section 8 is broken. | Technical |  |  |  | Update section to match with the content of other sections. | 1 | Accept in principle A new section 7 will have descriptions on each entity. CM description is, however, missing and needs more work.
| Jari Junell | N | Section 9 is broken. | Technical |  |  |  | Update section to match with the content of other sections. | 1 | Accept in principle Modify the draft as described in 19-13/0047r1 and 19-13/0043r0. Add text from contribution 19-13/0044r0 to section 10.
| Mika Kasslin | Y | Language and style in section 10.4 doesn't meet requirements of an industry standard. There is way too much text which belongs to documents like implementation guidelines and implementation specification. | General | 175 | 10.4 | 9 | Rewrite the whole section. | 0 | Accept in principle Instruct the editor to remove introduction text from section 10 that belongs to overview section 4. As an example, remove introduction in section 10 that is already in section 4. Take into account the motion on re-ordering the sections describing algorithms.
| Mika Kasslin | Y | PICS is incomplete. | Technical | 240 | B | 1 | Update the PICS as proposed in 19-12/0201r0. | 0 | Accept in principle Remove annex B on PICS
| Mika Kasslin | Y | MIB would be really useful addition to the draft as it would make it more clear what information each entity needs to maintain. | Technical | 241 | C | 8 | Add MIB as proposed in 19-12/0202r0. | 0 | Accept in principle Adopt text in contribution 19-13/0029r1 as informative annex.
| Mika Kasslin | Y | In some countries and areas it is illegal for a service provider to release location of a customer and thus the current operating model in which a CM registers WSO location to CDIS for coexistence discovery is illegal in some countries. | General | 5 | 4.3.3 | 26 | Modify the system so that a CM doesn't have to release location of a WSO to CDIS. Redesign the coexistence discovery so that the CDIS doesn't need to know actual location but it can still support the CM in coexistence discovery. | 0 | Withdrawn
| Mika Kasslin | Y | Interfaces A and C are between an IEEE 802.19.1 specified and an external element like WSO and TVBD DB. A specific implementation of those interfaces can not be mandated by the IEEE 802.19.1. | Technical | 6 | 4.4 | 1 | Make it clear in the specification that the interfaces A and C are logical and the IEEE 802.19.1 specification doesn't mandate a specific implementation. Consider deleting all the procedures and message definitions related to the interface C and specify the interface with primitives similarly with the interface A. | 0 | Accept in principle IETF PAWS is used in the interface C. See corresponding straw polls and motions.
| Mika Kasslin | Y | Authentication and deauthentication procedures and related messages as well as data types are useless since the specification mandates use of SSH and TLS. | Technical | 47 | 6.3.1 | 2 | Delete all the procedures dealing with authentication and deauthentication and update rest of the draft accordingly. | 0 | Accept in principle Profile N and O don't use authentication procedure. Profile E will be revised accordingly.
| Mika Kasslin | Y | The procedure description is incomplete. | Technical | 58 | 6.3.5.1 | 2 | Update the description as proposed in 19-12/0191r0. | 0 | Accepted
| Mika Kasslin | Y | Procedure description is incomplete. | Technical | 58 | 6.3.5.2 | 7 | Update the description as proposed in 19-12/0192r0. | 0 | Accepted
| Mika Kasslin | Y | Procedure description is incomplete. | Technical | 64 | 6.3.8.1 | 32 | Update the description as proposed in 19-12/0193r0. | 0 | Accept in principle See 19-12/0193r1
| Mika Kasslin | Y | Procedure description is incomplete. | Technical | 65 | 6.3.8.2 | 6 | Update the description as proposed in 19-12/0194r0. | 0 | Accepted
| Mika Kasslin | Y | Procedure description is incomplete. | Technical | 65 | 6.3.8.3 | 11 | Update the description as proposed in 19-12/0195r0. | 0 | Accepted See 19-12/0195r1
| Mika Kasslin | N | The TVWS DB interface is not specified by the 802.19.1 but the IETF PAWS is used. | T | 7 |  | 21 | Make it clear that the interface C is not specified in the 802.19.1 but the PAWS is used. | Yes | Accepted in principle. Refer response in CID 2.
| Mika Kasslin | N | This introduction section on algorithms is not up to date after the changes to the algorithm descriptions. | T | 9 | 4.6 | 12 | Update the section. | Yes | Accepted in principle. Refer response in CID 2.
| Mika Kasslin | N | Description of common entity operations is missing. | T | 112 | 7.1 | 5 | Add description of common entity operations approved earlier by the TG. | Yes | Accepted in principle. Refer response in CID 15.
| Mika Kasslin | N | CDIS and coexistence discovery should be the common basis for all the 802.19.1 implementations and there should be no profile dependency in its implementation. Otherwise there will be several independent profile dependent coexistence systems and that should not be allowed to happen. | T | 112 | 7.2 | 6 | Provide one CDIS description that is mandatory for all the CDIS implementations. | Yes | Accepted in principle. Update draft as described in contribution 19-13/0085r0
| Mika Kasslin | N | CM descriptions are missing. | T | 134 | 7.3 | 1 | Provide CM descriptions. | Yes | Accepted in principle.
| Mika Kasslin | N | This description is not a primitive description but a data type description. | T | 369 | B.3 | 11 | Move the content of the sub-section to A.3. | Yes | Refer CID 50
| Mika Kasslin | N | Message definitions are not up to date. | T | 390 | C.3 | 36 | Update the message definitions | Yes | Refer CID 61
| Mika Kasslin | N | Clause 4.1 has served as a good introduction to the specification and it should not be deleted. | T | 3 | 4 | 30 | Re-introduce the system overview clause. | Y | Reject. The current clause 4.1 provides good overview.
| Mika Kasslin | N | Term coexistence system is used in the draft text in many places (here first time) without any definition. It is unclear what a coexistence system is. Additionally, it is weird that one immediately talks about "the coexistence system" without any definition. | T | 13 | 4.1 | 8 | Define coexistence system and modify the sentence here to make clear what is "the coexistence system". | Y | Accept in principle. Add "defined in this draft standard" after the coexistence system.
| Mika Kasslin | N | The last sentence of the first paragraph below the figure implies that a CDIS has one algorithm. Does this mean that a CDIS may not have multiple different CDIS algorithms e.g. Depending on the CM profile? | T | 13 | 4.1 | 18 | Consider replacing the "...a coexistence discovery algorithm." with "...at least one coexistence algorithm." | Y | Accept in principle. Substitute "executes a coexistence discovery algorithm" by "performs coexistence discovery."
| Mika Kasslin | N | How can a CM provide anything to a WSO since it is having connections only to a CDIS, another CMs and CEs? | T | 13 | 4.1 | 20 | Modify the description to state that all the communication from/to WSO happens through a CE. | Y | Accept in principle. Add sentence "Comminication between the CM and the WSOs is performed via their CEs."
| Mika Kasslin | N | This sentence seems to imply that a CM may have only one coexistence decision algorithm. Is that really the intention? I would like to see it possible to have a CM to run several algorithms if so desired. | T | 14 | 4.1 | 2 | Consider replacing the "...a coexistence decision algorithm." with "...at least one decision algorithm." | Y | Accept in principle. Substitute "executes a coexistence decision algorithm" by "makes coexistence decisions."
| Mika Kasslin | N | I believe I know what a CE is but this sentence doesn't make any sense in my mind. Do you really mean that a CE needs to be able to interface different types of WSOs? I believe we should allow CEs which are tailored for one specific WSO. Additionally, I don't understand how a CE may provide a unified interface between WSOs and the coexistence system while it is itself part of the coexistence system. | T | 14 | 4.1 | 3 | Please re-write the sentence to simply state that a CE is an interface element that may represent one or multiple WSOs in a coexistence system. | Y | Accept in principle. Substitute the sentence mentioned in the comment by the following: "The Coexistence Enabler (CE) is an interface element that represents one ore several WSOs of the same type in the coexistence system."
| Mika Kasslin | N | What is meant with WSO type? This states that interface A implementation depends on WSO type. Does it mean that all the WLAN APs, as an example, have same interface A? I don't believe that is the case. I rather believe it can be anything and the draft should acknowledge it by stating that this interface is beyond the scope of the spec and implementation specific. | T | 14 | 4.1 | 8 | As per the comment | Y | Accept in principle. Remove "and its implementation depends on the WSO type" from the sentence.
| Mika Kasslin | N | This sentence seems to be in contradiction with the strict requirement in clause 5.1 on page 28 which mandates TCP. How is it possible that TCP is just an example? | T | 14 | 4.2 | 20 | Delete "for example" from the sentence. | Y | Accept.
| Mika Kasslin | N | Why a transport SAP would be used to interface an application layer? | T | 14 | 4.2 | 17 | Delete "application layer" from the sentence. | Y | Accept in principle. Delete the whole sentence.
| Mika Kasslin | N | What is the middle part of a figure with four vertical sections? | T | 15 | 4.2 | 2 | Make it very clear that the management entity is the second vertical box from right. | Y | Accept in principle. Delete sentences describing left, middle, and right parts of figure 3.
| Mika Kasslin | N | What does it mean that mapping "might be highly desirable"? Something is highly desirable but I would not use verb might in this context. | T | 15 | 4.2 | 13 | Re-write the sentence to read as follows: "A one-to-one mapping is highly desirable..." | N | Accept.
| Mika Kasslin | N | One-to-one mapping doesn't depend only on standard to which the WSO complies but WSO implementation matters as well. | T | 15 | 4.2 | 14 | Re-write the end of the sentence to read as follows: "standard, but feasibility of such an implementation depends on the standard the WSO complies to and the WSO implementation." | Y | Accept
| Mika Kasslin | N | It is unclear whether the intent is to enforce every CM implementation to support at least one of the profiles specificed in the spec or can a manufacturer specify its own profile | T | 16 | 4.3 | 13 | If the intent is to enforce every CM to support at least one of the profiles specified in the spec, re-write the bullet point to read as follows: "Any CM shall support at least one of the profiles specified in this specification" | Y | Accept
| Mika Kasslin | N | It is unclear whether the intent is to enforce every CE implementation to support at least one of the profiles specificed in the spec or can a manufacturer specify its own profile | T | 16 | 4.3 | 15 | If the intent is to enforce every CM to support at least one of the profiles specified in the spec, re-write the bullet point to read as follows: "Any CE shall support at least one of the profiles specified in this specification" | Y | Accept
| Mika Kasslin | N | One shouldn't use shall in the context of primitives that are not mandatory. | T | 35 | 5.2.2.3 | 5 | Revise the procedure description so that there are no mandates to use primitives defined for the interface A. As an example, follow the style of the other procedure descriptions. | Y | Accept in principle. Modify draft as shown in contribution 19-13-113r0. Request technical editor to check primitives and messages names and update when needed according to the names used in Annexes B and C.
| Mika Kasslin | N | Throughout this new clause one refers to a CE operation related to something that is specified in another clause. I can't imagine there is just one operation that is specified in that clause but one should rather use plural format. That's the way this is described in other similar clauses. | T | 35 | 5.2.2.3 | 6, 9, 12, 15 | Change operation to operations and "is specified" to "are specified". | Y | Accept.
| Mika Kasslin | N | The first sentence is gramatically broken and needs to be fixed. As an example, there is no such a thing as another CM. | T | 51 | 5.2.9.1 | 15 | Make the first sentence to read as follows: "After a CM receives a MasterCMRequest message from another CM, the CM shall generate and send a MasterCMResponse message to the CM." | Y | Accept in principle. Modify draft as shown in contribution 19-13-114r0.
| Mika Kasslin | N | Throughout this new clause one refers to a CM operation related to something that is specified in another clause. I can't imagine there is just one operation that is specified in that clause but one should rather use plural format. That's the way this is described in other similar clauses. | T | 51 | 5.2.9.1 | 16 | Change operation to operations and "is specified" to "are specified". | Y | Accept.
| Mika Kasslin | N | Throughout this new clause one refers to a CM operation related to something that is specified in another clause. I can't imagine there is just one operation that is specified in that clause but one should rather use plural format. That's the way this is described in other similar clauses. | T | 52 | 5.2.9.2 | 8, 10 | Change operation to operations and "is specified" to "are specified". | Y | Accept.
| Mika Kasslin | N | The rules are not on a specific MasterSlaveCMConfigurationRequest message but to any. Thus one should not use "the" but "a". Additionally, the message name is incorrect. | T | 52 | 5.2.9.2 | 8 | Change from "...the MasterSlaveCMRequest..." to "...a MasterSlaveCMConfigurationRequest...". | N | Accept in principle. Modify draft as shown in contribution 19-13-114r0.
| Mika Kasslin | N | Message names are incorrect in the second paragraph below the figure. | T | 52 | 5.2.9.2 | 9, 11 | Fix the message names. | N | Accept in principle. Modify draft as shown in contribution 19-13-114r0.
| Mika Kasslin | N | Why we need the bullet points on lines 16-18 while we have the point on line 15? In my mind the point 15 covers the next two points. | T | 60 | 6.1.1.1 | 16-18 | Delete the last two list items. | Y | Accept
| Mika Kasslin | N | It is stated that the transport service notifies the coexistence protocol above but I wonder whether that is really the case. At least the reference model in clause 4.2 states that transport services are used by an entity like a CE. Figure 51 here seems to imply the same. I believe notifications are sent to the entity instead. | T | 60 | 6.1.1.1 | 12, 17 | Replace the coexistence protocol with the entity. | N | Accept
| Mika Kasslin | N | It is stated that the figure 51 shows general operation of the transport SAP but it looks at least to me more like illustrating main phases of the transport service use. First, it is not clear from the figure where the SAP is. Second, the three horizontal solid line boxes cover everything including the two entities and their transport layers. I believe I understand what one tries to say with the figure but unfortunately it fails to do so at the moment. | T | 60 | 6.1.1.1 | 20 | Either modify the figure so that it really illustrate where the transport SAP is and how is it related to interaction between two transport layers, or change the title of the figure to be more in line with the current figure. | Y | Accept in principle. Request technical editor to modify figure title as proposed by the commenter.
| Mika Kasslin | N | Even if one doesn't intend to specify what needs to happen on failures like a failed transport service configuration, it would be good to state that this depends on implementation. | T | 62 | 6.1.1.2 | 4 | Add a sentence to this clause and to every other similar clause which states that when the status parameter contains a value other than noError, the entity operations are implementation specific and not specified in this specification. | Y | Reject This is already described in clause 6.1.3.
| Mika Kasslin | N | The clause seems to imply that the transport layer establishes a connection with two-way packet exchange. To my understanding this is not the way connection establishment works in TCP but three-way handshake is used. | T | 62 | 6.1.1.3 |  | Don't try to describe what happens on the transport layer since the intention is to specify the transport SAP behavior. Instead, simply state something like on a request primitive a transport specific connection establishment procedure is initiated and upon completing the procedure an indication is issued to the entity. | Y | Reject. Transport SAP needs to be specified.
| Mika Kasslin | N | Primitive name is incorrect. | T | 63 | 6.1.1.3 | 1 | Change the TrConnectionIndication to TrConnectionResponse. | N | Accept
| Mika Kasslin | N | The first sentence on this page is broken and needs to be fixed. Additionally, it is not clear what is meant with confirmation on the transmission status. | T | 64 | 6.1.1.4 | 1 | Change "being" to "been". Consider refining "confirmed on the transmission status". | N | Accept in principle. Change the sentence in line 1 to be "After the source entity transport service has been notified about the transmission status..."
| Mika Kasslin | N | The clause seems to imply that the transport layer terminates a connection with two-way packet exchange. To my understanding this is not the way connection termination works in TCP but four-way handshake is used. | T | 64 | 6.1.1.5 |  | Don't try to describe what happens on the transport layer since the intention is to specify the transport SAP behavior. Instead, simply state something like on a request primitive a transport specific connection termination procedure is initiated and upon completing the procedure an indication is issued to the entity. | Y | Reject. Transport SAP needs to be specified.
| Mika Kasslin | N | The last paragraph of this clause is entirely broken and needs to be fixed. First, I believe this specification specifies how an entity needs to behave when the status parameter is equal to noError. Second, it may be so that entity operations upon receiving some other parameter value are implementation specific. The current sentence doesn't reflect any of that though. | T | 67 | 6.1.3 | 3 | Fix the sentence e.g. as per the comment. | Y | Accept in principle. Request technical editor to update the paragraph as proposed by the commenter.
| Mika Kasslin | N | I challenge the approach taken in the draft according to which each CDIS needs to implement every possible CM profile from messaging perspective. The TG should instead harmonize the messages used in different profiles. This should not be an issue at all since CDIS is for coexistence discoery and there are really not too many different ways to conduct this discovery and all the basic parameters are the same regardless of the actual algorithm. The current design, instead, complicates a lot the CDIS design since there are two different ways to convey the same information. This is like the TG admitting that it has failed with its business to develop a specification for interoperability. | T | 67 | 6.2.1 | 41499 | Unify messages used between CMs and CDISs and make CM profiles invisible for a CDIS. | Y | Reject. The draft described how CDIS can communicate with a CM operating according to profile 1 or 2. How manufacturers of CDIS will optimize implem,entation of CDIS is left outside the scope of the draft.
| Mika Kasslin | N | The language in this clause is broken. In my mind this is a technical matter since it is very difficult to understand what is requested from an implementation. Fix the issues in the language. As an example, I think an entity may have states but entity operation may not. Additionally, a state doesn't go anywhere including another state. An entity may transfer to a state to another. It is also very unclear how the states relate to the CDIS operations illustrated in figure 57. The figure has no states whatsoever. They are not visible anywhere in the further descriptions of the profile. Thus their value is very unclear and questionable. My suggestion is to delete all the states from the description and shorten the general description a lot. | T | 76 | 6.2.2.1 |  | Delete everything from line 2 through line 33 on page 76. Modify the remaining text on page 78 by deleting everything that relates to states. | Y | Reject. An entity operation may have states. Sub-clause 6.2.1.1 describes states and how state transitions occur. It also describes how the states relate to the CDIS operation based on procedures and messages.
| Mika Kasslin | N | I believe a CDIS does something else than just replies with a response message upon receiving a subscription request message from a CM. The current description doesn't state that and is thus to my understanding very incomplete. | T | 78 | 6.2.2.2 | 25 | Add text that specifies what a CDIS needs to do with the information received in a subscription request message. | Y | Reject. A profile describes a required procedures and messages to operate. Profile do not describe how to generate the required information for the response message. It depends on implementation.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CM. | T | 79 | 6.2.2.3 | 7 | Delete the sentence. | N | Reject. The CDIS operation is affected by what happens in a CM.
| Mika Kasslin | N | I believe a CDIS does something else than just replies with a response message upon receiving a subscription update request message from a CM. The current description doesn't state that and is thus to my understanding very incomplete. | T | 79 | 6.2.2.3 | 9 | Add text that specifies what a CDIS needs to do with the information received in a subscription update request message. | Y | Reject. The comment is superseded by CID 48.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CM. | T | 80 | 6.2.2.4 | 2 | Delete the sentence. | N | Reject. The comment is superseded by CID 49.
| Mika Kasslin | N | I believe a CDIS does something else than just replies with a response message upon receiving a registration request message from a CM. The current description doesn't state that and is thus to my understanding very incomplete. | T | 80 | 6.2.2.4 | 4 | Add text that specifies what a CDIS needs to do with the information received in a registration request message. | Y | Reject. The comment is superseded by CID 48.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CM. | T | 80 | 6.2.2.5 | 14 | Delete the sentence. | N | Reject. The comment is superseded by CID 49.
| Mika Kasslin | N | I believe a CDIS does something else than just replies with a response message upon receiving a registration update request message from a CM. The current description doesn't state that and is thus to my understanding very incomplete. | T | 80 | 6.2.2.5 | 16 | Add text that specifies what a CDIS needs to do with the information received in a registration update request message. | Y | Reject. The comment is superseded by CID 48.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CM. | T | 81 | 6.2.2.6 | 8 | Delete the sentence. | N | Reject. The comment is superseded by CID 49.
| Mika Kasslin | N | Profile 3 CDIS description is missing. | T | 95 | 6.2.4 | 15 | Adopt text proposal in submission 19-13/0100r0 | Y | Accept in principle. Remove empty clause 6.3.3 Profile 3 and clause 6.4.3 Profile 3 from the draft.
| Mika Kasslin | N | The language in this clause is broken. In my mind this is a technical matter since it is very difficult to understand what is requested from an implementation. Fix the issues in the language. As an example, I think an entity may have states but entity operation may not. Additionally, a state doesn't go anywhere including another state. An entity may transfer to a state to another. It is also very unclear how the states relate to the CM operations illustrated in figure 59. The figure has no states whatsoever. They are not visible anywhere in the further descriptions of the profile. Thus their value is very unclear and questionable. My suggestion is to delete all the states from the description and shorten the general description a lot. | T | 95 | 6.3.1.1 |  | Delete everything from line 18 on page 95 through line 35 on page 96. Modify the remaining text on pages 99 and 100 by deleting everything that relates to states. | Y | Reject. An entity operation may have states. Sub-clause 6.3.1.1 describes states and how state transitions occur. It also describes how the states relate to the CM operation based on procedures and messages.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CE. | T | 102 | 6.3.1.4 | 7 | Delete the sentence. | N | Reject. The CM operation is affected by what happens in a CE.
| Mika Kasslin | N | I believe a CM does something else than just replies with a response message upon receiving a subscription request message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 102 | 6.3.1.4 | 9 | Add text that specifies what a CM needs to do with the information received in a subscription request message. | Y | Reject. A profile describes a required procedures and messages to operate. Profile do not describe how to generate the required information for the response message. It depends on implementation.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CE. | T | 102 | 6.3.1.5 | 16 | Delete the sentence. | N | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | I believe a CM does something else than just replies with a response message upon receiving a subscription update request message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 102 | 6.3.1.5 | 18 | Add text that specifies what a CM needs to do with the information received in a subscription update request message. | Y | Reject. The comment is superseded by CID 62.
| Mika Kasslin | N | What does it mean that "WSO/CE is not feasible for the current coexistence service"? Feasible is not a proper word for this sentence, I's sure about that. But I don't know what would be the more appropriate term since I don't understand the reasons for a CM to request a WSO/CE to change the service subscription. If one means that the other service is more appropriate from coexistence perspective, the suitable or appropriate term might be used. | T | 103 | 6.3.1.6 | 4 | Modify the sentence to make more sense e.g. as proposed in the comment. | Y | Accepted. Replace "feasible" with "suitable"
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CE. | T | 103 | 6.3.1.6 | 5 | Delete the sentence. If you leave it, fix the gramatical errors at least. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | The description starts with reference to RegistrationResponse message but I believe this clause should start from reception of a RegistrationRequest message and describe what happens after that. | T | 103 | 6.3.1.7 | 22 | Add description for RegistrationRequest message reception and RegistrationResponse message generation and transmission. | Y | Reject. Comment is wrong. See sub-clause 5.2.2.1.
| Mika Kasslin | N | The description starts with reference to RegistrationResponse message but I believe this clause should start from reception of a RegistrationRequest message and describe what happens after that. | T | 104 | 6.3.1.8 | 9 | Add description for RegistrationRequest message reception and RegistrationResponse message generation and transmission. | Y | Reject. Comment is wrong. See sub-clause 5.2.2.2.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CE. | T | 105 | 6.3.1.9 | 5 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | I believe a CM does something else than just replies with a confirm message upon receiving an event indication message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 105 | 6.3.1.9 | 7 | Add text that specifies what a CM needs to do with the information received in an event indication message. | Y | Reject. The comment is superseded by CID 62.
| Mika Kasslin | N | The current description allows a CM to indicate to another CM that some threshold has been met/exceeded or QoS has degraded. But there is no indication of the WSO to which this indication relates. | T | 106 | 6.3.1.10 | 4 | Add a WSO id parameter to the message. | Y | Accept in principle. Modify sub-clause 6.3.1.10 in the draft as shown in contribution 19-13/0120r0.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CE. | T | 107 | 6.3.1.12 | 2 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 108 | 6.3.1.13 | 12 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 108 | 6.3.1.13 | 14 | Delete the sentence and all the related tables. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 110 | 6.3.1.17 | 6 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | I believe a CM does something else than just replies with a confirm message upon receiving a one time measurement message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 110 | 6.3.1.17 | 8 | Add text that specifies what a CM needs to do with the information received in a measurement response message. | Y | Reject. The comment is superseded by CID 62.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 110 | 6.3.1.18 | 6 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | I believe a CM does something else than just replies with a confirm message upon receiving a scheduled measurement message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 110 | 6.3.1.18 | 8 | Add text that specifies what a CM needs to do with the information received in a measurement response message. | Y | Reject. The comment is superseded by CID 62.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 112 | 6.3.1.20 | 2 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | The description lacks information about the actual negotiatoin process as it does describes only the protocol. Further text is required to describe what's put into the messages and why. | T | 113 | 6.3.1.22 |  | Provide more text about the negotiation itself. If the description is already somewhere in the draft, please, add at least a reference to that clause. | Y | Reject. Negotiation process is described in sub-clause 7.4.2.2
| Mika Kasslin | N | This sentence and the subsequent list don't belong to this clause as it describes what happens in a CE. | T | 119 | 6.3.1.27 | 41529 | Delete the sentence and the following list. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | Profile 3 CM description is missing. | T | 155 | 6.3.3 | 14 | Adopt text proposal in submission 19-13/0098r0 | Y | Accept in principle. Remove empty clause 6.3.3 Profile 3 and clause 6.4.3 Profile 3 from the draft.
| Mika Kasslin | N | Profile 3 CE description is not up to date. | T | 229 | 6.4.3.1 | 4 | Adopt text proposal in submission 19-13/0099r0 | Y | Accept in principle. Remove empty clause 6.3.3 Profile 3 and clause 6.4.3 Profile 3 from the draft.
| Mika Kasslin | N | This algorithm clearly assumes and requires profile 2 based CDIS implementation. This is not, however, stated anywhere in the description. The biggest concern I have with the current description is that it discusses a lot how message parameters are set but doesn't describe any form of algorithm pretty much all except in the very few equations. In my mind the current description fits much better into the profile 2 clause. | T | 255 | 7.4.1.2 | 20 | Consider moving a lot of the current description to the clause that specified profile 2 based CDIS. To the very least, make it very clear that this algorithm requires profile 2 implementation. | N | Accept in principle. Add sentence at the beginning "This algorithm is related to profile 2."
| Mika Kasslin | N | The algorithm description is still way too much like implementation specification. The description doesn't follow the style assumed in industry standard and it should be entirely re-written in order to ensure interoperability. | T | 258 | 7.4.2.1 | 21 | Re-write the whole clause especially from the style perspective. | Y | Reject. Flags in the algorithm are used for a trigger to start designated action. The algorithm is mainly composed by two steps: channel classification and channel allocation. This is not like implementation specification.
| Mika Kasslin | N | There is way too much repetition in the algorithm description which makes the implementation practically impossible. | T | 267 | 7.4.2.2 | 3 | Re-write the whole clause especially from the style perspective. | Y | Reject. The number of message exchnages between CMs for negotiation is limited.
| Mika Kasslin | N | This algorithm clearly assumes and requires profile 2 based CM implementation. This is not, however, stated anywhere in the description. | T | 290 | 7.4.2.7 | 21 | Make it very clear that this algorithm requires profile 2 implementation. | Y | Accept in principle. Add sentence at the beginning "This algorithm is related to profile 2."
| Mika Kasslin | N | A lot of grammatical errors in the algorithm descrption in this clause which make implementation of the algorithm practically impossible. | T | 295 | 7.4.2.8 | 11 | Adopt text proposal in submission 19-13/0103r0 | Y | Reject. The current description is quite clear.
| Mika Kasslin | N | Profile 3 support in data type definitions is incomplete. | T | 364 | Annex A | 13 | Adopt text proposal in submission 19-13/0102r0 | Y | Reject. Profile 3 has been removed from the draft due to its incompleteness.
| Mika Kasslin | N | Primitives are not mandatory and thus they should not be specified in normative annex. | T | 379 | Annex B | 1 | Change the annex from normative to informative. | Y | Reject. This Annex is normative because this is needed for proper operation of the coexistence system. Translation between WSO-specific primitives and coexistence system specific primitives is done by CXPM described in reference model.
| Mika Kasslin | N | Profile 3 support in message definitions is incomplete. | T | 433 | Annex C | 16 | Adopt text proposal in submission 19-13/0101r0 | Y | Reject. Profile 3 has been removed from the draft due to its incompleteness.
| Mika Kasslin | N | The coexistence report announcement message is broken. | T | 440 | Annex C | 8 | Replace the text on lines 8 through 10 with the following: "--Coexistence report information coexistenceReport CoexistenceReport}" | Y | Reject. The message is not broken.