## Title Page
2013-11-13 |  | IEEE P802.19.1-13/0141r0
IEEE P802.19.1
Project | IEEE P802.19.1
Title | Comments associated with No votes
Date Submitted | 2013
Spurce | Stanislav Filin | Voice:
| NICT | Fax: [ ]
E-mail: sfilin@nict.go.jp
Abstract
Purpose | This document contains comments and related resolutions for outstanding No votes.
Notice | This document has been prepared to assist the IEEE P802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.

## Comments
CID | Name | Vote (Y/N/A) | Comment | Category | Page Number | Subclause | Line Number | Proposed Change | Must Be Satisfied | Response
| Jari Junell | N | Flow chart in figure 57 is implementation description. CDIS internal processing behavior is not needed in spec. According to this flow chart e.g. If CDIS receives coexistence information request from CM and it is at that time in checking ""one or more subscribed CM are existed?"" CDIS has to make many decisions before it can start to solve the request from CM. | T | 77 | 6.2.2.1 | 1 | Remove flow chart or modify it to match with input to CDIS and related output to CM | Y | Reject. Flow chart in figure 57 is not implementation description. A profile describes a required procedures and messages to operate. Profile do not describe how to generate coexistence information for the CM. it depends on implementation.
| Jari Junell | N | Are CDIS states for each CM separately or is the whole CDIS in one state at a time? In principle Inactive state refers to latter one but at least couple of last state transitions to the first option. If CDIS is always in one state it means e.g. that simultaneous requests from CM or CMs serving far away WSOs not in a same coexistence set can not be served simultaneously. | T | 57 | 6.2.2.1 | 3-35 | Clarify coverage of states (for each CM separately or CDIS has only one state at a time) so that standard unambiguously defines the principle of operation or remove states. | Y | Reject. Coverage of states depends on implementation which is outside of the scope of the draft. Also, this comment was responded to during the 2nd recircualation.
| Jari Junell | N | Flow chart in figure 58 is implementation description. | T | 97 | 6.3.1.1 | 1 | Change figure to more like spec type of description | Y | Reject. The comment is superseded by CID 47.
| Jari Junell | N | In figure 58 there is a decision ""Measurement is required"". If the answer is no still the flow goes to another measurement decision leading to ""obtaining X measurement procedure"" | T | 97 | 6.3.1.1 | 1 | If there is an error correct it. | Y | Reject. Obtaining measurement procedure may required if the CE received the measurement request by the CM previously. The requirement of current measurement is nothing to do with the past measurement request.
| Jari Junell | N | Add coexistence discovery algorithm for profile O | T | 269 | 8.4.1.2 | 20 |  | Yes | Rejected due to lack of contribution.
| Mika Kasslin | N | Clause 4.1 has served as a good introduction to the specification and it should not be deleted. | T | 3 | 4 | 30 | Re-introduce the system overview clause. | Y | Reject. The current clause 4.1 provides good overview.
| Mika Kasslin | N | Even if one doesn't intend to specify what needs to happen on failures like a failed transport service configuration, it would be good to state that this depends on implementation. | T | 62 | 6.1.1.2 | 4 | Add a sentence to this clause and to every other similar clause which states that when the status parameter contains a value other than noError, the entity operations are implementation specific and not specified in this specification. | Y | Reject This is already described in clause 6.1.3.
| Mika Kasslin | N | The clause seems to imply that the transport layer establishes a connection with two-way packet exchange. To my understanding this is not the way connection establishment works in TCP but three-way handshake is used. | T | 62 | 6.1.1.3 |  | Don't try to describe what happens on the transport layer since the intention is to specify the transport SAP behavior. Instead, simply state something like on a request primitive a transport specific connection establishment procedure is initiated and upon completing the procedure an indication is issued to the entity. | Y | Reject. Transport SAP needs to be specified.
| Mika Kasslin | N | The clause seems to imply that the transport layer terminates a connection with two-way packet exchange. To my understanding this is not the way connection termination works in TCP but four-way handshake is used. | T | 64 | 6.1.1.5 |  | Don't try to describe what happens on the transport layer since the intention is to specify the transport SAP behavior. Instead, simply state something like on a request primitive a transport specific connection termination procedure is initiated and upon completing the procedure an indication is issued to the entity. | Y | Reject. Transport SAP needs to be specified.
| Mika Kasslin | N | I challenge the approach taken in the draft according to which each CDIS needs to implement every possible CM profile from messaging perspective. The TG should instead harmonize the messages used in different profiles. This should not be an issue at all since CDIS is for coexistence discoery and there are really not too many different ways to conduct this discovery and all the basic parameters are the same regardless of the actual algorithm. The current design, instead, complicates a lot the CDIS design since there are two different ways to convey the same information. This is like the TG admitting that it has failed with its business to develop a specification for interoperability. | T | 67 | 6.2.1 | 41499 | Unify messages used between CMs and CDISs and make CM profiles invisible for a CDIS. | Y | Reject. The draft described how CDIS can communicate with a CM operating according to profile 1 or 2. How manufacturers of CDIS will optimize implem,entation of CDIS is left outside the scope of the draft.
| Mika Kasslin | N | The language in this clause is broken. In my mind this is a technical matter since it is very difficult to understand what is requested from an implementation. Fix the issues in the language. As an example, I think an entity may have states but entity operation may not. Additionally, a state doesn't go anywhere including another state. An entity may transfer to a state to another. It is also very unclear how the states relate to the CDIS operations illustrated in figure 57. The figure has no states whatsoever. They are not visible anywhere in the further descriptions of the profile. Thus their value is very unclear and questionable. My suggestion is to delete all the states from the description and shorten the general description a lot. | T | 76 | 6.2.2.1 |  | Delete everything from line 2 through line 33 on page 76. Modify the remaining text on page 78 by deleting everything that relates to states. | Y | Reject. An entity operation may have states. Sub-clause 6.2.1.1 describes states and how state transitions occur. It also describes how the states relate to the CDIS operation based on procedures and messages.
| Mika Kasslin | N | I believe a CDIS does something else than just replies with a response message upon receiving a subscription request message from a CM. The current description doesn't state that and is thus to my understanding very incomplete. | T | 78 | 6.2.2.2 | 25 | Add text that specifies what a CDIS needs to do with the information received in a subscription request message. | Y | Reject. A profile describes a required procedures and messages to operate. Profile do not describe how to generate the required information for the response message. It depends on implementation.
| Mika Kasslin | N | I believe a CDIS does something else than just replies with a response message upon receiving a subscription update request message from a CM. The current description doesn't state that and is thus to my understanding very incomplete. | T | 79 | 6.2.2.3 | 9 | Add text that specifies what a CDIS needs to do with the information received in a subscription update request message. | Y | Reject. The comment is superseded by CID 48.
| Mika Kasslin | N | I believe a CDIS does something else than just replies with a response message upon receiving a registration request message from a CM. The current description doesn't state that and is thus to my understanding very incomplete. | T | 80 | 6.2.2.4 | 4 | Add text that specifies what a CDIS needs to do with the information received in a registration request message. | Y | Reject. The comment is superseded by CID 48.
| Mika Kasslin | N | I believe a CDIS does something else than just replies with a response message upon receiving a registration update request message from a CM. The current description doesn't state that and is thus to my understanding very incomplete. | T | 80 | 6.2.2.5 | 16 | Add text that specifies what a CDIS needs to do with the information received in a registration update request message. | Y | Reject. The comment is superseded by CID 48.
| Mika Kasslin | N | The language in this clause is broken. In my mind this is a technical matter since it is very difficult to understand what is requested from an implementation. Fix the issues in the language. As an example, I think an entity may have states but entity operation may not. Additionally, a state doesn't go anywhere including another state. An entity may transfer to a state to another. It is also very unclear how the states relate to the CM operations illustrated in figure 59. The figure has no states whatsoever. They are not visible anywhere in the further descriptions of the profile. Thus their value is very unclear and questionable. My suggestion is to delete all the states from the description and shorten the general description a lot. | T | 95 | 6.3.1.1 |  | Delete everything from line 18 on page 95 through line 35 on page 96. Modify the remaining text on pages 99 and 100 by deleting everything that relates to states. | Y | Reject. An entity operation may have states. Sub-clause 6.3.1.1 describes states and how state transitions occur. It also describes how the states relate to the CM operation based on procedures and messages.
| Mika Kasslin | N | I believe a CM does something else than just replies with a response message upon receiving a subscription request message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 102 | 6.3.1.4 | 9 | Add text that specifies what a CM needs to do with the information received in a subscription request message. | Y | Reject. A profile describes a required procedures and messages to operate. Profile do not describe how to generate the required information for the response message. It depends on implementation.
| Mika Kasslin | N | I believe a CM does something else than just replies with a response message upon receiving a subscription update request message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 102 | 6.3.1.5 | 18 | Add text that specifies what a CM needs to do with the information received in a subscription update request message. | Y | Reject. The comment is superseded by CID 62.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CE. | T | 103 | 6.3.1.6 | 5 | Delete the sentence. If you leave it, fix the gramatical errors at least. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | The description starts with reference to RegistrationResponse message but I believe this clause should start from reception of a RegistrationRequest message and describe what happens after that. | T | 103 | 6.3.1.7 | 22 | Add description for RegistrationRequest message reception and RegistrationResponse message generation and transmission. | Y | Reject. Comment is wrong. See sub-clause 5.2.2.1.
| Mika Kasslin | N | The description starts with reference to RegistrationResponse message but I believe this clause should start from reception of a RegistrationRequest message and describe what happens after that. | T | 104 | 6.3.1.8 | 9 | Add description for RegistrationRequest message reception and RegistrationResponse message generation and transmission. | Y | Reject. Comment is wrong. See sub-clause 5.2.2.2.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CE. | T | 105 | 6.3.1.9 | 5 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | I believe a CM does something else than just replies with a confirm message upon receiving an event indication message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 105 | 6.3.1.9 | 7 | Add text that specifies what a CM needs to do with the information received in an event indication message. | Y | Reject. The comment is superseded by CID 62.
| Mika Kasslin | N | The first sentence in the clause doesn't belong to this clause as it describes what happens in a CE. | T | 107 | 6.3.1.12 | 2 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 108 | 6.3.1.13 | 12 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 108 | 6.3.1.13 | 14 | Delete the sentence and all the related tables. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 110 | 6.3.1.17 | 6 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | I believe a CM does something else than just replies with a confirm message upon receiving a one time measurement message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 110 | 6.3.1.17 | 8 | Add text that specifies what a CM needs to do with the information received in a measurement response message. | Y | Reject. The comment is superseded by CID 62.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 110 | 6.3.1.18 | 6 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | I believe a CM does something else than just replies with a confirm message upon receiving a scheduled measurement message from a CE. The current description doesn't state that and is thus to my understanding very incomplete. | T | 110 | 6.3.1.18 | 8 | Add text that specifies what a CM needs to do with the information received in a measurement response message. | Y | Reject. The comment is superseded by CID 62.
| Mika Kasslin | N | This sentence doesn't belong to this clause as it describes what happens in a CE. | T | 112 | 6.3.1.20 | 2 | Delete the sentence. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | The description lacks information about the actual negotiatoin process as it does describes only the protocol. Further text is required to describe what's put into the messages and why. | T | 113 | 6.3.1.22 |  | Provide more text about the negotiation itself. If the description is already somewhere in the draft, please, add at least a reference to that clause. | Y | Reject. Negotiation process is described in sub-clause 7.4.2.2
| Mika Kasslin | N | This sentence and the subsequent list don't belong to this clause as it describes what happens in a CE. | T | 119 | 6.3.1.27 | 41529 | Delete the sentence and the following list. | Y | Reject. The comment is superseded by CID 61.
| Mika Kasslin | N | The algorithm description is still way too much like implementation specification. The description doesn't follow the style assumed in industry standard and it should be entirely re-written in order to ensure interoperability. | T | 258 | 7.4.2.1 | 21 | Re-write the whole clause especially from the style perspective. | Y | Reject. Flags in the algorithm are used for a trigger to start designated action. The algorithm is mainly composed by two steps: channel classification and channel allocation. This is not like implementation specification.
| Mika Kasslin | N | There is way too much repetition in the algorithm description which makes the implementation practically impossible. | T | 267 | 7.4.2.2 | 3 | Re-write the whole clause especially from the style perspective. | Y | Reject. The number of message exchnages between CMs for negotiation is limited.
| Mika Kasslin | N | A lot of grammatical errors in the algorithm descrption in this clause which make implementation of the algorithm practically impossible. | T | 295 | 7.4.2.8 | 11 | Adopt text proposal in submission 19-13/0103r0 | Y | Reject. The current description is quite clear.
| Mika Kasslin | N | Profile 3 support in data type definitions is incomplete. | T | 364 | Annex A | 13 | Adopt text proposal in submission 19-13/0102r0 | Y | Reject. Profile 3 has been removed from the draft due to its incompleteness.
| Mika Kasslin | N | Primitives are not mandatory and thus they should not be specified in normative annex. | T | 379 | Annex B | 1 | Change the annex from normative to informative. | Y | Reject. This Annex is normative because this is needed for proper operation of the coexistence system. Translation between WSO-specific primitives and coexistence system specific primitives is done by CXPM described in reference model.
| Mika Kasslin | N | Profile 3 support in message definitions is incomplete. | T | 433 | Annex C | 16 | Adopt text proposal in submission 19-13/0101r0 | Y | Reject. Profile 3 has been removed from the draft due to its incompleteness.
| Mika Kasslin | N | The coexistence report announcement message is broken. | T | 440 | Annex C | 8 | Replace the text on lines 8 through 10 with the following: "--Coexistence report information coexistenceReport CoexistenceReport}" | Y | Reject. The message is not broken.