## Slide 1: Proposed project timeline
Date: 2015-05-14
Authors:
Notice: This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.

## Slide 2: Study Group Action items
From “March 2015 CUB SG Minutes” (19-15/0031r0)
  Need to develop a timeline for the project (19-15/0044r0)
  Need to decide between two approaches to the title of the PAR (19-15/0034r0)
    List frequencies (e.g. TVWS, 3.5 GHz, 5 GHz)
    Describe regulatory constraints (e.g. “database managed bands”)
  Develop one to two slides giving a concise describing the need for new amendment to the current 802.19.1 standard (19-15/0032r0)
  Develop a draft press release for the July plenary (19-15/0045r0)
  Finalized the PAR and CSD

## Slide 3: Draft development process
Documents for draft development
  System design document
  Technical guidance document
  Use case document
  …
Contribution approach of text proposal
  Contributions on different parts of standards
  Full proposal

## Slide 4: Schedule 1

## Slide 5: Proposed call for proposal
Sep.
Bangkok
13-18
Nov.
Dallas 8-13
Jan.
Atlanta
17-22
Initial
Presentations
Deadline Jan. 10
Issue Call Sep. 17
Call for Proposals
Full
Presentations

## Slide 6: Schedule plan details
PAR/CSD submission June 17, 2015
PAR/CSD Approval
  EC July 17, 2015
  NesCom September 2, 2015
WG Letter Ballot
  Initial May, 2016
  1st Recirc. September, 2016
  2nd Recirc. November, 2016
Form Sponsor Ballot Pool January, 2017
IEEE-SA Sponsor Ballot
  Initial January, 2017
  1st Recirc. May, 2017
  2nd Recirc. July, 2017
Final WG and EC approval November, 2017
Final RevCom approval January, 2018

## Slide 7: Letter Ballot details
May 2016 Session
  The TG and WG move to submit draft specification to Letter Ballot.
  WG submits to Letter Ballot at the end of the session
  30 days to issue all comments
July 2016 Session
  TG responds to all comments (as long as it takes)
September 2016 Session
  TG responds to all comments (as long as it takes)
  1st recirculate draft specification at the end of the session

## Slide 8: Schedule 2

## Slide 9: Proposed call for proposal
Nov.
Dallas
8-13
Jan.
Atlanta 17-22
Mar.
Macau
13-18
Initial
Presentations
Deadline Jan. 10
Issue Call Sep. 17
Call for Proposals
Full
Presentations

## Slide 10: Schedule plan details
PAR/CSD submission June 17, 2015
PAR/CSD Approval
  EC July 17, 2015
  NesCom September 2, 2015
WG Letter Ballot
  Initial November, 2016
  1st Recirc. March, 2017
  2nd Recirc. May, 2017
Form Sponsor Ballot Pool July, 2017
IEEE-SA Sponsor Ballot
  Initial August, 2017
  1st Recirc. November, 2017
  2nd Recirc. January, 2018
Final WG and EC approval March, 2018
Final RevCom approval May, 2018

## Slide 11: Letter Ballot details
November 2016 Session
  The TG and WG move to submit draft specification to Letter Ballot.
  WG submits to Letter Ballot at the end of the session
  30 days to issue all comments
January 2017 Session
  TG responds to all comments (as long as it takes)
March 2017 Session
  TG responds to all comments (as long as it takes)
  1st recirculate draft specification at the end of the session