## Slide 1: TG1a Project timeline plan
Date: 2015-11-09
Authors:
Notice: This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.

## Slide 2: Abstract
This document is the presentation of TG1a project timeline plan.
Timeline document is 19-15/0096r0.

## Slide 3: Schedule plan details
The first TG1a meeting November, 2015
Draft development
  First candidate draft document March, 2016
  Candidate draft document May, 2016
  Draft text (Draft 1.0) July, 2016
WG Letter Ballot
  Initial November, 2016
  1st Recirculation March, 2017
  2nd Recirculation May, 2017
Form Sponsor Ballot Pool May, 2017
IEEE-SA Sponsor Ballot
  Initial August, 2017
  1st Recirculation November, 2017
  2nd Recirculation January, 2018
Final WG and EC approval March, 2018
Final RevCom approval May, 2018

## Slide 4: Letter Ballot details
November 2016 Session
  The TG and WG move to submit draft specification to Letter Ballot.
  WG submits to Letter Ballot at the end of the session
  30 days to issue all comments
January 2017 Session
  TG responds to all comments (as long as it takes)
March 2017 Session
  TG responds to all comments (as long as it takes)
  1st recirculate draft specification at the end of the session