## Slide 1: January 2017 TG1a Closing Report
Date: 2016-11-19
Authors:
Notice: This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.

## Slide 2: Abstract
This is TG1a closing report from January 2017 IEEE 802.19 meeting in Atlanta, GA.

## Slide 3: Results of the week (1/2)
Technical contributions were discussed
  DCN 19-17/0012r2: Proposed resolution to CID 11 for D1.0 (C. Sun)
  DCN 19-17/0013r2: Proposed resolution to CID 12 for D1.0 (C. Sun)
  DCN 19-17/0014r2: Proposed resolution to CID 13 for D1.0 (C. Sun)
  DCN 19-17/0011r2: Comment resolutions on CID7, CID8, CID9 and CID10 (S. Furuichi)
  DCN 19-17/0015r2: Comment resolutions on CID1, CID2 and CID3 (S. Furuichi)
All comments from WG letter ballot were resolved
  Total 13 comments were received
  Technical: 10, Editorial: 3

## Slide 4: Results of the week (2/2)
Project time line was reviewed
  Update to DCN 19-15/0096r1
Move to recirculation WG letter ballot after this meeting
Discussed PAR title change
  Please see DCN 19-17/0020r0
Run some TG motions
  Please see following slides;

## Slide 5: New project time line
 | 2015 | 2016 |  |  |  |  |  | 2017 |  |  |  |  |  | 2018 |  |  |  |  | 
 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11
Task Group formed | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Technical proposal presentations |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop draft document |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Create candidate draft document |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment ballot on the candidate draft |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolutions on the candidate draft |  |  |  |  | x | x | x |  |  |  |  |  |  |  |  |  |  |  | 
Adoption of draft text (Draft1.0) |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  | 
Submit Draft 1.0 to Letter Ballot |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolutions in Letter Ballot |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | 
Submit Draft 2.0 to 1st Recirculation Ballot |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  | 
Comment resolutions in 1st Recirculation Ballot |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  | 
Submit Draft 3.0 to Sponsor Ballot |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  | 
Comment resolutions in Sponsor Ballot |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  | 
Submit Draft 4.0 to 1st Recirculation Ballot |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  | 
Comment resolutions in 1st Recirculation Ballot |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | 
Submit Draft 5.0 to 2nd Recirculation Ballot |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  | 
Comment resolutions in 2nd Recirculation Ballot |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  | 
Final WG and 802 EC approval |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  | 
IEEE-SA RevCom approval |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  | 

## Slide 6: TG Motion
Instruct the TG editor to resolve editorial comments, and implement the resolutions for technical comments according to column J of DCN 19-17/0009r2
  Move: S. Furuichi
  Second: C. Sun
  Approved by unanimous consensus

## Slide 7: TG Motion
Approve text proposals in DCN 19-17/0011r2, 19-17/0012r2, 19-17/0013r2, 19-17/0014r2 and 19-17/0015r2 instruct the TG editor to implement approved text proposals and update to the IEEE P802.19.1a candidate draft D2.0 by January 19, 2017
  Move: C. Sun
  Second: S. Furuichi
  Approved by unanimous consensus

## Slide 8: TG Motion
Approve to ask working group chairman to start 14 days recirculation working group letter ballot using the IEEE P802.19.1a-D2.0
  Move: C. Sun
  Second: S. Furuichi
  Approved by unanimous consensus

## Slide 9: Conference calls
Day | Date | Start Time | End Time | Call Host
Tuesday | Jan. 22 | 1:00AM ET | 2:00AM ET | Naotaka Sato
Meeting Logistics
  Use “Join Me”
    Join the meeting: https://join.me/ieeesawg802.19 On a computer, use any browser. Nothing to download. On a phone or tablet, launch the join.me app and enter meeting code:ieeesawg802.19 Join the audio conference: Dial a phone number and enter access code, or connect via internet.
  The chair will send out a notification to IEEE 802.19 reflector in advance of the meeting

## Slide 10: March 2017 meeting Objectives
Start to resolve comments from recirculation WG Letter Ballot
Possible to move Sponsor Ballot after March meeting