IEEE P802.21 Media Independent Handover Services

Teleconference Minutes of the IEEE P802.21a Security Task Group

Chair: Yoshihiro Ohba

Minutes taken by H Anthony Chan

# Meeting called to order by Yoshi Ahba 802.21a SG at 10:04AM EST.

# Call for Proposal (21-09-0017-00-0000)

## The call for proposal was discussed in the January Interim meeting, but the attendance was low at that time. This teleconference discusses this again to receive more comments

## Scope of proposals

### Work Item #1: Mechanisms to reduce the latency during authentication and key establishment for handovers between heterogeneous access networks that support IEEE 802.21

### Work Item #2: Mechanisms to provide data integrity, replay protection, confidentiality and data origin authentication to IEEE 802.21 MIH protocol exchanges and enable authorization for MIH serviceshttps://mentor.ieee.org/802.21/documents

## Submission deadline May 3 2009

## Timeline and proposal presentation (slides 5 and 6)

### Call for proposal: March 2009

### Presentation I May 2009 (text not yet needed), may vote to allow new proposal in May (if there are not enough proposals in May)

### Presentation II July 2009 (detail text needed), may vote to allow new proposal

### Presentation III September 2009 (detail text needed), no new proposals after this.

### Down-delection November 2009 after above 3 rounds of presentations

Comment: 3 trials in Slide 6 refers to 3 rounds of presentations

## Discussion about voting in May to allow new proposal

### Comment: may not be enough time to make decision to vote

### Question: Is consolidation or modification of proposals considered a new proposal

### Consolidation of existing proposals is considered harmonization, and is not a new proposal.

### Modification of proposal to address feedback is not considered new proposal

### Shubhranshu and Lily will revise item 8 in slide 6

## Down-selection process is detailed in slides 7 and 8

### Authors provide Draft Text for review two weeks prior to presentation

### Written questions for clarifications to be submitted to groups one week in advance

#### Answers to these questions submitted within 3 days thereafter

### A technical motion to approve Draft Text provided by the proposal and make it part of the IEEE 802.21a draft specification is brought forward to the Task Group at presentation time

### A proposal containing multiple components can  lead to multiple motions

### Authors must indicate at presentation time how many motions they intend to bring forward to the working group

### All motions are carried out at the end of all presentations

### Time allocated for motions is advertised in the opening meeting of each session

### A technical motion at Down-Selection requires 75% to pass

### One member can vote on multiple motions

### In case no motion passes by 75%, the proposal receiving the most number of votes is selected for another round of confirmation vote by the Working Group

#### More than one proposal can be selected at this stage in case the most popular proposal does not cover all work items specified in the CFP

#### Proposals are selected in decreasing order of popularity (# votes) received

#### If this confirmation vote fails, Proposal(s) are broken up into several technical items and WG votes on each technical item

### In case multiple proposals are approved by more than 75% they are integrated into the Draft Text

#### Proposers work with the Editing Committee which consists of the Editor and the TG Chair in order to combine proposals

#### Conflict and overlaps are brought back to the WG to vote on

#### Failed proposals are eliminated from further consideration

### In case no proposal is approved at the end of Down-Selection, the Task Group may need to regroup. The options include (1) refining the requirements document, (2) refining the evaluation and down-selection criteria, (3) reissuing a new call for proposals

## Presentation rule (slide 10)

### 1. Presentation order is random as determined by the Chair

### 2. Time allocated to each presentation is evenly distributed among all presentations

### Comments and discussion:

#### Different (competing) presentations on same item may be grouped together

#### Presentations may be ordered according to order of work items

#### Proposals on same item may be in the same group but may be randomized within the group.

#### Comment: presentation on more items/functionalities take more time than presentation on fewer items/functionalities

#### Presentations will be in following 3 categories: Work item 1, work item 2, combined work items (cannot separate into work item 1 and work item 2)

#### Comment: Need guidelines such as whether proposal is a modification of 802.21. Lily will draft such guidelines before next teleconference and upload to enable people to comment.

#### It is desirable to check with people in March meeting to express their interest/intention to submit proposal.

#### Need enough timeslots to accomodate the proposals.

### Slide 10 will be revised according to above discussions

## March meeting:

### Call for proposal will be discussed again and then be frozen at the March meeting.

### Preliminary proposals to present in March are welcome.

### 802.21a TG meetings will take a few timeslots of the 802.21 meeting. Parallel sessions are not planned but may be arranged in future if such needs arise.

### Call for proposal will be made for March meeting

## Summary of Action items

### Shubhranshu will send details of Slide 6 item 8

### Lily will submit draft on proposal guideline

## Next teleconference: February 25

### Lily will not be available on February 25, but attempt to find a different date to accommodate her was not successful.

## Adjourn at 11:22AM EST

## Attendees

| Yoshihiro Ohba | Toshiba |
| --- | --- |
| Ashutosh Dutta | Telcordia |
| H Anthony Chan | Huawei Technologies |
| Lidong Lily Chen | NIST |
| Rafael Marin Lopez | Univ. of Murcia |
| Shubhranshu Singh | Samsung |
| Anirudh Bhatt | Samsung |
| Dapeng Liu | China Mobile |