## Comment Form
Clause Number | Starting Page Number | Starting Line Number | Figure or Table Number (if applicable) | Comment Type (Editorial (E) or Technical (T)) (Note: Technical Comments require suggested Remedy) | Comment Details | Suggested Remedy | Commenter | Resolution (suggested) | Remarks
0.all | 0 |  |  | E | There are still "Information Repository" in figures such as Figure Q.2 and Figure Q.3. "Information Repository" needs to be changed into "Information Server." | Please update figures that include "Information Repository." Hyunho Park will help update for the figures. | Hyunho | accept | corrected Figures Q.2, Q.3, S.1, S.2, S.3 | done
0.all | 0 |  |  | E | Consistency check,it should be an MIHF, an MN | Correct it | Antonio | accept |  | done-CEP
1.4 | 2 | 12 |  | E | "used to support data transfer" --> "carry data" |  | Charles | accept with modification | used to carry data | done
3 | 2 | 20 |  | E | In IEEE 802.21-2008 standard, all definitions in clause 3 are written as small letter. For example, in IEEE 802.21-2008 standard, "3.1 candidate point of attachment (candidate PoA)" also is comprised of small letters. | Please change capital letters in clause 3 into small letters. | Hyunho | accept |  | done
1.4 | 3 | 1 |  | E | "for mobility signaling between" --> "to" |  | Charles | accept |  | done
1.4 | 3 | 4 |  | E | "for mobility signaling between" --> "to" |  | Charles | accept |  | done
1.4 | 3 | 8 |  | E | "on only one radio" --> "over only one radio link" |  | Charles | accept |  | done
4 | 3 | 21 |  | E | Abbreviation ANDSF stands for "Access Network Discovery and Selection Function" instead of "Functions" | change "functions" to "Function" | Dapeng | accept |  | done
4 | 3 | 24 |  | E | delete definition for MIHF |  | Charles | accept |  | done
4 | 3 | 25 |  | E | delete definition for MIH_SAP |  | Charles | accept |  | done
4 | 3 | 26 |  | E | delete definition for MIH_LINK_SAP |  | Charles | accept |  | done
4 | 3 | 27 |  | E | delete definition for MN |  | Charles | accept |  | done
4 | 3 | 29 |  | E | delete definition for PoS |  | Charles | accept |  | done
5.1.11 | 5 | 4 |  | E | Suggest to reorder the references | 3GPP, 3GPP2 and WiMAX Forum, 3GPP2. | Subir | accept |  | done
5.1.11 | 5 | 7 |  | E | "However, they have been typically quite time consuming because of reliance on distant authentication agents." This sentence stinks. What is "they"? | "However, authentication has been typically quite time consuming because of reliance on distant authentication agents."? | Clint | accept |  | done
5.1.11 | 5 | 10 |  | E | Add section before 10.3 | See Section 10.3 | Subir | reject | In style manual, clause is used in Clause 10, but subclause is omitted in 10.3 | reject
5.2.3 | 5 | 19 |  | E | Missing ":" at the end of phrase. | Place ":" at the end of phrase. | Daniel | accept |  | done
5.4.4 | 5 | 29 |  | E | "exchanges" --> "may exchange" NOTE: SRHO should still allow for 802.21-2008 (i.e., not layer-2) signaling. |  | Charles | accept |  | done
5.8 | 7 | 5 |  | E | "different" --> "various" <occurs elsewhere> -- <if "different", must also say different than *what*> |  | Charles | accept |  | done
5.8 | 7 | 9 | 11a | E | mobile node has a blue screen <must be a Microsoft product> |  | Charles | accept |  | done
5.8 | 7 | 12 |  | E | Missing "the" in the phrase: "enables MN" | Correct phrase to "enables the MN" | Daniel | accept |  | done
5.8 | 7 | 23 |  | E | Missing ":" at the end of phrase. | Place ":" at the end of phrase. | Daniel | accept |  | done
5.9.1 | 8 | 21 |  | E | "bridge" --> "intermediate" |  | Charles | accept |  | done
5.9.1 | 8 | 29 |  | E | delete "Proxy services may be located at a border router of the network." |  | Charles | accept |  | done
5.9.1 | 9 | 8 |  | E | What is the definition of distributed mobility management? | Add definition or reference of "distributed mobility management" | Dapeng | accept | delete this paragraph and insert after the 3GPP2 paragraph "In network employing centralized or distributed mobility management architecture, the proxy services may be collocated within the mobility management anchors. " Also add reference [B9] Internet Draft (draft-ietf-dmm-requirements-05 (June 2013), Requirements for Distriuted Mobility management." | done-CEP
5.9.1 | 9 | 11 |  | E | Use of 'may then be shown in Figure 10a' is not clear | Revise it or delete this part of the sentence. | Subir | accept | Change to "The distributed mobility management architecture may then be represented in Figure 10a in which the Information Server contains the logical function of location management information and the proxy PoA contains the logical function of mobility routing." | see comment #77 re: definition of distributed mobility management
5.9.1 | 9 | 5-6 |  | E | The sentence "Control signals between the MN and the proxy service are implemented in a media independent manner using the functions of, respectively, the originating network PoS and target network PoS and the signaling messages defined in this specification." is not clear. Do we mean specified instead of implemented? Also we should use respectively at the end. | Revise it. | Subir | accept | "Signaling between the MN and the proxy service may be accomplished in a media independent manner using the functions of the originating network PoS, and the target network PoS and the signaling messages defined in this specification." | done
5.9.2 | 9 | 19 |  | E | Missing "a" in the phrase "use different radio technology" | Correct phrase to "use a different radio technology" | Daniel | accept |  | done
5.9.2 | 9 | 22 |  | E | "sends query" --> "sends a query" |  | Charles | accept | line 38 | done
5.9.2 | 9 | 31 |  | E | "This step is out of scope." I assume this is OMA-DM for 3GPP ANDSF. Perhaps some examples should be included here. |  | Farrokh | superceded by #71 | ANDSF is added in the revised text | done
5.9.2 | 10 | 1 | 11b | E | bad font in cloud |  | Charles | accept |  | done
5.9.2 | 10 | 1 | 11b | E | "requst" --> "request" |  | Charles | accept |  | done
5.9.2 | 10 | 3 |  | E | "Use cases and extension" -- what does "extension" mean? |  | Charles | accept | delete "and extension" | done-CEP
5.9.3 | 10 | 5 |  | E | delete "eventually". Sentence should perhaps begin with "Suppose"…? |  | Charles | accept | Refer to 21-13-0133-00. | done-CEP
5.9.3 | 10 | 6 |  | E | "performing network access procedure" --> "performing a network access procedure" |  | Charles | accept |  | done
5.9.3 | 11 | 10 | 11d | E | font should match other figures. Lines too bold, distracting |  | Charles | accept |  | done
5.9.3 | 11 |  | 11d | E | Figure seems to be much bigger than the rest | Make it the same format as 11c, for example | Antonio | superceded by comment #37 |  | superceded
5.9.3 | 12 | 15 |  | E | "indicating whether the L2 handover is successful." --- is incorrect, if these are preregistration procedures |  | Charles |  | change "handover" to "preregistration signaling" | done
7.4.29 | 19 | 4 |  | E | Missing "the" in the phrase: "running on MN" | Correct phrase to "running on the MN" | Daniel | accept |  | done
7.4.29 | 20 | 1 |  | E | There is Annex A in the first row of the parameter table | Remove it | Antonio | superceded by comment #43 |  | superceded
7.4.29.1 | 20 | 0 |  | E | There is a "Annex A" artifact in the table | Remove "Annex A" | Daniel | superceded by comment #43 |  | superceded
7.4.29.1.2 | 20 | 1 |  | E | "Annex A" in the parameter name. | Delete "Annex A" in the parameter name. | Yoshi | accept |  | done
7.4.29.1.2 | 20 | 1 | Parameter Table | E | What is 'Annex A' in CiphersuiteCode | Delete 'Annex A'. | Subir | superceded by comment #43 |  | done
7.4.29.1.2 | 20 | 1 |  | E | "Annex" should not appear preceding the parameter name "CiphersuiteCode" |  | Charles | superceded by comment #43 |  | superceded
7.4.29.1.3 | 20 | 4 |  | E | In some other places OPoS is called as 'Local PoS' and here it is called serving PoS. | Be consistent and use only one definition. | Subir | accept | serving PoS | done-CEP
7.4.29.1.3 | 20 | 8-9 |  | E | Is it referring to a TPoA or more than one TPoAs. If one use 'a' or 'the' PoA or else use 'TPoAs'. Note: If it is more than one 'TPoA' make sure that the parameters are sufficiently defined to carry more than one L2 frames. | Correct it. | Subir | accept | a TPoA | done-CEP
7.4.29.2.4 | 21 | 7 |  | E | Missing "the" in "primitive for TPoS." | Correct phrase to "primitive for the TPoS." | Daniel | accept |  | done
7.4.29.3.2 | 21 | 1 |  | E | Parameter table has inadequate spacing preceding table cell text <this error occurs in other tables within the document> |  | Charles | accept |  | done-CEP
7.4.29.4.2 | 22 | 24 |  | E | )' is in some cases shown in a separate line and in some cases it is not | Be consistent. | Subir | accept | new line | done-CEP
7.4.29.4.3 | 23 | 5 |  | E | K' should be italicized <this error also occurs elsewhere in the document> |  | Charles | accept |  | done
7.4.30.1.2 | 23 | 28 |  | E | Remove "," after last parameter |  | Daniel | accept |  | done
7.4.30.2.2 | 24 | 22 |  | E | Remove "," after last parameter |  | Daniel | accept |  | done
7.4.30.4.2 | 26 | 20 |  | E | Redundant footnote should be deleted, cite footnote 7 in both cases. |  | Charles | accept with modification | All the 8 footnotes belong to the table, and are numbered with letter in each table | done-CEP
7.4.32 | 28 | 18 |  | E | "The primitives defined in 7.4.33" --> "The primitives defined in clause 7.4.33". The word "clause" is similarly missing elsewhere in the document. |  | Charles | reject | I think this is according to the Std manual | reject
8.6.3.24 | 32 | 12 |  | E | Is reference to 7.4.30.1 correct? Note: Please check all references. This seems to be a major problem with the specification. | Correct them. | Subir | accept |  | done-CEP
10.4 | 39 | 1 |  | E | Missing "a" in the phrase "to enable wider" | Correct phrase to "to enable a wider" | Daniel | accept |  | done
10.5 | 40 | 23 |  | E | This paragraph needs to be removed or changed since it refers to details that will be specified "in later revisions of this document". Is this some kind of ongoing work? |  | Daniel | accept | Changed to "is outside the scope of this document" | done-CEP
R.1 | 55 | 34 |  | E | Instead of "decrease" it should be "decreases" |  | Daniel | accept |  | done
R.2 | 56 | 14 |  | E | "InformationServer" needs to have a space between both words |  | Daniel | accept |  | done
S | 59 |  |  | E | Figure numbers in Annex S are incorrectly written as Figure R.1, etc. | Correct figure numbers. | Yoshi | superceded by comment #43 | Auto-numbering corrected to Annex R after fixing comment #2 | superceded
S | 63 | 1 | S.3 | E | "Information Repository" in Figure S.3(a) should be changed to "Information Server". | Change "Information Repository" in Figure S.3(a) to "Information Server". | Yoshi | superceded by comment #5 |  | superceded
T | 63 | 1 | S.3 | E | "Other Information Server" in Figure S.3(b) should be changed to "Information Server". | Change "Other Information Server" in Figure S.3(b) to "Information Server". | Yoshi | accept |  | done
T | 63 | 1 | S.3 | E | "OPoS/Proxy IR" in Figure S.3(b) should be changed to "OPoS/Proxy Information Server". | Change "OPoS/Proxy IR" in Figure S.3(b) to "OPoS/Proxy Information Server". | Yoshi | superceded by comment #5 |  | superceded
T | 63 |  |  | E | Figure numbers in Annex T are incorrectly written as Figure S.1, etc. | Correct figure numbers. | Yoshi | superceded by comment #43 | Auto-numbering corrected to Annex S after fixing comment #2 | superceded
3 | 3 | 2 |  | T | How will the MN identity whether the Information server is a virtual or not? Either define the how part or delete the 'virtual'. It should be just like another Information Server. | Delete "To the MN the Proxy Information server appears to be an virtual Information Server of the originating network." | Subir | accept with modification | Change definition to "proxy Information Server: A Server that can assist the mobile node to obtain the required information when a query is made via the originating network. To the MN, the proxy Information Server appears to be an Information Server of the originating network." | Done-Anthony
3 | 3 | 5 |  | T | How will the MN identity whether the PoA is a virtual or not? Either define the how part or delete the 'virtual'. It should be just like another PoA | Delete "To the MN, the proxy PoA appears to be a virtual point of 5 attachment (PoA) in the target network. It enables such services as preregistration of the MN." | Subir | accept with modification | Change definition of proxy PoA to "An entity that provides service to a mobile node and a target point of attachment via the originating network. To the MN, this entity appears to be a point of attachment (PoA) in the target network. It enables such services as preregistration of the MN. " | Done-Anthony
5.8 | 7 |  | 11a | T | What is the purpose of Target Radio in the figure after step b? Does it mean that the Target Radio is on at this point? | Delete the 'Target radio' | Subir | accept | source radio line for the whole column | Done-Anthony
5.9.1 | 8 | 33 |  | T | If the information is consumed at the proxy Information Server, why the control frames need to be tunneled? | Discuss | Subir |  | delete paragraph. They are already explained in 5.9.2 and 5.9.3 | done-CEP
5.9.1 | 9 | 10 |  | T | Which 'Proxy' is referred here? Is it Proxy Information Server or Proxy PoA? | Discuss | Subir | accept | proxy PoA | done
5.9.2 | 9 | 15 |  | T | The MIHF cannot provide translation services for different protocols, this can be done using an MIH user | 21-13-0114-00-srho | Antonio | accept |  | done-Hyunho
5.9.2 | 9 | 34 |  | T | Shouldn't this be a MIH_CTRL_Transfer response message? |  | Daniel | superceded by #71 |  | done-Hyunho
5.9.2 | 9 | 14 |  | T | This whole section needs to be revised. Not clear what use cases are we referring here? Are we expecting the Proxy Information server do the protocol message translation? If so did we define these anywhere. Do not understand how this will work. Also I wondering if the title of the section should be "Network Discovery using Proxy Information Server' | Discuss. I can provide a contribution if I understand the use case. | Subir | accept | refer to 21-13-0114. Also change title as suggested. | done
5.9.2 | 10 | 1 | 11b | T | In message f) shouldn't this be a response? |  | Daniel | superceded by #75 |  | done-Hyunho
5.9.2 | 10 | 1 | 11b | T | Redo figure 11b following previous comment | redraw | Antonio | accept |  | done-Hyunho
5.9.3 | 10 | 4 |  | T | It seems that the title of this section does not convey the proper intent. | Change it to "Preregistartion using Proxy PoA" | Subir | accept |  | done
5.9.3 | 10 | 8-9 | 11d | T | The assumption that TPOA will have always TCP/IP stack for legacy devices may not be correct. Legacy TPOA (for example, Wi-Fi AP) may not have TCP/IP stack. At least they do not process TCP/IP packets (e.g., for split MAC model). For example, many Wi-Fi deployment today, AP forwards the L2 frames and a concentrator or first of router process the TCP/IP packets. | Modify the figure and change the description. | Subir | accept | Refer to 21-13-0133-00. Use the protocol stack figure in 21-13-0126-01 | done-CEP
5.9.3 | 11 |  | 11c | T | The TPOS/proxy PoA layering seems to be not correct. To me TPOS is a network entity (could be a server) and may use wired Ethernet or some other lower layers to communicate. Why are we saying that this is the same L2 that MN has? What is purpose of PHY(2) in SRHO Capable TPOA? What is the assumption here? TPOA should have only one PHY and it is L2. | Update the figure and corresponding text. Delete PHY(2) from TPOA. Also discuss. | Subir | accept | Refer to 21-13-0133-00. Use the protocol stack figure in 21-13-0126-01 | done-CEP
5.9.3 | 11 |  | 11d | T | The TPOS/proxy PoA layering seems to be not correct. To me TPOS is a network entity (could be a server) and may use wired Ethernet or some other lower layers to communicate. Why are we saying that this is the same L2 that MN has? | Update the figure and corresponding text. Also discuss. | Subir | accept | Refer to 21-13-0133-00. Use the protocol stack figure in 21-13-0126-01 | done-CEP
6.4.3.21.1 | 13 |  | Table 7 | T | The section cross references are not correct. For example, MIH_Prereg_Xfer is described in 7.4.29 | Correct them | Subir |  | cross reference to 7.4.29 | done-CEP
6.5.4 | 14 | 9 |  | T | It should be 'PoS information elements include …' | Replace 'PoS information includes' with 'PoS information elements include' | Subir | accept with modification | The PoS sends information elements that include … | Done-Anthony?
6.5.4 | 14 | 10 |  | T | It says: " The MN information includes location information of the MN' ; which information element does contain this? | Be specific and mention the name of the information element. If none is defined in this specification, delete this sentence. | Subir |  | Correct editor instruction to: Insert following text after item b. "The Information Server provides access to the Point of Service information, the Mobile Node information and the capability for supporting SRHO for each of the available access networks. The PoS sends information elements that includes PoS addressing information and tunnel management protocol information." | done-CEP
7.2.2.2 | 15 |  | Table 16 | T | Check the cross reference. It should be 7.4.30; Note: Make sure all other references are correct the subsequent table(s) (e.g., Table 17 and so on) | Correct it. | Subir | accept |  | done-CEP
7.3.15.1.4 | 17 | 6 |  | T | on behalf is PHY of the target link' is confusing. | Replace the sentence with "The L2 messages are transferred to the MIHF for preregistration preparation with the target link layer." | Subir | accept |  | done-CEP
7.4.29 | 19 | 7-8 |  | T | The sentence "Such layer-2 ….by the mobile node or the target network…" is not clear. In particular is it 'or the target network' or 'to the target network'? | Discuss and correct it. | Subir | accept with modification | change "or" to "or by", i.e., "or by the target network" | done-CEP
7.4.29.1.2 | 19 | Parameters table |  | T | CipherSuite should be defined, in .21a and .21d we have a table with ciphersuites, I think here they should have the same one. | Add it | Antonio | accept | reference to table 25 in 21a | done-CEP
7.4.29.4.2 | 22 | 22 |  | T | It would be if we can name this parameter instead of just 'k'. All other parameters are defined as names. | Discuss or just add a name such as 'KeyDerKey' | Subir | reject | The name 'K' reflects earlier usage | done
7.4.30 | 23 | 12 |  | T | Is the reference 7.4.31 correct here? Also it seems that the reference to Annex N is not correct. There is no such example in Annex N | Correct them. | Subir | accept with modification | Change to defined in "this subclause" . Annex N is Annex O, which is superceded by #2; | done-CEP
7.4.30.1.3 | 24 | 6 |  | T | I assume by 'MIHF first produces' means 'MIHF of OPoS first produces' but this may not be obvious to others. | Add 'MIHF of OPoS first produces'… | Subir | accept |  | done-CEP
7.4.30.1.3 | 24 | 4-5 |  | T | It is difficult to parse this sentence with so many 'possibly'. Would suggest to rephrase it. | Revise it. | Subir | accept | Change to "OPoS may do this to relay link-layer frames, or to establish a security association derived from key derivation key K. " | done-CEP
7.4.30.2.4 | 25 | 7 |  | T | Is 'target AAA' correct? Are we defining any method for this? If nor why do we mention this? | Discuss | Subir | accept | delete ", installing keys as necessary in the target AAA" | done-CEP
7.4.30.4.4 | 27 | 4 |  | T | I assume by 'The TPoS also' means 'The TPoS MIHF'. Is this correct? | If it is correct, pl. change the sentence as : "The OPoS MIHF retrieves its …", If not discuss. It then again adds multiple requests in remote MIHF. By receiving one request it can generate multiple requests. | Subir | accept |  | done-CEP
7.4.31.1.2 | 27 | 19 |  | T | MIH_PreReg_Ready.request primitive needs to contain link type to prepare preregistration, but it does not have the link type. | Insert link type into MIH_PreReg_Ready.request. | Hyeong | accept with modification | refer to 21-13-0116-01. Also delete Execution Delay. | done-Hyunho
7.4.31.1.4 | 27 | 27 |  | T | Why is it 'lower layer link(s)'? Are we registering for multiple links? If so how? | Discuss or delete '(s)' in all instances. | Subir | accept | remove (s), also correct IF to MIH | done-CEP
7.4.31.2.2 | 28 | 7 |  | T | MIH_PreReg_Ready.confirm primitive needs to contain link type to prepare preregistration, but it does not have the link type. | Insert link type into MIH_PreReg_Ready.confirm. | Hyeong | accept with modification | refer to 21-13-0116-01. | done-Hyunho
7.4.32.1.1 | 28 | 23-24 |  | T | The sentence 'The control messages …' is not clear | Suggest to change as " The control messages are not only MIH specific control messages but may include other control messages, such as ANQP and ANDSF control messages." | Subir | accept |  | done-CEP
7.4.32.3.4 | 30 | 9 |  | T | Why is it 'may generate'? Is it not 'must' or simply 'generates' | Either replace 'may' by simply 'generates' or discuss if it has to be 'may'. | Subir | accept | change "may generate" to "generates" | done-CEP
8.6.3.26 | 33 | 5 |  | T | Here it is mentioned that 'encrypted key derivation key K' and in the message parameter table it is labeled as 'Encrypted K'. Is it really an 'encrypted key k' or the 'key derivation key k' that is used to encrypt other information. Whatever terminology is used, it should be consistent. | Be consistent with the name and discuss. In a previous comment I suggested to label as 'KeyDerKey'. Whatever is chosen it needs to be consistent. | Subir | accept | key derivation key | done-CEP
8.6.3.26 | 33 |  | Parameter Table | T | Several of these parameters are not defined in the corresponding primitve in Section 7.4.30.1.2. For example, K, Nonce values and so on. Am I missing somethng here? Note: This is true for other messages as well, for example, section 8.6.3.35. | Discuss | Subir | accept with modification | The nonce values are generated by MIHF, and not passed as parameters in the primitive. Text added to clarify. | done-CEP
8.6.3.28 | 34 | 5 |  | T | MIH_PreReg_Ready request message needs to contain link type to prepare preregistration, but it does not have the link type. | Insert link type into MIH_PreReg_Ready request message. | Hyeong | accept with modification | refer to 21-13-0116-01. | done-Hyunho
8.6.3.29 | 34 | 9 |  | T | MIH_PreReg_Ready response message needs to contain link type to prepare preregistration, but it does not have the link type. | Insert link type into MIH_PreReg_Ready response message. | Hyeong | accept with modification | refer to 21-13-0116-01. | done-Hyunho
T |  |  |  | T | There is no ANQP Server anywhere defined, in addition, the MIHF cannot perform translation between protocols | 21-13-0114-00-srho | Antonio | accept | change "ANQP" server to "advertising service server" 4.5.9 in 802.11-2010 | done-Hyunho