## Comment Form
Issue # | Document | Clause | Page | Line | Fig./Table | Type: Editorial (E) or Technical (T) | Comment Details | Suggested Remedy | Commentor | Assign to | Resolution | Remarks | Proposed Resolution by Assignee
| 21-14-0121-03-REVP |  |  |  |  | NOTE: first issue is numbered as issue #3 in column A
3 | 802.21-2008 | [5 empty] | abbreviated version of the Table of Contents for the base document | 21-13-0082-01-0000-toc-level-3 |  | accepted | done
4 | 802-21a | [5 empty] | abbreviated ToC for 802-21a | DCN 21-13-0095 |  | accepted | done
5 | 802-21b | [5 empty] | abbreviated ToC for 802-21b | DCN 21-13-0097 |  | accepted | done
6 | All | [5 empty] | Determination of meaning of the following PICS sentence: "The supplier of a protocol implementation that is claimed to conform to IEEE Std 802.21, shall complete the following protocol implementation conformance statement (PICS) proforma." | determine a minimal set of protocol mandates, and create groupings for optional commands |  | needs discussion
7 | All | [5 empty] | Handover services can be considered as service depending on base protocol features | Handover services to be moved to 802.21.1 |  | accepted | 802.21m action done: moved handover services into "excluded" document for further consideration in 802.21.1
8 | [6 empty] | Need to decide whether registration is a different service from pre-registration |  |  | needs discussion
9 | 802.21-2008 | Annex C | 191 |  | C.1 | E | Error in "Mobile initiated handover procedure (continued)" [comment 1(i)] | MIH_N2N_HO_Complete request needs to Stop at PoS-S not MIH user in the serving network | David Cypher | tabled for attention in 802.21.1 |  | Cypher, David E. <david.cypher@nist.gov> Date: Tue, Aug 27, 2013 at 12:09 PM
10 | 802.21-2008 | Annex C | 191 |  | C.1 | E | Error in "Mobile initiated handover procedure (continued)" [comment 1(ii)] | MIH_N2N_HO_Complete indication needs its arrow swapped (i.e., start in PoS-S and end at MIH user in the serving network | David Cypher | tabled for attention in 802.21.1 |  | Cypher, David E. <david.cypher@nist.gov> Date: Tue, Aug 27, 2013 at 12:09 PM
11 | 802.21-2008 | Annex C | 191 |  | C.1 | E | Error in "Mobile initiated handover procedure (continued)" [comment 1(iii)] | MIH_N2N_HO_Complete response needs its arrow swapped (i.e., start in MIH user and end in PoS-S in the serving network | David Cypher | tabled for attention in 802.21.1 |  | Cypher, David E. <david.cypher@nist.gov> Date: Tue, Aug 27, 2013 at 12:09 PM
12 | 802.21-2008 | Annex C | 191 |  | C.1 | E | Error in "Mobile initiated handover procedure (continued)" [comment 1(iv)] | that MIH_N2N_HO_Complete response needs to Start at PoS-S not MIH user in the serving network | David Cypher | tabled for attention in 802.21.1 |  | Cypher, David E. <david.cypher@nist.gov> Date: Tue, Aug 27, 2013 at 12:09 PM
13 | 802.21-2008 | xxx | nnn |  |  | E | A variable appears in the text but is not defined [comment 2] | comment incomplete | David Cypher | not understood | todo: ask David Cypher for details | Cypher, David E. <david.cypher@nist.gov> Date: Tue, Aug 27, 2013 at 12:09 PM
14 | All |  |  |  |  | E | MIH appllication is called "user", which is often misleading. | Replace "user" with "application" whenever appropriate. For instance, change "MIH user" to "MIH application". | Charlie Perkins | accepted | done (except with MIS instead of MIH)
14 | All |  |  |  |  | E | MIH is no longer appropriate, since 'H' stands for "Handover". | Change "MIH" to "MIS", where 'S' stands for "Services". | Charlie Perkins | accepted | done
16 | 802.21-2008 |  |  |  |  | T | Disposition of text related to handover… | Submit to 802.21.1 after update. | Charlie Perkins | accepted | See comment #7
17 | 802.21-2008 | 8.2.2 | 27 | 21 |  | E | delete "for" after "request" |  | Charlie Perkins | accepted | done
18 | 802.21-2008 | 8.2.3.4 | 28 | 12 |  | E | What are "power save mobile nodes." Why are others excluded? |  | Charlie Perkins | accepted | Replaced with "that may be sleeping"
19 | 802.21-2008 | 7.4.14.1.3 | 9 | 17 |  | E | Missing a number of “When Generated” text. We need them before SB. |  | Farrokh Khatibi | accepted
20 | 802.21a | 8.4.1a | 34 |  |  | E | Renumber this and all following sections |  | Charlie Perkins | accepted | done
21 | 802.21a | 8.4.2.1 | 36 |  |  | E | Figure 29a has to be redrawn |  | Charlie Perkins | accepted
22 | 802.21a | F.3.16 | 71 |  |  | E | Coalesce two parts of table F.24 |  | Charlie Perkins | accepted | done
23 | 802.21a | F.3.16 | 71 |  |  | E | Use label "Table" for the tables in section |  | Charlie Perkins | accepted
24 | 802.21a | M |  |  |  | T | Fix PICS |  | Charlie Perkins | accepted
25 | 802.21-2008 |  | 2 |  |  | E | What is the title of the document? MI Handover Services or MI Services? | MI Services Framework | Charlie Perkins | accepted | done
26 | 802.21b | 6.4.2 | 11 |  |  | E | There is no such paragraph as described | Inserted all text as shown… | Charlie Perkins | accepted | done; text seems intended to be included in section 6.4.1, not 6.4.2.
27 | 802.21b | 6.4.2 | 11 |  |  | E | No figure provided in Word document | Must find how to recreate figures | Charlie Perkins | accepted | done, but errors persist
28 | 802.21 | Definitions |  |  |  |  | Need to change "handover" to "services", not just well as MIH to MIS. |  | Jin Seek | accepted | done
29 | 802.21 |  |  |  |  | E | Instances of "mobile node" to be replaced by "MN". |  | Farrokh Khatibi | accepted | done
30 | 802.21a | Parameter lists |  |  |  | E | Find out about Word "Keep Together" |  |  | accepted | done
31 | 802.21 | Acronyms |  |  |  | E | Move MN back into "include" document |  | Jin Seek | accepted | done
32 | [5 empty] | E |  | Remove Space before Paragraph | Subir Das | accepted | done
33 | All | Figures |  |  |  | E | Transform figure descriptions into Microsoft Word *captions* |  | Charlie Perkins | accepted | Problem with enabling IEEE macros
34 | 802.21m | 7.1 | 58 |  |  | E | Itemized list is not consistent |  | Michelle Turner | accepted | done
35 | 802.21m | F.3.16 | 221 |  |  | E | Should this be Table F.24? |  | Michelle Turner | accepted | done
36 | 802.21m | K.2 | 258 |  |  | E | Figure is incorrectly drawn |  | Michelle Turner | accepted | done
37 | 802.21m | K.2 | 257 |  |  | E | exeeds |  | Charlie Perkins | accepted | done
38 | 802.21m | K.2 | 257 |  |  | E | Ptotection |  | Charlie Perkins | accepted | done
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57