## Title
IEEE P802.22 Wireless RANs
Submission
Designator: | doc.: IEEE 802.22-07/0086r1
Venue Date: | March 2007
First Author: | Edward Au, Huawei Technologies / HKUST
Subject: | Summary of Comments and Resolutions discussed in London
Full Date: | 2007-03-29
Author(s): | Name(s) | Edward K. S. Au
| Company | Huawei Technologies Co. Ltd., Hong Kong University of Science and Technology
| Address | Department of ECE, HKUST, Clear Water Bay, Hong Kong SAR
| Phone: | 852-2358-7086
| Fax: | 852-2358-1485
| email: | ks.au@ieee.org
Abstract:
Notice: This document has been prepared to assist IEEE 802.22. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.22.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures
<http://standards.ieee.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <carl.stevenson@ieee.org> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.22 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.
This spreadsheet contains four tables listing the comments and resolutions that are (1) discussed and classified; and (2) unclassified in London interim, January 2007. They are classified as (1) MAC (mostly Section 6 of P802-22_D0.2); (2) Security (Section 7); (3) PHY (mostly Section 8); (4) Others (other sections) according to the contents and/or the section numbers. The intent of the document is to provide a consolidated listing to assist WG members in the subsequent discussion.
Notice: This document has been prepared to assist IEEE 802.22. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.22.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures
<http://standards.ieee.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <carl.stevenson@ieee.org> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.22 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## MAC
Acceptecd
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
11 | 39 | Gerald CHOUINARD | Carlos Cordeiro | TR | 6.4 | Assign to Carlos | need materials | ready, accepted
12 | 39 | Gerald CHOUINARD |  | TR | 6.4 | Delete "possible contention intervals for coexistence with purposes" (Line 4, Page 11). Change the sentences in Lines 8 - 9 as "of fixed size (MAC) slots, which are, in turn, an integral number of modulation symbols and sub-channels (currently, 1 MAC slo | need action
14 | 40 | Gerald CHOUINARD |  | TR | 6.4 | Change the sentence in Line 5 as follows: "together with coexistence beacons (i.e., through CBP) shall be employed. The SSS window (depicted in Figure 4) is scheduled at the end of the upstream subframe for simpler multiplexing and to accommodate simpler | need action
15 | 40 | Gerald CHOUINARD |  | TR | 6.4 | Change the sentence in Line 15 as "Whenever a CPE is neither receiving nor sending data to its BS, it is capable of decoding CBP packets transmitted by nearby stations belonging to other BSs operating on the same TV channel, and/or performing out-of-band | need action
18 | 42 | Gerald CHOUINARD | Dave Cavalcanti | TR | 6.5.2 | Defer Green until Gereld's clarification about the increase in addressing size and the QPSK rate | need assignment | accepted
21 | 44 | Gerald CHOUINARD | Carlos Cordeiro | TR | 6.8.1.1 | Assign to Carlos. Defer (Green) sensing RTG until submission (quiet periods?). Table 26: Change the word "slots" to "by 8 samples increment" for both TTG and RTG. Delete the Frame Duration Code. Explanation is given for the comments on "repetition period | need materials | ready, accepted
22 | 44 | Gerald CHOUINARD |  | TR | 6.8.1.1.1 |  | need action
36 | 16 | Gerald CHOUINARD |  | TR | 6.21.1.4.1 |  | need action
37 | 17 | Gerald CHOUINARD |  | TR | 6.21.1.4.2 |  | need action
39 | 20 | Gerald CHOUINARD | Ko | TR | 6.21.1.5.1 | Assign to Ko | need materials | ready, accepted
40 | 21 | Gerald CHOUINARD |  | TR | 6.21.2 | Delete "although this may be implementation dependent" in P+F4+F663age 155 Line 17 | need action
41 | 26 | Gerald CHOUINARD |  | TR | 6.21.2.1 | Change "Several mechanisms are implemented on top of CBP" (Page 156, Line 14) to "There are several optional mechanisms that are implemented on top of CBP in the annex" | need action
46 | 33 | Gerald CHOUINARD |  | TR | 6.21.3.2.1 | [1] Scheduling Issues. [2] Sensing Architecture Issues. | need discussion | discussed, accepted.
49 | 36 | Gerald CHOUINARD |  | TR | 6.21.5.1 | Replace "NSTQP" by "NSIQP" | need action
53 | 35 | Baowei JI |  | TR | 6.21.5 | Defer Green. New Topic | need discussion | accepted
62 | 47 | Soo-Young CHANG |  | TR | 6.8.2 |  | need action
87 | 39 | Carlos CORDEIRO | Carlos Cordeiro | TR | 6.4 | Carlos to insert new figure | need materials | ready, accepted
88 | 47 | Carlos CORDEIRO |  | TR | 6.8.2 | Table 30 Message should be an integer number of bytes, Delete Padding Nibble of 4 bits | need assignment | actionable
89 | 47 | Carlos CORDEIRO |  | TR | 6.8.2 |  | accepted
90 | 47 | Carlos CORDEIRO |  | TR | 6.8.2 |  | accepted
94 | 30 | Carlos CORDEIRO |  | TR | 6.21.3.2 |  | need action
100 | 26 | Carlos CORDEIRO | Carlos and Wendong | TR | 6.21.2.3 | Assign to Carlos and Wendong | need materials | ready, accepted
107 | 19 | Carlos CORDEIRO | Ko | TR | 6.21.1.5.1 | Assign to Ko | need materials | ready, accepted
120 | 53 | Liwen CHU |  | T | Table 21 |  | accepted
126 | 34 | Liwen CHU | Carlos Cordeiro | TR | 6.21.4 | Defer Green. Clarify is broadcasting in explicit channel mode equivalent to embedded channel mode? | need assignment | ready, accepted
127 | 34 | Liwen CHU | Carlos Cordeiro | T | 6.21.4.2 | Defer Green. Assign to Ko to clarify the discrepancy between the text and Figure 6.1 for transition 1 | need assignment | ready, accepted
128 | 34 | Liwen CHU | Ko | T | 6.21.4.2 | Assign to Ko | need materials | ready, accepted
129 | 37 | Liwen CHU |  | TR | 6.21.6.2 | Change "shall" by "may" in Page 176, Line 1. Insert "For example" in front of the first sentence in Page 176, Line 1. | need action
134 | 14 | Liwen CHU |  | T | 6.15.5.1 | Move the texts (Page 125, lines 14 - 15) regarding Multiple Channel Support to A.1 | need action
154 | 48 | Steve SHELLHAMMER |  | T | 6.8.22.1.1 |  | accepted
155 | 48 | Steve SHELLHAMMER |  | T | 6.8.22.3.1 |  | accepted
177 | 38 | Wendong HU | Carlos Cordeiro | TR | 6.4 | Assign to Carlos | need materials | ready, accepted
178 | 38 | Wendong HU | Carlos Cordeiro | TR | 6.4 | Assign to Carlos | need materials | ready, accepted
180 | 43 | Wendong HU | Carlos and Wendong | TR | 6.6.1.2 | Assign to Carlos and Wendong | need materials | ready, accepted
188 | 10 | Wendong HU | Carlos and Wendong | TR | 6.15 | Modify Figure 20 and revise the associated text to illustrate and explain the need for a keepout region extending beyond the protected contour. | need assignment
190 | 12 | Wendong HU | Carlos Cordeiro | TR | 6.15.3 | Assigned to Carlos CORDEIRO | need materials | ready, accepted
191 | 14 | Wendong HU | Wendong and Carlos | TR | 6.21 | Assign to Wendong and Carlos to resolve | need materials | ready, accepted
192 | 15 | Wendong HU |  | TR | 6.21.1.1 | Change the words "have a direct effect" by "experience leakages due to limited IF filtering". Replace "e.g." by "i.e.,". Move the definition of "in-band sensing" and "out-of-band sensing" to the definition section. | need action
193 | 15 | Wendong HU |  | TR | 6.21.1.3 | Change "both TV signals and Part 74 services, according to the DFS model defined in FRD" to "incumbent devices defined in clause 15.1 of the FRD according to the DFS model defined in the same document" | need action
197 | 17 | Wendong HU |  | TR | 6.21.1.4.2.1 | Delete the word "a small amount of" in Line 43, Page 147 | need action
198 | 18 | Wendong HU |  | TR | 6.21.1.4.2.1 | Delete (Page 148, Lines 3 - 7) "In case no other CPES … in order to resolve the issue" | need action
199 | 17 | Wendong HU |  | TR | 6.21.1.4.2 | Change the sentence (Page 147, Line 23) "The quiet period notification phase ends whenever the BS has acquired a reliable picture of the measurement outcome in its cell" to "The quiet period notification phase ends whenever the BS has acquired a picture o | need action
203 | 20 | Wendong HU | Ko | TR | 6.21.1.5.1 | Assign to Ko | need materials | ready, accepted
206 | 21 | Wendong HU | Carlos and Wendong | TR | 6.21.2 | Assign to Carlos and Wendong | need materials | ready, accepted
210 | 25 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | ready, accepted
214 | 23 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | ready, accepted
215 | 23 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | ready, accepted
222 | 27 | Wendong HU |  | TR | 6.21.3 | Change "Not engagled in communication with its BS during normal cell operation" to "possible" | need action
232 | 31 | Wendong HU |  | TR | 6.21.3.2 | Replace "the fine sensing could be over 3 orders of magnitude larger than fast sensing" by "the fine sensing time could be orders of magnitude larger than the fast sensing" | need action
237 | 33 | Wendong HU | Carlos Cordeiro | TR | 6.21.3.2.2 | Assign to Carlos to redraw the figure for single channel operation and move the current figure (Figure 59) to annex | need materials | ready, accepted
239 | 33 | Wendong HU |  | TR | 6.21.4 | Delete the text "(e.g., this can be done through clustering)" in Page 165, Lines 21-22 | need action
240 | 34 | Wendong HU | Ko | TR | 6.21.4.1 | Assign to Ko | need materials | ready, accepted
241 | 34 | Wendong HU | Wen Gao | TR | 6.21.4.3 | Assign to Thomson to address this issue | need materials | ready, accepted
243 | 36 | Wendong HU |  | TR | 6.21.6 | Change "shall" by "may" in Page 176, Line 1. Insert "For example" in front of the first sentence in Page 176, Line 1. Remark: the algorithm refers to "k-means algorithm". | need action
244 | 35 | Wendong HU | Wendong Hu | TR | 6.21.5 | Assign to Wendong to bring the text from 802.16h | need materials | ready, accepted
246 | 20 | Wendong HU |  | TR | 6.21.2 | Defer Salmon until submission | need materials | ready, accepted
333 | 40 | George VLANTIS |  | T | 6.4 | Move this paragraph (beginning at Line 36 of page 11 and ending on Line 2 of Page 12) to Technology Overview Document. | need action
367 | 45 | George VLANTIS |  | TR | 6.8.1.2 | Delete "Offset". In Table 29, element ID 150, bits 3 - 7 should be reserved. Bits 0 - 2 have the following values: 000 = DBTC, 001 = CTC, 010 = LDPC, 011 = SBTC. Bits 3 - 5 have the following values: 000 = Spreading, 001 = reserved, 010 = QPSK, 011 = 16QA | need action
368 | 51 | George VLANTIS |  | TR | 6.8.3.2 |  | accepted.
380 | 4 | George VLANTIS |  | E | 6 | Editor to carefully review because CMAC has two meanings/usages in the document. | need action
381 | 4 | George VLANTIS |  | E | 6 |  | need action
382 | 5 | George VLANTIS |  | E | 6 |  | need action
383 | 5 | George VLANTIS | Gerald CHOUINARD and Dave | E | 6 |  | Accepted
388 | 6 | George VLANTIS |  | T | 6.1.1 | Delete the parenthetical text about directional antennas | need action
511 | 12 | Stephen KUFFNER | Carlos Cordeiro | T | 6.15.3 | Assigned to Carlos CORDEIRO | need materials | ready, accepted
516 | 17 | Stephen KUFFNER |  | T | 6.21.1.4.2.1 | Refer to Comment 198. The sentences (Page 148, Lines 3 - 7) have been deleted. | need action
519 | 19 | Stephen KUFFNER | Carlos Cordeiro for (2) and (3) | T | 6.21.1.5 | Defer Green for point (1) on EIRP profile. Assign (2) and (3) to Carlos | need assignement for (1), need materialsf or (2) and (3) | accepted
524 | 37 | Stephen KUFFNER |  | T | 6.21.6.2 | Change "shall" by "may" in Page 176, Line 1. Insert "For example" in front of the first sentence in Page 176, Line 1. | need action
526 | 38 | Stephen KUFFNER | Carlos Cordeiro | T | 6.4 | Assign to Carlos | need materials | ready, accepted.
528 | 42 | Stephen KUFFNER |  | T | 6.5.1 |  | need action
529 | 42 | Stephen KUFFNER |  | T | 6.5.1 |  | need action
Proposed Accept in Principle
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
26 | 46 | Gerald CHOUINARD | Gerald CHOUINARD | TR | 6.8.15.3.3.2 | Change title to "Maximum Transmit Power and EIRP". The 8-bit values should indicate -64 to +64 dbM in 0.5 dB steps. Manufacturer in the regulatory domain has to guarantee that the EIRP and power constraints are not exceeded in the ideal cabling and antenn | need assignment
27 | 46 | Gerald CHOUINARD | Carlos | TR | 6.8.15.3.3.4.1 | Delete bit 0 = 1K FFT, change to "reserved". Other FFT sizes are only for channel bonding. Assign to Carlos. | need materials | not ready
29 | 49 | Gerald CHOUINARD | Dave | TR | 6.8.22.3.1.6 |  | Accepted in principle
63 | 48 | Soo-Young CHANG |  | TR | 6.8.2 |  | accepted in principle
93 | 28 | Carlos CORDEIRO | MAC ad hoc | TR | 6.21.3 | Defer Green until the discussion on preamble | Pending | Accepted in Principle.
97 | 9 | Carlos CORDEIRO | Wendong Hu (changed in the DB) | TR | 6.15 | Adapt material from corresponding 802.16 section on Network Entry and Initialization, strarting from 6.15.5 onward. Assigned to Carlos CORDEIRO | need materials | not ready
98 | 14 | Carlos CORDEIRO | Carlos Cordeiro | TR | 6.20_ | Assign to Carlos CORDEIRO to recommend 802.16 text | need materials | not ready
111 | 13 | Carlos CORDEIRO | MAC ad hoc | TR | 6.15.3 | Need to be rephrased, related to Comment Number 512 | need assignment | Accepted in Principle.
116 | 53 | Liwen CHU | Dave | TR | Table 1 |  | accepted in principle
119 | 54 | Liwen CHU | Dave | TR | Table 8 |  | Accepted in Principle
153 | 48 | Steve SHELLHAMMER | Wendong Hu | T | 6.8.22.1.1 |  | accepted in principle
157 | 52 | Steve SHELLHAMMER |  | TR | 6.8.7.3.7.9 | refer to CID 513 | accapted in principle
159 | 49 | Steve SHELLHAMMER |  | TR | 6.8.22.3.1.1 |  | accepted in principle pending on sensing.
181 | 52 | Wendong HU |  | TR | 6.8.8.22.1 | refer to CID 63 | accapted in principle
194 | 16 | Wendong HU | Wendong Hu | TR | 6.21.1.4.1 |  | need assignment | accepted in principle pending on sensing.
224 | 28 | Wendong HU | MAC ad hoc | TR | 6.21.3 | See the document 22-05-0105-01-0000 | need discussion | Accepted in Principle.
264 | 10 | Winston CALDWELL | Wendong Hu (changed in the DB) | TR | 6.15 | Adapt material from corresponding 802.16 section on Network Entry and Initialization, strarting from 6.15.5 onward. Assigned to Carlos CORDEIRO | need materials | Accepted in Principle.
265 | 10 | Winston CALDWELL | Wendong Hu (changed in the DB) | TR | 6.15 | Adapt material from corresponding 802.16 section on Network Entry and Initialization, strarting from 6.15.5 onward. Assigned to Carlos CORDEIRO | need materials | not ready
267 | 10 | Winston CALDWELL | Wendong Hu (changed in the DB) | TR | 6.15 | Adapt material from corresponding 802.16 section on Network Entry and Initialization, strarting from 6.15.5 onward. Assigned to Carlos CORDEIRO | need materials | not ready
384 | 5 | George VLANTIS | Gerald CHOUINARD and Dave | E | 6.1.1 |  | Accepted in Principle
507 | 6 | Stephen KUFFNER | Carlos Cordeiro | T | 6.1.1 | Need to create a section on the spectrum manager function. Rewrite section to define mandatory signal channel system and optional channel bonding/aggregation | need assignment
512 | 13 | Stephen KUFFNER | MAC ad hoc | T | 6.15.3 | Need to be rephrased, related to Comment Number 111 | need assignment | Accepted in Principle.
513 | 13 | Stephen KUFFNER | Steve Kuffner? | T | 6.15.5.1 | Factor linking EIRP to Maximum Transmit Power needs to be known by the MAC. Professional installation should not be forced. Because the antenna gain and cable losses should be set by the manufactorers to not exceed the limit. | need assignment for rewriting the text | tentatively assigned to steve kuffner, need comfirmation from steve
517 | 18 | Stephen KUFFNER | Carlos and Wendong | T | 6.21.1.4.2.2.2 | Assigned to Carlos and Wendong | need materials | ready
518 | 19 | Stephen KUFFNER | Carlos Cordeiro | T | 6.21.1.5 | Assigned to Carlos CORDEIRO | need materials | ready
522 | 28 | Stephen KUFFNER |  | T | 6.21.3 | If quiet period is not an integer number of antennas, a partial frame is used | need assignment | pending for sensing input
525 | 37 | Stephen KUFFNER |  | T | 6.3 | Suggested Remedy: A fixed number of frames, not to mention the number | need materials | change to "16" need to confirm with steve.
531 | 46 | Stephen KUFFNER | George Vlantis | T | 6.8.15.3.3.4.2 | In Table 125, bits 3 - 7 should be reserved. Bits 0 - 2 have the following values: 000 = DBTC, 001 = CTC, 010 = LDPC, 011 = SBTC. Values 4 - 7 are reserved. In Table 126, bits 0 - 1: reserved, the other bits remain unchanged. | need assignment
532 | 47 | Stephen KUFFNER |  | T | 6.18.15.3.3.4.4 | In Table 127, bits 0 - 1 should be reserved. | need assignment | pending for phy ad hoc (will AMC be supported?)
Pending for WG's discussion
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
25 | 51 | Gerald CHOUINARD |  | TR | 6.8.4.1.2.1 |  | defer (green) for the WG discussion
184 | 49 | Wendong HU |  | TR | 6.8.25 |  | Need discusion | Pending for WG's discussion
480 | 52 | Stephen KUFFNER |  | TR | 6.8.7.3.7.10 |  | defer (green) for the WG discussion
523 | 32 | Stephen KUFFNER |  | T | 6.21.3.2.1 | Refer this issue to WG | need discussion
Defer Until Clarification
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
50 | 36 | Gerald CHOUINARD | Gerald CHOUINARD | TR | 6.21.5.3 | Defer (Green) until Gerald's clarification on 7 slots | need assignment
121 | 53 | Liwen CHU |  | T | Table 25 | refer to 122 | defer for clarification
122 | 54 | Liwen CHU | Dave | T | Table 30 |  | defer for clarification
123 | 54 | Liwen CHU |  | T | Table 37 | refer to 122 | defer for clarification
124 | 53 | Liwen CHU | Liwen Chu | TR | Figure 41 |  | deferrd for clarification
135 | 53 | Liwen CHU | Dave | T | Table 162 |  | defer for clarification
481 | 52 | Stephen KUFFNER | Dave | T | 6.8.8.10.13 |  | defer (green) for clarification
482 | 52 | Stephen KUFFNER | Dave | T | 6.8.8.10.14 | refer to 481 | defer (green) for clarification
Defer / Pending
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
4 | 5 | Gerald CHOUINARD | Gerald CHOUINARD and Dave | TR | 6 | Changed from "ER" to "TR" | assigned
24 | 51 | Gerald CHOUINARD |  | TR | 6.8.4.1 |  | Defer (1, 3), accepted (2)
30 | 8 | Gerald CHOUINARD |  | TR | 6.13.5.1 | Defer pending discussios of 22-06-0219-01-0000 | need discussion
70 | 29 | Soo-Young CHANG |  | TR | 6.21.3.2 | Defer until the discussion in the Sensing Tiger Team | Pending
95 | 36 | Carlos CORDEIRO |  | TR | 6.21.5.1 |  | Pending
118 | 53 | Liwen CHU |  | T | Table 1 |  | defered for discussion on SCH/superframe
509 | 9 | Stephen KUFFNER | suggest to assigned to the text proponent. | T | 6.13.5.2 |  | need assignment | 22-06-0219-01-0000
Defer / Pending (Sensing)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
91 | 48 | Carlos CORDEIRO |  | TR | 6.8.2 |  | Pending on Sensing
156 | 52 | Steve SHELLHAMMER |  | TR | 6.8.7.3.7.9 |  | defered for discussion
158 | 49 | Steve SHELLHAMMER |  | TR | 6.8.22.3.1.1 |  | Pending on Sensing
227 | 29 | Wendong HU |  | TR | 6.21.3.2 | efficiency and effectiveness issues will not be resolved until the sensing methods are selected. | Pending
228 | 29 | Wendong HU |  | TR | 6.21.3.2 |  | Pending on Sensing
229 | 30 | Wendong HU |  | TR | 6.21.3.2 | efficiency and effectiveness issues will not be resolved until the sensing methods are selected. | Pending on Sensing
230 | 30 | Wendong HU |  | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until sensing methods are selected. Clarify the meaning of "mandatory" in Page 161, Line 4 | Pending on Sensing
233 | 31 | Wendong HU |  | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until sensing methods are selected. Clarify the meaning of "mandatory" in Page 161, Line 4 | Pending on Sensing
234 | 31 | Wendong HU |  | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until sensing methods are selected. Clarify the meaning of "mandatory" in Page 161, Line 4 | Pending on Sensing
235 | 31 | Wendong HU |  | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until sensing methods are selected. Clarify the meaning of "mandatory" in Page 161, Line 4 | Pending on Sensing
Defer for Discussion (Green)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
5 | 5 | Gerald CHOUINARD | Gerald CHOUINARD and Dave | TR | 6.1 | Changed from "ER" to "TR" | Defered (Green)
6 | 5 | Gerald CHOUINARD | Gerald CHOUINARD and Dave | TR | 6.1.1 | Changed from "ER" to "TR" | Defered (Green)
7 | 6 | Gerald CHOUINARD | Gerald CHOUINARD and Dave | TR | 6.1.1 | Changed from "ER" to "TR" | Defered (Green)
8 | 7 | Gerald CHOUINARD | Gerald CHOUINARD and Dave | TR | 6.1.1 | Changed from "ER" to "TR" | Defered (Green)
13 | 39 | Gerald CHOUINARD |  | TR | 6.4 | Defer Green for the upstream OFDMA parameters (subchannelization) to be resolved. | Pending
16 | 41 | Gerald CHOUINARD |  | TR | 6.5.1 | Defer Green until discussion on superframes | Pending
17 | 41 | Gerald CHOUINARD |  | TR | 6.5.1 |  | need discussion
42 | 26 | Gerald CHOUINARD | Carlos Cordeiro | TR | 6.21.2.1.2 | Assign to Carlos | need materials
44 | 31 | Gerald CHOUINARD |  | TR | 6.21.3.2 | informative | need discussion
47 | 35 | Gerald CHOUINARD | Carlos Cordeiro | TR | 6.21.5 | Assign to Carlos | need materials
92 | 49 | Carlos CORDEIRO | Carlos, Dave, Wendong | TR | 6.8.22.3.1.2 | need clarification | Deferred (Green)
117 | 53 | Liwen CHU |  | TR | Table 1 |  | defered (green) for discussion on SCH/superframe
136 | 35 | Liwen CHU |  | TR | 6.21.5 | Get the text from 802.16h. Note: currently, there is no proposal regarding this topic | need materials
176 | 37 | Wendong HU |  | TR | 6.3 |  | need assignment
179 | 41 | Wendong HU | Wendong and Carlos | TR | 6.5.1 |  | need assignment | Assigned
182 | 49 | Wendong HU | Carlos, Dave, Wendong | TR | 6.8.23 |  | Defered (Green)
183 | 50 | Wendong HU |  | TR | 6.8.25 |  | Defer (Green) for further discussion
195 | 16 | Wendong HU | Carlos and Wendong | TR | 6.21.1.4.1 | Assign to Carlos and Wendong | need materials
201 | 18 | Wendong HU | Carlos Cordeiro | TR | 6.21.1.4.2.2.2 |  | need assignment | Assigned
207 | 24 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
208 | 25 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
209 | 26 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | The solution is not satisfying after being carefully reviewed by the commenter, who suggests to defer this comment.
213 | 23 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
216 | 27 | Wendong HU | Carlos and Wendong | TR | 6.21.2.4 | Assign to Wendong and Carlos | need materials | The solution is not satisfying after being carefully reviewed by the commenter, who suggests to defer this comment.
217 | 23 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
218 | 24 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | The solution is not satisfying after being carefully reviewed by the commenter, who suggests to defer this comment.
219 | 24 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | The solution is not satisfying after being carefully reviewed by the commenter, who suggests to defer this comment.
220 | 25 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
221 | 24 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | The solution is not satisfying after being carefully reviewed by the commenter, who suggests to defer this comment.
231 | 30 | Wendong HU | Carlos Cordeiro | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until the sensing methods are selected. Page 163 Line 18 and Line 26 imply that the fast sensing is mandatory. Consider inserting conditional clause if fast sensing is implemented. Assign to Carlos | need materials
236 | 32 | Wendong HU | Carlos Cordeiro | TR | 6.21.3.2 | Issue: How to synchronize "dynamically allocated" fine sensing periods of overlapping WRANs? | need assignment | Assigned
238 | 33 | Wendong HU |  | TR | 6.21.3.2.3 | Editorial Comment: Replace "following" by "subsequent" in Page 164, Line 15 | need assignment | Doc: 22-07-0122
242 | 35 | Wendong HU | Wendong Hu | TR | 6.21.5 | Assign to Wendong to bring the text from 802.16h | need materials
331 | 37 | George VLANTIS |  | TR | 6.3 | Defer Green until presentation | Pending
344 | 50 | George VLANTIS |  | TR | 6.8.28.9 |  | Defer (Green) pending secuirty discussion
345 | 50 | George VLANTIS |  | TR | 6.8.28.9 |  | Defer (Green) pending secuirty discussion
350 | 7 | George VLANTIS | Wendong | ER | 6.10_ |  | Defered (Green)
385 | 6 | George VLANTIS | Gerald CHOUINARD and Dave | E | 6.1.1 |  | Defered (Green)
386 | 6 | George VLANTIS | Gerald CHOUINARD and Dave | E | 6.1.1 |  | Defered (Green)
387 | 6 | George VLANTIS | Gerald CHOUINARD and Dave | E | 6.1.1 |  | Defered (Green)
510 | 11 | Stephen KUFFNER | Suggest to refer to "22-07-0122-00-0000" for resolution of comment CID 190 for the BS initialization procedure. Database and regulatory issues are pending on TG2's decisions. | T | 6.15.1 | Defer Green. BS initialization needs to be defined (normative text and flowchart). Regulatory requirements could exist and some max outage time for database access may need to be defined. Database requirements need further development/clarification. | need assignment
Defer for Discussion (Yellow)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
61 | 1 | Soo-Young CHANG |  | TR |  |  | need materials
106 | 8 | Carlos CORDEIRO |  | TR | 6.13.1 | pending normative text for annex | pending
508 | 8 | Stephen KUFFNER |  | T | 6.13.1 | pending normative text for annex | pending
Defer for Discussion (Salmon)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
64 | 22 | Soo-Young CHANG |  | TR | 6.21.2 |  | need discussion
68 | 9 | Soo-Young CHANG |  | TR | 6.15 |  | need discussion | 22-06-0126-01-0000_Huawei_Network_Entry_and_Initialization
186 | 7 | Wendong HU |  | TR | 6.11.1 |  | need discussion | 22-06-0229-00-0000
245 | 21 | Wendong HU |  | TR | 6.21.2 |  | need discussion
505 | 21 | Stephen KUFFNER |  | T | 6.21.2 |  | need discussion
506 | 20 | Stephen KUFFNER |  | T | 6.21.2 |  | need discussion
Defer for Discussion (Gray)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
66 | 21 | Soo-Young CHANG |  | TR | 6.21.2 |  | need discussion | 22-06-0124-01-0000_Huawei_Inter-BS_Synchronization
185 | 51 | Wendong HU |  | T | 6.8.30_ |  | Defer (grey)
204 | 20 | Wendong HU |  | TR | 6.21.1.6 |  | need discussion
205 | 20 | Wendong HU |  | TR | 6.21.1.7 |  | need discussion
226 | 29 | Wendong HU |  | TR | 6.21.3.2 |  | need discussion
348 | 51 | George VLANTIS |  | TR | 6.8.30_ |  | defer (grey)
Defer Until Submission
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
43 | 27 | Gerald CHOUINARD |  | TR | 6.21.3 | Defer Green until submission of text | need materials
45 | 32 | Gerald CHOUINARD |  | TR | 6.21.3.2 | Defer Green until submission on how to synchronize inter-cell's quiet period if this mechansim is used. | need materials
125 | 29 | Liwen CHU |  | TR | 6.21.3.2 | Defer Green until submission on how to synchronize inter-cell's quiet period if this mechansim is used. | need materials
175 | 1 | Wendong HU |  | TR |  |  | need materials | 22-07-0051-00-0000_STM-Huawei_interBS_com_messages.ppt
202 | 18 | Wendong HU |  | TR | 6.21.1.5 | Defer Green until submission of text with simulations comparable to doc no. 22-05-105r1 | need materials
225 | 28 | Wendong HU |  | TR | 6.21.3.1 | Defer Green until submission of proposal. Reference from text of 802.16h. Assign it to Wendong | need materials
504 | 21 | Stephen KUFFNER |  | T | 6.21.2 | Defer Green until submission | need materials | 22-06-0228-00-0000_Scheduling_Connection_Based_Inter_BS_communications.doc
521 | 28 | Stephen KUFFNER |  | T | 6.21.3 | Defer Green until submission of text | need materials
Defer: New Topics
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
55 | 7 | Soo-Young CHANG |  | TR | 6.10_ |  | need materials
56 | 7 | Soo-Young CHANG |  | TR | 6.11 |  | need materials
57 | 11 | Soo-Young CHANG |  | TR | 6.15.1 |  | need materials
59 |  | Soo-Young CHANG |  | TR |  |  | need materials
263 | 11 | Winston CALDWELL |  | TR | 6.15 | Defer Green. Need Contribution. | need assignment
Withdraw / Reject
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
19 | 43 | Gerald CHOUINARD |  | TR |  | Reject. Explanation is given.
23 | 51 | Gerald CHOUINARD |  | TR | 6.8.3.1 |  |  | withdrawn
110 | 12 | Carlos CORDEIRO |  | TR |  | Withdraw
189 | 12 | Wendong HU |  | TR |  | Withdraw
196 | 16 | Wendong HU |  | TR |  | Withdraw
200 | 18 | Wendong HU |  | TR |  | Withdraw
211 | 25 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | withdrawn
212 | 26 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | withdrawn
223 | 27 | Wendong HU |  | TR |  | Withdraw
527 | 40 | Stephen KUFFNER |  | T |  | Withdraw
530 | 45 | Stephen KUFFNER |  | TR |  | Withdraw
Unread / Unclassify
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
9 | 38 | Gerald CHOUINARD |  | ER | 6.3
10 | 38 | Gerald CHOUINARD |  | ER | 6.3
20 | 43 | Gerald CHOUINARD |  | ER | 6.7.3
28 | 48 | Gerald CHOUINARD |  | ER | 6.8.22.3.1.1
31 | 13 | Gerald CHOUINARD |  | ER | 6.15.5.1
32 | 14 | Gerald CHOUINARD |  | ER | 6.21.1
33 | 15 | Gerald CHOUINARD |  | ER | 6.21.1.1
34 | 15 | Gerald CHOUINARD |  | ER | 6.21.1.2
35 | 16 | Gerald CHOUINARD |  | ER | 6.21.1.3
38 | 19 | Gerald CHOUINARD |  | ER | 6.21.1.5
48 | 36 | Gerald CHOUINARD |  | ER | 6.21.5.1
187 | 10 | Wendong HU |  | ER | 6.15
266 | 10 | Winston CALDWELL | wendong Hu | TR | 6.15
268 | 50 | George VLANTIS |  | T | 6.8.28.10
332 | 40 | George VLANTIS |  | E | 6.4
342 | 46 | George VLANTIS |  | ER | 6.8.15.3.3.2
343 | 9 | George VLANTIS |  | ER | 6.13.5.2
346 | 50 | George VLANTIS |  | T | 6.8.28.10
347 | 50 | George VLANTIS |  | T | 6.8.28
351 | 8 | George VLANTIS |  | ER | 6.13.5.2
352 | 9 | George VLANTIS |  | ER | 6.13.5.2
353 | 14 | George VLANTIS |  | ER | 6.20_
354 | 14 | George VLANTIS |  | ER | 6.20.9
Total: 232

## Security
Defer: New Topics
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
113 | 54 | Liwen CHU | TR | 7 | Defer (Green) New Topic
Unread / Unclassify
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
109 | 54 | Carlos CORDEIRO | TR | 7
130 | 55 | Liwen CHU | TR | 7.4.2
329 | 55 | George VLANTIS | E | 7.5
355 | 54 | George VLANTIS | ER | 7
356 | 54 | George VLANTIS | ER | 7.2
357 | 54 | George VLANTIS | ER | 7.2.1
358 | 55 | George VLANTIS | ER | 7.2.2
359 | 55 | George VLANTIS | ER | 7.3
360 | 55 | George VLANTIS | ER | 7.4.1
361 | 55 | George VLANTIS | ER | 7.4.2
362 | 56 | George VLANTIS | ER | 7.5
389 | 55 | George VLANTIS | E | 7.5
Total: 13

## PHY
Acceptecd
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
147 | 60 | Patrick PIRAT | T | 8.6.1.1
148 | 61 | Patrick PIRAT | T | 8.9.1.3 | This was for DVB-RCT, and is not applicable to these OFDMA parameters. Delete clause.
151 | 60 | Patrick PIRAT | TR | 8.5.3 | One "encoded block" is one subchannel per OFDMA symbol. NCBPB = number of coded bits per subchannel per OFDMA symbol. Fix definition
152 | 61 | Patrick PIRAT | TR | 8.6.1.1 | Ramon: Need to supply reference code
484 | 57 | Stephen KUFFNER | T | 8 | Follow same principle as in the bandwidth rwo of Table 225. Put single channel maximum; in remarks column, put "up to 72.6Mbps within 3 bonded channels"
492 | 58 | Stephen KUFFNER | T | 8.3.2.1
Proposed Accept in Principle
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
51 | 56 | Gerald CHOUINARD | TR | 8
96 | 58 | Carlos CORDEIRO | T | 8.3.1.2 | Defer Green pending PHY preamble discussions | Accepted In Principle in Orlando
144 | 60 | Patrick PIRAT | T | 8.1.2.3.3 | Defer Green pending PHY discussions
145 | 60 | Patrick PIRAT | T | 8.4.1.1 | Need to define subcarrier indexing | Accepted In Principle in Orlando
146 | 61 | Patrick PIRAT | T | 8.4 | Defer Green pending PHY OFDMA discussions.
336 | 59 | George VLANTIS | TR | 8.9.2 | Defer Green pending PHY decision on ranging methods. See document 22-06-0092r1
337 | 59 | George VLANTIS | TR | 8.9.3 | Defer Green pending PHY decision on power control methods
483 | 56 | Stephen KUFFNER | T | 8 | Include remark about EIRP and BS antenna height. Defer remedy for discussions of more robust coding techniques for 1.5 Mbps minimum data rate (rate 1/4 code?). AssignL PHY (Zander/Ramon)
491 | 58 | Stephen KUFFNER | T | 8.3.1.1 | Superframe preamble will change to span the same number of subcarriers as the frame preamble. Preamble text will be changed by PHY editors pending decision on preamble sequences.
495 | 59 | Stephen KUFFNER | T | 8.4.2 | Delete clause 8.4.2; we have only one pilot pattern now. Need a new figure in describing pilot patterns in the appropriate clause. Overall pilot text needs to be added throughout document. | Accepted In Principle in Orlando
Defer Until Clarification
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
150 | 60 | Patrick PIRAT | TR | 8.5.3 | Clarify interleaving method, pending PHY OFDMA discussions
Defer for Discussion (Green)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
115 | 61 | Liwen CHU | TR |  | Defer Green MAC/PHY discussion
137 | 8 | David MAZZARESE | TR | 6.13.5 | Defer Green, Pending PHY review of document 22-06-0219-01-0000_Proposed_text_changes_to_P802-22_D0.1_Final_Section_6_13_5.doc
149 | 60 | Patrick PIRAT | TR | 8.4.1.2 | This whole section needs to change pending PHY decisions on OFDMA parameters
493 | 58 | Stephen KUFFNER | T | 8.3.2.1 | Spreading method needs to be defined
494 | 59 | Stephen KUFFNER | T | 8.4.1.2 | PHY group needs to decide how subchannels can be used; also ties in with OFDMA parameters. Draft doesn't support Figure 59; needs to be fixed; the 'steps' don't allign with baud boundaries
Withdraw / Reject
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
58 | 57 | Soo-Young CHANG | TR | 8.3 | Defer Green pending presentation and discussion | Withdraw/Reject in Orlando
247 | 57 | Wendong HU | TR | 8.3 | Defer Green pending PHY/MAC discussions | Withdraw/Reject in Orlando
489 | 57 | Stephen KUFFNER | T |  | Withdraw
490 | 58 | Stephen KUFFNER | T |  | Withdraw
Unread / Unclassify
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
141 | 1 | Patrick PIRAT | E | 8.2
142 | 61 | Patrick PIRAT | E | 8.6
143 | 1 | Patrick PIRAT | ER | 8.4
Total: 29
****

## Others
Acceptecd
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
339 | 59 | George VLANTIS | TR | C.6.2.1.4 | Fix equations
Proposed Accept in Principle
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
108 | 4 | Carlos CORDEIRO | TR | 5 | If needed create normative text, if not needed removed. Consider use/modification of the IP convergence sublayer from 802.16
379 | 4 | George VLANTIS | T | 5 | If needed create normative text, if not needed removed. Consider use/modification of the IP convergence sublayer from 802.16
Defer Until Clarification
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
103 | 65 | Carlos CORDEIRO | TR | A.4.3 | Defer Salmon for Samsung to clarify if it is an implementation or a standardization issue. If it is the latter, documents should be provided.
254 | 62 | Wendong HU | TR | A.1.4.1 | Defer Yellow Until Samsung's clarification about if it is stable or transitory situation
Defer for Discussion (Green)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
253 | 62 | Wendong HU | TR | A.1.3
Defer for Discussion (Red)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
65 | 59 | Soo-Young CHANG | TR | D.11.3 | See 22-06-0263-00-0000_Huawei_Sensing_Scheme_for_DVB-1
Defer for Discussion (Yellow)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
131 | 66 | Liwen CHU | TR | AA | Normative text for Appendix A
173 | 65 | Wendong HU | TR | AA
249 | 66 | Wendong HU | TR | A.1.1
252 | 62 | Wendong HU | TR | A.1.3 | Defer Yellow until discussion on FDD
258 | 64 | Wendong HU | TR | A.3
259 | 64 | Wendong HU | TR | A.3
260 | 64 | Wendong HU | TR | A.3
261 | 64 | Wendong HU | TR | A.3
514 | 66 | Stephen KUFFNER | T | A.1.1
515 | 67 | Stephen KUFFNER | T | A.1.4 | Defer Yellow for Samsung
Defer for Discussion (Salmon)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
69 | 68 | Soo-Young CHANG | TR | A.A.C.3
101 | 64 | Carlos CORDEIRO | TR | A.4.1 | Defer Salmon for Samsung
102 | 64 | Carlos CORDEIRO | TR | A.4.2 | Defer Salmon for Samsung
104 | 65 | Carlos CORDEIRO | TR | A.4.4 | See the document 22-06-0229-00-0000_Spectrum_Contention_Algorithm_Submission.doc
105 | 65 | Carlos CORDEIRO | TR | A.4.5 | See the document 22-07-0024-00-0000
132 | 66 | Liwen CHU | TR | AA | Normative text for Appendix
262 | 65 | Wendong HU | TR | A.4.4
520 | 67 | Stephen KUFFNER | T | A.4.1 | Defer Salmon for Samsung
Defer for Discussion (Gray)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
112 | 63 | Carlos CORDEIRO | TR | A.1.6 | Refer the topic on coexistence between 802.22 systems and non-802.22 systems to main group
114 | 66 | Liwen CHU | TR | AA
133 | 65 | Liwen CHU | TR | A.5.1
Defer: New Topics
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
59 | 67 | Soo-Young CHANG | TR | AA.A.2
60 | 68 | Soo-Young CHANG | TR | AA.C.6
174 | 1 | Wendong HU | TR
Withdraw / Reject
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
248 | 63 | Wendong HU | TR |  | Withdraw
250 | 61 | Wendong HU | TR | A.1.1 | Defer Green: Refer the topic of superframe to the main group. Defer Yellow the discussion on optional channel bonding | Withdraw/Reject in Orlando
251 | 62 | Wendong HU | TR |  | Withdraw
255 | 62 | Wendong HU | TR |  | Withdraw
Unread / Unclassify
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Any Update?
371 | 1 | George VLANTIS | ER | 1.3
1 | 2 | Gerald CHOUINARD | E | 2
3 | 2 | Gerald CHOUINARD | ER | 3
375 | 3 | George VLANTIS | E | 3.13
376 | 3 | George VLANTIS | E | 3.26
372 | 3 | George VLANTIS | E | 3.3
373 | 3 | George VLANTIS | E | 3.5
374 | 3 | George VLANTIS | E | 3.9
3 | 3 | Gerald CHOUINARD | ER | 4
377 | 4 | George VLANTIS | E | 4
378 | 4 | George VLANTIS | E | 4
256 | 63 | Wendong HU | ER | A.1.6
257 | 63 | Wendong HU | TR | A.1.7
99 | 63 | Carlos CORDEIRO | ER | A.1.7.2
67 | 69 | Soo-Young CHANG | TR | AA.D.11.3
54 | 69 | Baowei JI | TR | AA.4.3
340 | 69 | George VLANTIS | ER | B.2
330 | 69 | George VLANTIS | TR | C.3
334 | 70 | George VLANTIS | TR | C.4.2
335 | 70 | George VLANTIS | TR | C.4.2
338 | 70 | George VLANTIS | E | C.6
341 | 70 | George VLANTIS | ER | C.6.2.1.6
364 | 70 | George VLANTIS | ER | C.6.4
365 | 70 | George VLANTIS | TR | C.6.5.2
369 | 71 | George VLANTIS | E | 11.3
349 | 71 | George VLANTIS | TR | 11.3.3.1
363 | 71 | George VLANTIS | ER | 11.3.3.3
366 | 71 | George VLANTIS | E | Table G.1
138 | 71 | David MAZZARESE | TR | Annex
160 | 71 | Steve SHELLHAMMER | TR | 11.3
161 | 72 | Steve SHELLHAMMER | TR | 11.3.1
162 | 72 | Steve SHELLHAMMER | TR | 11.3.1
163 | 72 | Steve SHELLHAMMER | TR | 11.3.2.1
164 | 72 | Steve SHELLHAMMER | TR | 11.3.22
165 | 72 | Steve SHELLHAMMER | TR | 11.3.3.1
166 | 73 | Steve SHELLHAMMER | TR | 11.3.3.2.1
167 | 73 | Steve SHELLHAMMER | TR | 11.3.3.2.2
168 | 73 | Steve SHELLHAMMER | TR | 11.3.3.2.3
169 | 73 | Steve SHELLHAMMER | TR | 11.3.3.2.3
170 | 73 | Steve SHELLHAMMER | TR | 11.3.3.3
171 | 73 | Steve SHELLHAMMER | TR | 11.3.3.4
172 | 74 | Steve SHELLHAMMER | TR | 11.3.4
52 | 74 | John BENKO | T | C.4.1
485 | 74 | Stephen KUFFNER | TR | C.3
496 | 74 | Stephen KUFFNER | T | C.4.1.4
497 | 74 | Stephen KUFFNER | T | C.5
486 | 74 | Stephen KUFFNER | T | C.6.2.1.2
487 | 75 | Stephen KUFFNER | T | C.6.2.1.5
488 | 75 | Stephen KUFFNER | T | C.6.5.4
498 | 75 | Stephen KUFFNER | T | 11.3.1
500 | 75 | Stephen KUFFNER | T | 11.3.2.1
499 | 75 | Stephen KUFFNER | T | 11.3.2.1
501 | 75 | Stephen KUFFNER | T | 11.3.3.1
502 | 76 | Stephen KUFFNER | T | 11.3.3.2
503 | 76 | Stephen KUFFNER | T | 11.3.3.4
370 | 76 | George VLANTIS | E | Introduction
Total: 91

## References
References: