## Title
IEEE P802.22 Wireless RANs
Submission
Designator: | doc.: IEEE 802.22-07/0087r1
Venue Date: | March 2007
First Author: | Wendong Hu, STMicroelectronics, Inc.
Subject: | Statistics of MAC Comment Resolutions
Full Date: | 2007-03-01
Author(s): | Name(s) | Wendong Hu
| Company | STMicroelectronics, Inc.
| Address | 1060 East Brokaw Road, San Jose, CA 95131
| Phone: | 1-408-467-8410
| Fax: | 1-408-452-0278
| email: | wendong.hu@st.com
Abstract:
This spreadsheet contains statistics of MAC comment resolutions for IEEE 802.22 working document D0.2.
Notice: This document has been prepared to assist IEEE 802.22. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.22.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures
<http://standards.ieee.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <carl.stevenson@ieee.org> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.22 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Overview
Accepted |  | Defered (Green) |  |  | Defered (New Topics)
Subtotal | 21 | Subtotal | 59 |  | Subtotal | 6
Need Assignment | 2 | Need Assignment | 1+15 | 16 | Need Assignment | 1
Need Materials | 2 | Need Materials | 1+28 | 29 | Need Materials | 4
Need Discussion | 0 | Need Discussion | 1+5 | 6 | Need Discussion | 1
Need Decision | 0 | Need Decision | 0 |  | Need Decision | 0
Need Action | 17 | Need Action | 0 |  | Need Action | 0
Pending | 0 | Pending | 8 | 1+7 | Pending | 0
Accepted in Principle |  | Defered (Yellow) |  |  | Unread / Unclassify
Subtotal | 40 | Subtotal | 3 |  | Subtotal | 72
Need Assignment | 6 | Need Assignment | 0
Need Materials | 19 | Need Materials | 1
Need Discussion | 0 | Need Discussion | 0
Need Decision | 0 | Need Decision | 0
Need Action | 15 | Need Action | 0
Pending | 0 | Pending | 2
Defered Until Clarification |  | Defered (Salmon) |  |  | Withdrawn/Rejected
Subtotal | 4 | Subtotal | 6 |  | Subtotal | 8
Need Assignment | 4 | Need Assignment | 0
Need Materials | 0 | Need Materials | 0
Need Discussion | 0 | Need Discussion | 6
Need Decision | 0 | Need Decision | 0
Need Action | 0 | Need Action | 0
Pending | 0 | Pending | 0
Defered Until Submission |  | Defered (Grey) |  |  | Summary
Subtotal | 9 | Subtotal | 4 |  | Total | 232
Need Assignment | 0 | Need Assignment | 0 |  | Need Assignment | 29
Need Materials | 9 | Need Materials | 0 |  | Need Materials | 64
Need Discussion | 0 | Need Discussion | 4 |  | Need Discussion | 17
Need Decision | 0 | Need Decision | 0 |  | Need Decision | 0
Need Action | 0 | Need Action | 0 |  | Need Action | 32
Pending | 0 | Pending | 0 |  | Pending | 10
[5 empty] | Unread/Unclassified | 72
[5 empty] | Withdrawn/Rejected | 8

## MAC
Acceptecd
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
380 | 4 | George VLANTIS |  | E | 6 | Editor to carefully review because CMAC has two meanings/usages in the document. | need action
381 | 4 | George VLANTIS |  | E | 6 |  | need action
382 | 5 | George VLANTIS |  | E | 6 |  | need action
188 | 10 | Wendong HU | Carlos and Wendong | TR | 6.15 | Modify Figure 20 and revise the associated text to illustrate and explain the need for a keepout region extending beyond the protected contour. | need assignment
190 | 12 | Wendong HU | Carlos Cordeiro | TR | 6.15.3 | Assigned to Carlos CORDEIRO | need materials | ready
36 | 16 | Gerald CHOUINARD |  | TR | 6.21.1.4.1 |  | need action
37 | 17 | Gerald CHOUINARD |  | TR | 6.21.1.4.2 |  | need action
197 | 17 | Wendong HU |  | TR | 6.21.1.4.2.1 | Delete the word "a small amount of" in Line 43, Page 147 | need action
198 | 18 | Wendong HU |  | TR | 6.21.1.4.2.1 | Delete (Page 148, Lines 3 - 7) "In case no other CPES … in order to resolve the issue" | need action
40 | 21 | Gerald CHOUINARD |  | TR | 6.21.2 | Delete "although this may be implementation dependent" in P+F4+F663age 155 Line 17 | need action
94 | 30 | Carlos CORDEIRO |  | TR | 6.21.3.2 |  | need action
49 | 36 | Gerald CHOUINARD |  | TR | 6.21.5.1 | Replace "NSTQP" by "NSIQP" | need action
87 | 39 | Carlos CORDEIRO | Carlos Cordeiro | TR | 6.4 | Carlos to insert new figure | need materials | ready
12 | 39 | Gerald CHOUINARD |  | TR | 6.4 | Delete "possible contention intervals for coexistence with purposes" (Line 4, Page 11). Change the sentences in Lines 8 - 9 as "of fixed size (MAC) slots, which are, in turn, an integral number of modulation symbols and sub-channels (currently, 1 MAC slo | need action
333 | 40 | George VLANTIS |  | T | 6.4 | Move this paragraph (beginning at Line 36 of page 11 and ending on Line 2 of Page 12) to Technology Overview Document. | need action
14 | 40 | Gerald CHOUINARD |  | TR | 6.4 | Change the sentence in Line 5 as follows: "together with coexistence beacons (i.e., through CBP) shall be employed. The SSS window (depicted in Figure 4) is scheduled at the end of the upstream subframe for simpler multiplexing and to accommodate simpler | need action
529 | 42 | Stephen KUFFNER |  | T | 6.5.1 |  | need action
528 | 42 | Stephen KUFFNER |  | T | 6.5.1 |  | need action
22 | 44 | Gerald CHOUINARD |  | TR | 6.8.1.1.1 |  | need action
88 | 47 | Carlos CORDEIRO |  | TR | 6.8.2 | Table 30 Message should be an integer number of bytes, Delete Padding Nibble of 4 bits | need assignment | actionable
62 | 47 | Soo-Young CHANG |  | TR | 6.8.2 |  | need action
Proposed Accept in Principle
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
507 | 6 | Stephen KUFFNER | Carlos Cordeiro | T | 6.1.1 | Need to create a section on the spectrum manager function. Rewrite section to define mandatory signal channel system and optional channel bonding/aggregation | need assignment
388 | 6 | George VLANTIS |  | T | 6.1.1 | Delete the parenthetical text about directional antennas | need action
97 | 9 | Carlos CORDEIRO | Carlos Cordeiro | TR | 6.15 | Adapt material from corresponding 802.16 section on Network Entry and Initialization, strarting from 6.15.5 onward. Assigned to Carlos CORDEIRO | need materials | not ready
265 | 10 | Winston CALDWELL | Carlos Cordeiro | TR | 6.15 | Adapt material from corresponding 802.16 section on Network Entry and Initialization, strarting from 6.15.5 onward. Assigned to Carlos CORDEIRO | need materials | not ready
267 | 10 | Winston CALDWELL | Carlos Cordeiro | TR | 6.15 | Adapt material from corresponding 802.16 section on Network Entry and Initialization, strarting from 6.15.5 onward. Assigned to Carlos CORDEIRO | need materials | not ready
264 | 10 | Winston CALDWELL | Carlos Cordeiro | TR | 6.15 | Adapt material from corresponding 802.16 section on Network Entry and Initialization, strarting from 6.15.5 onward. Assigned to Carlos CORDEIRO | need materials | not ready
511 | 12 | Stephen KUFFNER | Carlos Cordeiro | T | 6.15.3 | Assigned to Carlos CORDEIRO | need materials | ready
513 | 13 | Stephen KUFFNER | Steve Kuffner? | T | 6.15.5.1 | Factor linking EIRP to Maximum Transmit Power needs to be known by the MAC. Professional installation should not be forced. Because the antenna gain and cable losses should be set by the manufactorers to not exceed the limit. | need assignment for rewriting the text | tentatively assigned to steve kuffner, need comfirmation from steve
134 | 14 | Liwen CHU |  | T | 6.15.5.1 | Move the texts (Page 125, lines 14 - 15) regarding Multiple Channel Support to A.1 | need action
98 | 14 | Carlos CORDEIRO | Carlos Cordeiro | TR | 6.20_ | Assign to Carlos CORDEIRO to recommend 802.16 text | need materials | not ready
192 | 15 | Wendong HU |  | TR | 6.21.1.1 | Change the words "have a direct effect" by "experience leakages due to limited IF filtering". Replace "e.g." by "i.e.,". Move the definition of "in-band sensing" and "out-of-band sensing" to the definition section. | need action
193 | 15 | Wendong HU |  | TR | 6.21.1.3 | Change "both TV signals and Part 74 services, according to the DFS model defined in FRD" to "incumbent devices defined in clause 15.1 of the FRD according to the DFS model defined in the same document" | need action
199 | 17 | Wendong HU |  | TR | 6.21.1.4.2 | Change the sentence (Page 147, Line 23) "The quiet period notification phase ends whenever the BS has acquired a reliable picture of the measurement outcome in its cell" to "The quiet period notification phase ends whenever the BS has acquired a picture o | need action
516 | 17 | Stephen KUFFNER |  | T | 6.21.1.4.2.1 | Refer to Comment 198. The sentences (Page 148, Lines 3 - 7) have been deleted. | need action
517 | 18 | Stephen KUFFNER | Carlos and Wendong | T | 6.21.1.4.2.2.2 | Assigned to Carlos and Wendong | need materials | ready
518 | 19 | Stephen KUFFNER | Carlos Cordeiro | T | 6.21.1.5 | Assigned to Carlos CORDEIRO | need materials | ready
39 | 20 | Gerald CHOUINARD | Ko | TR | 6.21.1.5.1 | Assign to Ko | need materials | ready
41 | 26 | Gerald CHOUINARD |  | TR | 6.21.2.1 | Change "Several mechanisms are implemented on top of CBP" (Page 156, Line 14) to "There are several optional mechanisms that are implemented on top of CBP in the annex" | need action
222 | 27 | Wendong HU |  | TR | 6.21.3 | Change "Not engagled in communication with its BS during normal cell operation" to "possible" | need action
522 | 28 | Stephen KUFFNER |  | T | 6.21.3 | If quiet period is not an integer number of antennas, a partial frame is used | need assignment | pending for sensing input
232 | 31 | Wendong HU |  | TR | 6.21.3.2 | Replace "the fine sensing could be over 3 orders of magnitude larger than fast sensing" by "the fine sensing time could be orders of magnitude larger than the fast sensing" | need action
237 | 33 | Wendong HU | Carlos Cordeiro | TR | 6.21.3.2.2 | Assign to Carlos to redraw the figure for single channel operation and move the current figure (Figure 59) to annex | need materials | ready
239 | 33 | Wendong HU |  | TR | 6.21.4 | Delete the text "(e.g., this can be done through clustering)" in Page 165, Lines 21-22 | need action
240 | 34 | Wendong HU | Ko | TR | 6.21.4.1 | Assign to Ko | need materials | ready
128 | 34 | Liwen CHU | Ko | T | 6.21.4.2 | Assign to Ko | need materials | ready
243 | 36 | Wendong HU |  | TR | 6.21.6 | Change "shall" by "may" in Page 176, Line 1. Insert "For example" in front of the first sentence in Page 176, Line 1. Remark: the algorithm refers to "k-means algorithm". | need action
524 | 37 | Stephen KUFFNER |  | T | 6.21.6.2 | Change "shall" by "may" in Page 176, Line 1. Insert "For example" in front of the first sentence in Page 176, Line 1. | need action
129 | 37 | Liwen CHU |  | TR | 6.21.6.2 | Change "shall" by "may" in Page 176, Line 1. Insert "For example" in front of the first sentence in Page 176, Line 1. | need action
525 | 37 | Stephen KUFFNER |  | T | 6.3 | Suggested Remedy: A fixed number of frames, not to mention the number | need materials | change to "16" need to confirm with steve.
526 | 38 | Stephen KUFFNER | Carlos Cordeiro | T | 6.4 | Assign to Carlos | need materials | ready
177 | 38 | Wendong HU | Carlos Cordeiro | TR | 6.4 | Assign to Carlos | need materials | ready
178 | 38 | Wendong HU | Carlos Cordeiro | TR | 6.4 | Assign to Carlos | need materials | ready
11 | 39 | Gerald CHOUINARD | Carlos Cordeiro | TR | 6.4 | Assign to Carlos | need materials | ready
15 | 40 | Gerald CHOUINARD |  | TR | 6.4 | Change the sentence in Line 15 as "Whenever a CPE is neither receiving nor sending data to its BS, it is capable of decoding CBP packets transmitted by nearby stations belonging to other BSs operating on the same TV channel, and/or performing out-of-band | need action
21 | 44 | Gerald CHOUINARD | Carlos Cordeiro | TR | 6.8.1.1 | Assign to Carlos. Defer (Green) sensing RTG until submission (quiet periods?). Table 26: Change the word "slots" to "by 8 samples increment" for both TTG and RTG. Delete the Frame Duration Code. Explanation is given for the comments on "repetition period | need materials | ready
367 | 45 | George VLANTIS |  | TR | 6.8.1.2 | Delete "Offset". In Table 29, element ID 150, bits 3 - 7 should be reserved. Bits 0 - 2 have the following values: 000 = DBTC, 001 = CTC, 010 = LDPC, 011 = SBTC. Bits 3 - 5 have the following values: 000 = Spreading, 001 = reserved, 010 = QPSK, 011 = 16QA | need action
26 | 46 | Gerald CHOUINARD | Gerald CHOUINARD | TR | 6.8.15.3.3.2 | Change title to "Maximum Transmit Power and EIRP". The 8-bit values should indicate -64 to +64 dbM in 0.5 dB steps. Manufacturer in the regulatory domain has to guarantee that the EIRP and power constraints are not exceeded in the ideal cabling and antenn | need assignment
27 | 46 | Gerald CHOUINARD | Carlos | TR | 6.8.15.3.3.4.1 | Delete bit 0 = 1K FFT, change to "reserved". Other FFT sizes are only for channel bonding. Assign to Carlos. | need materials | not ready
531 | 46 | Stephen KUFFNER | George Vlantis | T | 6.8.15.3.3.4.2 | In Table 125, bits 3 - 7 should be reserved. Bits 0 - 2 have the following values: 000 = DBTC, 001 = CTC, 010 = LDPC, 011 = SBTC. Values 4 - 7 are reserved. In Table 126, bits 0 - 1: reserved, the other bits remain unchanged. | need assignment
532 | 47 | Stephen KUFFNER |  | T | 6.18.15.3.3.4.4 | In Table 127, bits 0 - 1 should be reserved. | need assignment | pending for phy ad hoc (will AMC be supported?)
Defer Until Clarification
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
126 | 34 | Liwen CHU | Carlos Cordeiro | TR | 6.21.4 | Defer Green. Clarify is broadcasting in explicit channel mode equivalent to embedded channel mode? | need assignment
127 | 34 | Liwen CHU | Carlos Cordeiro | T | 6.21.4.2 | Defer Green. Assign to Carlos to clarify the discrepancy between the text and Figure 6.1 for transition 1 | need assignment | assigned to Ko and it is ready
50 | 36 | Gerald CHOUINARD | Gerald CHOUINARD | TR | 6.21.5.3 | Defer (Green) until Gerald's clarification on 7 slots | need assignment
18 | 42 | Gerald CHOUINARD | Dave Cavalcanti | TR | 6.5.2 | Defer Green until Gereld's clarification about the increase in addressing size and the QPSK rate | need assignment
Defer
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
30 | 8 | Gerald CHOUINARD |  | TR | 6.13.5.1 | Defer pending discussios of 22-06-0219-01-0000 | need discussion
509 | 9 | Stephen KUFFNER |  | T | 6.13.5.2 |  | need assignment
191 | 14 | Wendong HU | Wendong and Carlos | TR | 6.21 | Assign to Wendong and Carlos to resolve | need materials
70 | 29 | Soo-Young CHANG |  | TR | 6.21.3.2 | Defer until the discussion in the Sensing Tiger Team | Pending
Defer for Discussion (Green)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
510 | 11 | Stephen KUFFNER |  | T | 6.15.1 | Defer Green. BS initialization needs to be defined (normative text and flowchart). Regulatory requirements could exist and some max outage time for database access may need to be defined. Database requirements need further development/clarification. | need assignment
111 | 13 | Carlos CORDEIRO |  | TR | 6.15.3 | Need to be rephrased, related to Comment Number 512 | need assignment
512 | 13 | Stephen KUFFNER |  | T | 6.15.3 | Need to be rephrased, related to Comment Number 111 | need assignment
194 | 16 | Wendong HU |  | TR | 6.21.1.4.1 |  | need assignment
195 | 16 | Wendong HU | Carlos and Wendong | TR | 6.21.1.4.1 | Assign to Carlos and Wendong | need materials
201 | 18 | Wendong HU |  | TR | 6.21.1.4.2.2.2 |  | need assignment
519 | 19 | Stephen KUFFNER | Carlos Cordeiro for (2) and (3) | T | 6.21.1.5 | Defer Green for point (1) on EIRP profile. Assign (2) and (3) to Carlos | need assignement for (1), need materialsf or (2) and (3)
107 | 19 | Carlos CORDEIRO | Ko | TR | 6.21.1.5.1 | Assign to Ko | need materials
203 | 20 | Wendong HU | Ko | TR | 6.21.1.5.1 | Assign to Ko | need materials
206 | 21 | Wendong HU | Carlos and Wendong | TR | 6.21.2 | Assign to Carlos and Wendong | need materials
217 | 23 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
213 | 23 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
215 | 23 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | Materials pending
214 | 23 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | Materials pending
218 | 24 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
219 | 24 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
221 | 24 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
207 | 24 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
220 | 25 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
208 | 25 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
210 | 25 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
211 | 25 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
212 | 26 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials
209 | 26 | Wendong HU | Carlos and Wendong | TR | 6.21.2.1 | Assign to Carlos and Wendong | need materials | Materials pending
42 | 26 | Gerald CHOUINARD | Carlos Cordeiro | TR | 6.21.2.1.2 | Assign to Carlos | need materials
100 | 26 | Carlos CORDEIRO | Carlos and Wendong | TR | 6.21.2.3 | Assign to Carlos and Wendong | need materials
216 | 27 | Wendong HU | Carlos and Wendong | TR | 6.21.2.4 | Assign to Wendong and Carlos | need materials
224 | 28 | Wendong HU |  | TR | 6.21.3 | See the document 22-05-0105-01-0000 | need discussion
93 | 28 | Carlos CORDEIRO |  | TR | 6.21.3 | Defer Green until the discussion on preamble | Pending
227 | 29 | Wendong HU |  | TR | 6.21.3.2 | efficiency and effectiveness issues will not be resolved until the sensing methods are selected. | Pending
228 | 29 | Wendong HU |  | TR | 6.21.3.2 |  | need assignment
231 | 30 | Wendong HU | Carlos Cordeiro | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until the sensing methods are selected. Page 163 Line 18 and Line 26 imply that the fast sensing is mandatory. Consider inserting conditional clause if fast sensing is implemented. Assign to Carlos | need materials
229 | 30 | Wendong HU |  | TR | 6.21.3.2 | efficiency and effectiveness issues will not be resolved until the sensing methods are selected. | Pending
230 | 30 | Wendong HU |  | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until sensing methods are selected. Clarify the meaning of "mandatory" in Page 161, Line 4 | need assignment
233 | 31 | Wendong HU |  | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until sensing methods are selected. Clarify the meaning of "mandatory" in Page 161, Line 4 | need assignement
234 | 31 | Wendong HU |  | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until sensing methods are selected. Clarify the meaning of "mandatory" in Page 161, Line 4 | need assignment
44 | 31 | Gerald CHOUINARD |  | TR | 6.21.3.2 | informative | need discussion
235 | 31 | Wendong HU |  | TR | 6.21.3.2 | Efficiency and effectiveness issues will not be resolved until sensing methods are selected. Clarify the meaning of "mandatory" in Page 161, Line 4 | need assignment
236 | 32 | Wendong HU |  | TR | 6.21.3.2 | Issue: How to synchronize "dynamically allocated" fine sensing periods of overlapping WRANs? | need assignment
523 | 32 | Stephen KUFFNER |  | T | 6.21.3.2.1 | Refer this issue to WG | need discussion
46 | 33 | Gerald CHOUINARD |  | TR | 6.21.3.2.1 | [1] Scheduling Issues. [2] Sensing Architecture Issues. | need discussion
238 | 33 | Wendong HU |  | TR | 6.21.3.2.3 | Editorial Comment: Replace "following" by "subsequent" in Page 164, Line 15 | need assignment
241 | 34 | Wendong HU | Thomson (to Wen Gao?) | TR | 6.21.4.3 | Assign to Thomson to address this issue | need materials
244 | 35 | Wendong HU | Wendong Hu | TR | 6.21.5 | Assign to Wendong to bring the text from 802.16h | need materials
242 | 35 | Wendong HU | Wendong Hu | TR | 6.21.5 | Assign to Wendong to bring the text from 802.16h | need materials
47 | 35 | Gerald CHOUINARD | Carlos Cordeiro | TR | 6.21.5 | Assign to Carlos | need materials
136 | 35 | Liwen CHU |  | TR | 6.21.5 | Get the text from 802.16h. Note: currently, there is no proposal regarding this topic | need materials
95 | 36 | Carlos CORDEIRO |  | TR | 6.21.5.1 |  | Pending
176 | 37 | Wendong HU |  | TR | 6.3 |  | need assignment
331 | 37 | George VLANTIS |  | TR | 6.3 | Defer Green until presentation | Pending
13 | 39 | Gerald CHOUINARD |  | TR | 6.4 | Defer Green for the upstream OFDMA parameters (subchannelization) to be resolved. | Pending
179 | 41 | Wendong HU |  | TR | 6.5.1 |  | need assignment
16 | 41 | Gerald CHOUINARD |  | TR | 6.5.1 | Defer Green until discussion on superframes | Pending
17 | 41 | Gerald CHOUINARD |  | TR | 6.5.1 |  | need discussion
180 | 43 | Wendong HU | Carlos and Wendong | TR | 6.6.1.2 | Assign to Carlos and Wendong | need materials
Defer for Discussion (Yellow)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
61 | 1 | Soo-Young CHANG |  | TR |  |  | need materials
508 | 8 | Stephen KUFFNER |  | T | 6.13.1 | pending normative text for annex | pending
106 | 8 | Carlos CORDEIRO |  | TR | 6.13.1 | pending normative text for annex | pending
Defer for Discussion (Salmon)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
186 | 7 | Wendong HU |  | TR | 6.11.1 |  | need discussion | 22-06-0229-00-0000
68 | 9 | Soo-Young CHANG |  | TR | 6.15 |  | need discussion | 22-06-0126-01-0000_Huawei_Network_Entry_and_Initialization
506 | 20 | Stephen KUFFNER |  | T | 6.21.2 |  | need discussion
505 | 21 | Stephen KUFFNER |  | T | 6.21.2 |  | need discussion
245 | 21 | Wendong HU |  | TR | 6.21.2 |  | need discussion
64 | 22 | Soo-Young CHANG |  | TR | 6.21.2 |  | need discussion
Defer for Discussion (Gray)
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
204 | 20 | Wendong HU |  | TR | 6.21.1.6 |  | need discussion
205 | 20 | Wendong HU |  | TR | 6.21.1.7 |  | need discussion
66 | 21 | Soo-Young CHANG |  | TR | 6.21.2 |  | need discussion | 22-06-0124-01-0000_Huawei_Inter-BS_Synchronization
226 | 29 | Wendong HU |  | TR | 6.21.3.2 |  | need discussion
Defer Until Submission
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent | Assignee | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
175 | 1 | Wendong HU |  | TR |  |  | need materials | 22-07-0051-00-0000_STM-Huawei_interBS_com_messages.ppt
202 | 18 | Wendong HU |  | TR | 6.21.1.5 | Defer Green until submission of text with simulations comparable to doc no. 22-05-105r1 | need materials
246 | 20 | Wendong HU |  | TR | 6.21.2 | Defer Salmon until submission | need materials
504 | 21 | Stephen KUFFNER |  | T | 6.21.2 | Defer Green until submission | need materials | 22-06-0228-00-0000_Scheduling_Connection_Based_Inter_BS_communications.doc
43 | 27 | Gerald CHOUINARD |  | TR | 6.21.3 | Defer Green until submission of text | need materials
521 | 28 | Stephen KUFFNER |  | T | 6.21.3 | Defer Green until submission of text | need materials
225 | 28 | Wendong HU |  | TR | 6.21.3.1 | Defer Green until submission of proposal. Reference from text of 802.16h. Assign it to Wendong | need materials
125 | 29 | Liwen CHU |  | TR | 6.21.3.2 | Defer Green until submission on how to synchronize inter-cell's quiet period if this mechansim is used. | need materials
45 | 32 | Gerald CHOUINARD |  | TR | 6.21.3.2 | Defer Green until submission on how to synchronize inter-cell's quiet period if this mechansim is used. | need materials
Defer: New Topics
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
55 | 7 | Soo-Young CHANG |  | TR | 6.10_ |  | need materials
56 | 7 | Soo-Young CHANG |  | TR | 6.11 |  | need materials
263 | 11 | Winston CALDWELL |  | TR | 6.15 | Defer Green. Need Contribution. | need assignment
57 | 11 | Soo-Young CHANG |  | TR | 6.15.1 |  | need materials
53 | 35 | Baowei JI |  | TR | 6.21.5 | Defer Green. New Topic | need discussion | 22-07-0021-01-0000_Revisit_CBP_and_Synchronization_of_Overlapping_WRAN.ppt
59 |  | Soo-Young CHANG |  | TR |  |  | need materials
Withdraw / Reject
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
110 | 12 | Carlos CORDEIRO |  | TR |  | Withdraw
189 | 12 | Wendong HU |  | TR |  | Withdraw
196 | 16 | Wendong HU |  | TR |  | Withdraw
200 | 18 | Wendong HU |  | TR |  | Withdraw
223 | 27 | Wendong HU |  | TR |  | Withdraw
527 | 40 | Stephen KUFFNER |  | T |  | Withdraw
19 | 43 | Gerald CHOUINARD |  | TR |  | Reject. Explanation is given.
530 | 45 | Stephen KUFFNER |  | TR |  | Withdraw
Unread / Unclassify
Comment No. | Page Number of 22-07-0035-01-0000 | Proponent |  | Common Type | Section and dependencies in P802-22_D0.2 | Remarks | Status | Any Update?
4 | 5 | Gerald CHOUINARD |  | ER | 6
383 | 5 | George VLANTIS |  | E | 6
5 | 5 | Gerald CHOUINARD |  | ER | 6.1
384 | 5 | George VLANTIS |  | E | 6.1.1
6 | 5 | Gerald CHOUINARD |  | ER | 6.1.1
385 | 6 | George VLANTIS |  | E | 6.1.1
386 | 6 | George VLANTIS |  | E | 6.1.1
7 | 6 | Gerald CHOUINARD |  | ER | 6.1.1
387 | 6 | George VLANTIS |  | E | 6.1.1
8 | 7 | Gerald CHOUINARD |  | ER | 6.1.1
350 | 7 | George VLANTIS |  | ER | 6.10_
351 | 8 | George VLANTIS |  | ER | 6.13.5.2
352 | 9 | George VLANTIS |  | ER | 6.13.5.2
343 | 9 | George VLANTIS |  | ER | 6.13.5.2
187 | 10 | Wendong HU |  | ER | 6.15
266 | 10 | Winston CALDWELL |  | TR | 6.15
31 | 13 | Gerald CHOUINARD |  | ER | 6.15.5.1
353 | 14 | George VLANTIS |  | ER | 6.20_
354 | 14 | George VLANTIS |  | ER | 6.20.9
32 | 14 | Gerald CHOUINARD |  | ER | 6.21.1
33 | 15 | Gerald CHOUINARD |  | ER | 6.21.1.1
34 | 15 | Gerald CHOUINARD |  | ER | 6.21.1.2
35 | 16 | Gerald CHOUINARD |  | ER | 6.21.1.3
38 | 19 | Gerald CHOUINARD |  | ER | 6.21.1.5
48 | 36 | Gerald CHOUINARD |  | ER | 6.21.5.1
9 | 38 | Gerald CHOUINARD |  | ER | 6.3
10 | 38 | Gerald CHOUINARD |  | ER | 6.3
332 | 40 | George VLANTIS |  | E | 6.4
20 | 43 | Gerald CHOUINARD |  | ER | 6.7.3
342 | 46 | George VLANTIS |  | ER | 6.8.15.3.3.2
89 | 47 | Carlos CORDEIRO |  | TR | 6.8.2
90 | 47 | Carlos CORDEIRO |  | TR | 6.8.2
63 | 48 | Soo-Young CHANG |  | TR | 6.8.2
91 | 48 | Carlos CORDEIRO |  | TR | 6.8.2
154 | 48 | Steve SHELLHAMMER |  | T | 6.8.22.1.1
153 | 48 | Steve SHELLHAMMER |  | T | 6.8.22.1.1
155 | 48 | Steve SHELLHAMMER |  | T | 6.8.22.3.1
28 | 48 | Gerald CHOUINARD |  | ER | 6.8.22.3.1.1
158 | 49 | Steve SHELLHAMMER |  | TR | 6.8.22.3.1.1
159 | 49 | Steve SHELLHAMMER |  | TR | 6.8.22.3.1.1
92 | 49 | Carlos CORDEIRO |  | TR | 6.8.22.3.1.2
29 | 49 | Gerald CHOUINARD |  | TR | 6.8.22.3.1.6
182 | 49 | Wendong HU |  | TR | 6.8.23
184 | 49 | Wendong HU |  | TR | 6.8.25
183 | 50 | Wendong HU |  | TR | 6.8.25
347 | 50 | George VLANTIS |  | T | 6.8.28
346 | 50 | George VLANTIS |  | T | 6.8.28.10
268 | 50 | George VLANTIS |  | T | 6.8.28.10
344 | 50 | George VLANTIS |  | TR | 6.8.28.9
345 | 50 | George VLANTIS |  | TR | 6.8.28.9
23 | 51 | Gerald CHOUINARD |  | TR | 6.8.3.1
368 | 51 | George VLANTIS |  | TR | 6.8.3.2
185 | 51 | Wendong HU |  | T | 6.8.30_
348 | 51 | George VLANTIS |  | TR | 6.8.30_
24 | 51 | Gerald CHOUINARD |  | TR | 6.8.4.1
25 | 51 | Gerald CHOUINARD |  | TR | 6.8.4.1.2.1
480 | 52 | Stephen KUFFNER |  | TR | 6.8.7.3.7.10
157 | 52 | Steve SHELLHAMMER |  | TR | 6.8.7.3.7.9
156 | 52 | Steve SHELLHAMMER |  | TR | 6.8.7.3.7.9
481 | 52 | Stephen KUFFNER |  | T | 6.8.8.10.13
482 | 52 | Stephen KUFFNER |  | T | 6.8.8.10.14
181 | 52 | Wendong HU |  | TR | 6.8.8.22.1
124 | 53 | Liwen CHU |  | TR | Figure 41
116 | 53 | Liwen CHU |  | TR | Table 1
117 | 53 | Liwen CHU |  | TR | Table 1
118 | 53 | Liwen CHU |  | T | Table 1
135 | 53 | Liwen CHU |  | T | Table 162
120 | 53 | Liwen CHU |  | T | Table 21
121 | 53 | Liwen CHU |  | T | Table 25
122 | 54 | Liwen CHU |  | T | Table 30
123 | 54 | Liwen CHU |  | T | Table 37
119 | 54 | Liwen CHU |  | TR | Table 8
Total: 232

## References
References: