IEEE P802.22
Wireless RANs

| IEEE 802.22.2 PAR Extension Form |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date: 2010-11-08 |  |  |  |  |
| Author(s): |  |  |  |  |
| Name | Company | Address | Phone | email |
| Apurva Mody | BAE Systems | P. O. Box 868, MER 15-2350 Nashua, NH, 03061 | 603-809-0459 | apurva.mody@baesystesms.com apurva_mody@yahoo.com |
| Winston Caldwell | Fox |  | 310-369-4367 | winston.caldwell@fox.com |

Abstract

The following document is the PAR Extension Form for the IEEE 802.22.2 Standard with a request to extend the PAR by a duration of two years

Notice: This document has been prepared to assist IEEE 802.22. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s).  The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.

Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication.  The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.22.

Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures

<http://standards.ieee.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard."  Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication.  Please notify the Chair Apurva N. Mody <apurva.mody@ieee.org> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.22 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

    - P802.22.2 PAR Extension Form

This PAR is valid until 31-Dec-2010. The original PAR was approved on 15-Sep-2006
PAR Extension Request Date: 09-Jul-2010
Extension Request Submitter Email: apurva_mody@yahoo.com
Why is an extension required?:

The IEEE P802.22.2 WG is requesting the PAR extension by duration of Two years for the following reasons –

- IEEE P802.22.2 Progress Report – The P802.22.2 is currently in its Working Group Letter Ballot 1.0 Comment Resolution Phase.

- The development of IEEE P802.22.2 is dependent upon the advancement of IEEE P802.22 Standard - IEEE P802.22.2 is a Standard for the Recommended Practice for the Installation and Deployment of IEEE P802.22 Systems. Hence the development of this standard for the recommended practice for installation and deployment of P802.22 systems relies on the advancement of the IEEE P802.22 base standard. The P802.22 Standard is mature enough at this time and is likely to go to the sponsor ballot in December 2010.

- The P802.22 WG knows how to complete projects – P802.22.1 Project has been completed. The 802.22.1-2010 Standard was published on November 1st  2010. We will leverage our past experience from 802.22.1 to make sure that the P802.22 project gets completed on time.

Do the title, scope and purpose match that of the current draft?: Yes
Number of Previous Extensions Requested: 0
Number of Years Being Requested: 2
Document Development Information
   a. What date did you begin writing the first draft?:  30-Jul-2010
   b. How many people are actively working on the project?: 15

c. How many times a year does the working group meet?
      In person?: 6
      Via teleconference?: 0
   d. How many times a year is a draft circulated to the working group via electronic means?: 2
   e. What percentage of the Draft is stable?: 30%
   f. How many significant work revisions has the Draft been through?: 0
Project Plan
   When will IEEE sponsor balloting begin?: 15-Nov-2011
   When do you estimate that the final IEEE Sponsor ballot will be completed?: 12-Sep-2012
   When do you expect to submit the proposed standard to RevCom?: 15-Oct-2012
Has this document already been adopted by another source?: No

For an extension request, the information on the original PAR below is not open to modification.

Submitter Email: wk3c@wk3c.com
Type of Project: New IEEE Standard

1.1 Project Number: P802.22.2
1.2 Type of Document: Recommended Practice
1.3 Life Cycle: Full Use

2.1 Title: Recommended Practice for Information Technology - Telecommunications and information exchange between systems - Wireless Regional Area Networks (WRAN) - Specific requirements - Part 22.2: Recommended Practice for the Installation and Deployment of IEEE 802.22 Systems

3.1 Working Group: Wireless Regional Area Networks Working Group (C/LM/WG802.22)
Contact Information for Working Group Chair
   Name: Apurva Mody
   Email Address: apurva_mody@yahoo.com
   Phone: 404-819-0314
Contact Information for Working Group Vice-Chair
   Name: Gerald Chouinard
   Email Address: gerald.chouinard@crc.ca
   Phone: 613-998-2500

3.2 Sponsoring Society and Committee: IEEE Computer Society/LAN/MAN Standards Committee (C/LM)
Contact Information for Sponsor Chair
   Name: Paul Nikolich
   Email Address: p.nikolich@ieee.org
   Phone: 857.205.0050
Contact Information for Standards Representative
None

4.1 Type of Ballot: Individual
4.2 Expected Date of submission of draft to the IEEE-SA for Initial Sponsor Ballot: 11/2007
4.3 Projected Completion Date for Submittal to RevCom: 03/2008

5.1 Approximate number of people expected to be actively involved in the development of this project: 30
5.2 Scope: This document recommends best engineering practices for the installation and deployment of IEEE 802.22 systems to help assure that such systems are correctly installed and deployed.
5.3 Is the completion of this standard dependent upon the completion of another standard: Yes
If yes please explain: To finalize this document the base 802.22 standard will need to be finalized. However, this document needs to be developed in parallel with the base 802.22 standard so that it will be available when 802.22 systems begin to be deployed.

5.4 Purpose: This document provides detailed technical guidance to installers, deployers, and operators of IEEE 802.22 compliant systems to help assure that such systems are correctly installed and deployed.
5.5 Need for the Project: Correct installation and deployment of IEEE 802.22 compliant systems are important to assure that those systems will maximally achieve their design goals in terms of system performance, reliability, and non-interference to incumbent licensed systems with which they will share the TV broadcast bands.
5.6 Stakeholders for the Standard: Stakeholders are installers, operators, users, and manufacturers of IEEE 802.22 systems.

Intellectual Property
6.1.a. Is the Sponsor aware of any copyright permissions needed for this project?: No
6.1.b. Is the Sponsor aware of possible registration activity related to this project?: No

7.1 Are there other standards or projects with a similar scope?: No
7.2 International Activities
   a. Adoption
   Is there potential for this standard (in part or in whole) to be adopted by another national, regional or international organization?: No
   b. Joint Development
   Is it the intent to develop this document jointly with another organization?: No
   c. Harmonization
   Are you aware of another organization that may be interested in portions of this document in their standardization development efforts?: No

8.1 Additional Explanatory Notes (Item Number and Explanation):