## Title
IEEE P802.22.2 Wireless RAN Recommended Practice
Submission
Designator: | doc.: IEEE 802.22-11/0145r01
Venue Date: | December 2011
First Author: | Gerald Chouinard, Communications Research Centre, Canada (CRC)
Subject: | IEEE P802.22.2 WRAN Recommended Practice Draft 3.0 Ballot Comments Database
Full Date: | 2011-12-19
Author(s): | Name(s) | Gerald Chouinard
| Company | Communications Research Cente
| Address | 3701 Carling Avenue, Ottawa, Canada K2H-8S2
| Phone: | 613-998-2500
| Fax: | 613-990-6339
| email: | gerald.chouinard@crc.ca
Abstract:
This spreadsheet contains all the comments from the 802.22 voting members on the new 802.22 Draft 3.0. This spreadsheet is to gather the votes, the comments and the suggested remedies from the voting members toward a more acceptable 802.22.2 Standard.
Note: This work-book is best viewed on a 1600x1200 pixels screen.
Notice: This document has been prepared to assist IEEE 802.22. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.22.
Patent Policy and Procedures: The contributor is familiar with the IEEE 802 Patent Policy and Procedures
<http://standards.ieee.org/guides/bylaws/sb-bylaws.pdf>, including the statement "IEEE standards may include the known use of patent(s), including patent applications, provided the IEEE receives assurance from the patent holder or applicant with respect to patents essential for compliance with both mandatory and optional portions of the standard." Early disclosure to the Working Group of patent information that might be relevant to the standard is essential to reduce the possibility for delays in the development process and increase the likelihood that the draft publication will be approved for publication. Please notify the Chair <apurva.mody@baesystems.com> as early as possible, in written or electronic form, if patented technology (or technology under patent application) might be incorporated into a draft standard being developed within the IEEE 802.22 Working Group. If you have questions, contact the IEEE Patent Committee Administrator at <patcom@ieee.org>.

## Instructions for ballot
Instructions for the electronic ballot of the 802.22.2 Draft 3.0
This spreadsheet contains the template for the 802.22 voters to fill in their comments on the 802.22.2 Draft 3.0. This Draft 3.0 contains the cleaned-up version of the 802.22.2 Draft as of 16 November 2011. The detailed changes made to the Draft 2.0 are also highlighted in the 'redline' version of Draft 3.0 in 'track change' and comments were added to refer to the corresponding comment resolutions in the Comment Database (22-11-111r9). All the information is available to trace back the discussions that took place. Note that if the text for the resolution is longer than 256 characters, you may need to click once on the cell to show the entire text in the content window at the top of the spreadsheet or click twice to show the entire formatted content in the cell. Since this is a re-circulation ballot, comments will be accepted only for the sections of the Draft where changes have been made as indicated in Draft 3.0 or for other sections that may be affected by the changes to the modified sections. For the purpose of this rule, a section may refer to a paragraph.
The commentor should enter his/her coordinates once in columns B to D and then hide it for the rest of the process for convenience (highlight the four columns and right-click on it and then click on 'Hide').
The commentor should then enter all his comments, one per row, by filling columns F to J to locate the specific text that is commented on. Page and Line will be used to refer to the text only in the cleaned-up version of Draft 3.0 whereas Clause, Subclause and Paragraph will be used to go across the various newer versions of the Draft.
The commentor should indicate the type for each of his comments: TR: Technical comment for which proper resolution is required for the commentor to support the modified Draft. T: Technical comment for which the resolution is not necessary of the commentor to support the Draft. ER: Editorial comment for which proper resolution is required for the commentor to support the modified Draft. E: Editorial comment for which the resolution is not necessary of the commentor to support the Draft.
The commentor should fill in his comment in detail in column L. Text can be copied in and edited if it is convenient.
The commentor should then indicate his suggested remedy in column M. Text formatting supported by Excel is allowed such as bold, underline, strike-out, etc. to facilitate identification of the actual changes to the text. Note that a change of paragraph within a cell is done by the "Alt/Enter" combination. If the comment is extensive and/or includes graphics, etc., it is recommended to produce a normal 802.22 WG contribution with the usual template and upload it on Mentor and refer to it by its document number or a hyperlink to its URL in the appropriate cell. Note that if the text for the resolution is longer than 256 characters, you may need to click once on the cell to show the entire text in the content window at the top of the spreadsheet or click twice to show the entire formatted content in the cell.
The commentor is requested to answer the question on the right of this Table once he has developed all his comments on Draft 3.0. His vote should represent his overall position relative to his support for Draft v3.0. Note that indicating any of his comments as TR or ER means a "Disapprove with comment". | Please, indicate your overall support status for the 802.22.2 Draft 2.0 by selecting one of the following options: | Approve - No Comments
Approve - with comments (Technical, Editorial or General)
Disapprove - No Comments
Disapprove - with Comments (Technical Required, Editorial Required or General Required)
The commentors should return their version of the spreadsheet with their initials added at the end of the file name (e.g., 22-11-0143-00-0002 WRAN Recommended Practice Draft 3.0 Electronic Ballot Template-GC.xls) to Gerald Chouinard <gerald.chouinard@crc.ca> before the end of the 15 days comment period ending on Thursday, December 1st, 2011. |  | Abstain - lack ot time
Abstain - lack of expertise
Abstain - Conflict of interest
Abstain - Others
A compilation of the comments from all respondents will be made available during the second week of December so that the new comment resolution process can start soon after over teleconference calls.
The approval status for the 802.22.2 Draft 2.0 has been included as the third tab in this spreadsheet. Since this is a re-circulation ballot, the votes indicated in the most recent circulation cycle still hold and, the absence of a return vote will be interpreted as if the voter is keeping his same position. The previous vote will also be counted towards the return ratio. A continued 'disapprove' vote will however need to be documented through appropriate comments in this re-circulation ballot.

## Approval status for the Draft
First Electronic Ballot in August 2010 |  |  |  |  | Second Electronic Ballot in September 2011 |  | First re-circulation ballot in November 2011
Draft 1.0 |  |  |  |  | Draft 2.0 |  | Draft 3.0
Commentor | Company | email | Vote | WG Chairmen | Voting status | Vote | Voting status | Vote
Buchwald, Greg | Motorola | greg.buchwald@motorola.com |  |  | Voter | Approve, no comment. | Voter | Approve, no comment.
Caldwell, Winston | Fox | winston.caldwell@fox.com | Approve, no comments. |  | Voter | Approve, no comment. | Voter | Approve, no comment.
Chouinard, Gerald | CRC | gerald.chouinard@crc.ca | Oppose. |  | Voter | Approve, with comments. | Voter | Approve, no comment.
Das, Subir | Telcordia | subir@research.telcordia.com |  |  | New voter |  | New voter
Einolf, Charles | NABA | c.einolf@ieee.org | Oppose. |  | Voter | Approve, no comment. | Voter | Approve, no comment.
Gurley, Tom | IEEE BTS | tgurley@ieee.org | Approve, no comments. |  | Voter | Disapprove, with comments. | Voter | Approve, with comments.
Harada, Hiroshi | NICT | harada@nict.go.jp |  |  | New voter | Approve, no comment. | New voter | Approve, no comment.
Heile, Bob | ZigBee Alliance | bheile@ieee.org |  | Y | Voter |  | Voter
Hu, Wendong | ST Microelectronics | wendong.hu@st.com |  |  | No longer voter |  | No longer voter
Hwang, SungHyun | ETRI | shwang@etri.re.kr | Approve, with comments. |  | Voter | Approve, with comments. | Voter | Approve, with comment.
Kalke, Jerry | CBS | jkalkesr@att.net | Approve, with comments. |  | Voter | Approve, no comment. | Voter | Approve, no comment.
Kiernan, Thomas | US Army | thomas.kiernan@us.army.mil |  |  | No longer voter |  | No longer voter
Ko, Gwangzeen | ETRI | gogogo@etri.re.kr | Approve, no comments. |  | Voter | Approve, with comments. | Voter | Approve, no comment.
Kraemer, Bruce | Marvell | bkraemer@marvell.com | Approve, no comments. | Y | Voter | Approve, no comment. | Voter | Approve, no comment.
Lei, Zhongding | I2R | leizd@i2r.a-star.edu.sg | Approve, with comments. |  | Voter | Approve, no comment. | Voter | Approve, no comment.
Li, Lingjie | Wi-Lan | jli@wilan.com | Approve, no comments. |  | Voter | Approve, no comment. | Voter | Approve, no comment.
Lynch, Mike | MJLynch Associates | freqmgr@sbcglobal.net | Approve, no comments. | Y | Voter | Approve, no comment. | Voter | Approve, no comment.
Mody, Apurva | BAE Systems | apurva_mody@baesystems.com | Oppose. | Y | Voter | Disapprove, with comments. | Voter | Approve, with comment.
Nikolich, Paul | IEEE 802 Chair | p.nikolich@ieee.org |  | Y | Voter | Abstain | Voter | Abstain
Rahman, Aziz | NICT | aziz@nict.go.jp |  |  | Voter | Abstain | Voter | Approve, no comment.
Reddy, Ranga | US Army | ranga.reddy@us.army.mil | Approve, with comments. |  | Voter | Approve, no comment. | Voter | Approve, no comment.
Reede, Ivan | Amerisys | i_reede@amerisys.com | Approve, no comments. |  | Voter | Approve, no comment. | Voter | Approve, no comment.
Sasaki, Shigenobu | Niigata | kojiro@eng.niigata-u.ac.jp | Approve, with comments. |  | Voter | Disapprove, with comments. | Voter | Approve, with comments.
Shellhammer, Steve | Qualcomm | sshellha@qualcomm.com | Abstain. | Y | Voter | Abstain. | Voter | Abstain
Tawil, Victor | MSTV | vtawil@mstv.org | Approve, no comments. |  | Voter |  | Voter
Um, Jung-Sun | ETRI | korses@etri.re.kr | Approve, no comments. |  | No longer voter |  | No longer voter
Wang, Jianfeng | Philips | jianfeng.wang@philips.com | Approve, no comments. |  | No longer voter |  | No longer voter
Zhang, Xin | NICT | amy_z_x@hotmail.com |  |  | New voter | Abstain | New voter
Total # | # Respondents | Return Ratio | Approve Rate |  | Total # | # Respondents | Total # | # Respondents
25 | 19 | 76% | 83.33% |  | 24 | 21 | 24 | 20
[5 empty] | Return Ratio | Approve Ratio | Return Ratio | Approve Ratio
[5 empty] | 87.5% | 82.35% | 83.33% | 100%
Note on J4: No response to the first re-circulation. Voter position expressed at the second main ballot still holds.
Note on J5: Bold: Voter responded to the first re-circulation.

## 802.22.2 D3.0 Comments
ID | Commenter Name | Affiliation | Email | Telephone | Clause | Subclause | Paragraph | Page | Line | Type | Comment | Suggested Remedy | Resolution | Comment Status | WG Status | Response Status | Editor Comments | Code
2 | Mody, Apurva | BAE Systems | apurva.mody@ieee.org | 404-819-0314 | 0 | 0 | 0 | 0 | 0 | E | Please harmonize all the Comment Resolution Statuses from previous Comment Ballots. You should either use Accept, Reject, Revised, Abstain or Agree, Disagree, Principle and Abstain. | Please harmonize all the Comment Resolution Statuses from previous Comment Ballots. You should either use Accept, Reject, Revised, Abstain or Agree, Disagree, Principle and Abstain | There is a difference between the overall vote that a participant can give and the resolution that can be assigned to a specific comment provided by a participant. In the first case, the following key words would apply: "Approve", "Disapprove" and "Abstain". In the second case, the following key words would apply: "Accept", "Reject" and "Revise". What is being proposed are two options for, it seems, the resolution of a comment rather than the overall vote. In this context, the word "Abstain" does not make sense since the WG should not abstain from resolving a comment. This proposed remedy needs to be discussed and clarified. Proposed resolution: Change "Counter" for "Revise" for the "Comment Status". | Revise |  | Closed | This comment is related to the TG2 Comments Database format and not the 802.22.2 Draft. (Note that the proposed change has been made for this Comments Database and for the two previous TG2 Comments Databases: 22-10-0161r8 and 22-11-0111r10.) | 2
3 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 5 | 5.1.2.1 | 2 | 7 | 33 | E | The statement that the 802.22 device would "exceed the D/U ratio" is confusing since, in this context, the 802.22 device is the U in the denominator. | Replace "exceed" with "unacceptably lower". | "These statistics would determine where an 802.22 device would exceed the produce an unacceptably low D/U ratio (Recommendation 5.1.1.2) in the unit areas where the DTV and/or analog TV services need to be legally protected from harmful interference (see 5.1.2.2 and 5.1.2.3)." | Revise |  | Closed |  | 0
4 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 5 | 5.2.2.1 | 1 | 10 | 4 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Do System planners should not cause harmful interference into the protected licensed services. | See resolution of comment #5. | Revise |  | Closed |  | 0
5 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 5 | 5.2.2.1 | 1 | 10 | 4 | E | Imperative sentence should be rewritten. | Revised sentence: "WRAN devices should avoid to cause harmful interference …" | "Do WRAN devices should not cause harmful interference into the protected licensed services." | Revise |  | Closed |  | 0
6 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 5 | 5.2.2.1.1 | 1 | 10 | 11 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Do System planners should not allow the CPE ... | See resolution of comment #7. | Revise |  | Closed |  | 0
7 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 5 | 5.2.2.1.1 | 1 | 10 | 11 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE should not be located closer than …" |  | Accept |  | Closed |  | 0
8 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 5 | 5.2.2.1.1 | 4 | 11 | 25 | E | TVBD has not been defined. | Delete "TVBD". |  | Accept |  | Closed |  | 0
9 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 5 | 5.2.2.3.2 | 1 | 13 | 17 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Prevent System planners should prevent BS interference … |  | Accept |  | Closed |  | 0
10 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 5 | 5.2.2.3.2 | 1 | 13 | 17 | E | Imperative sentence should be rewritten. | Revised sentence: "The system planner should prevent BS interference into …" | See resolution of comment #9. | Revise |  | Closed |  | 0
11 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 5 | 5.3 | 1 | 15 | 29 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Use System planners should use CPEs ... | "Use CPEs with two separate RF chains for WRAN operation and for RF sensing should be used." | Revise |  | Closed |  | 0
12 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 5 | 5.3 | 1 | 15 | 29 | E | Imperative sentence should be rewritten. | Revised sentence: "CPEs should be used with ..." | See resolution of comment #11. | Revise |  | Closed |  | 0
13 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 5 | 5.4 | 1 | 16 | 6 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Use System planners should use CPEs ... | "Use CPEs whose residual delay has been measured by the manufacturer with an accuracy of at least +/- 30 nsec should be used. | Revise |  | Closed |  | 0
14 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 5 | 5.4 | 1 | 16 | 6 | E | Imperative sentence should be rewritten. | Revised sentence: "CPEs should be used whose residual ..." | See resolution of comment #13. | Revise |  | Closed |  | 0
15 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6 | 2 | 16 | 23 | E | "NARTE" should be "iNARTE" | "NARTE" > "iNARTE" |  | Accept |  | Closed |  | 0
16 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.1.1 | 1 | 16 | 35 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should use Install only ... | "The installer should useInstall only certified 802.22 equipment that has been certified to meet local regulations and the requirements of the 802.22 Standard. | Revise |  | Closed |  | 0
17 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.1 | 1 | 16 | 35 | E | Imperative sentence should be rewritten. | Revised sentence: "The installer should install only …" | See resolution of comment #16. | Revise |  | Closed |  | 0
18 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.1.3 | 1 | 17 | 4 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should Do not ... |  | Accept |  | Closed |  | 0
19 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.1.3 | 1 | 17 | 4 | E | Imperative sentence should be rewritten. | Revised sentence: "WRAN equipment should be installed with …" | See resolution of comment #18. | Revise |  | Closed |  | 0
20 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.1.4 | 1 | 17 | 6 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Utilize appropriate Appropriate weather stripping tape should be applied to any ... |  | Accept |  | Closed |  | 0
21 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.1.4 | 1 | 17 | 6 | E | Imperative sentence should be rewritten. | Revised sentence: "Appropriate weather stripping tape should be utilized to …" | See resolution of comment #20. | Revise |  | Closed |  | 0
22 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.1.5.2 | 1 | 17 | 23 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should Check check nearby ... |  | Accept |  | Closed |  | 0
23 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.1.5.2 | 1 | 17 | 23 | E | Imperative sentence should be rewritten. | Revised sentence: "The installer should check nearby TV installations …" | See resolution of comment #22. | Accept |  | Closed |  | 0
24 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.1.5.3 | 1 | 17 | 26 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should Ensure ensure ... |  | Accept |  | Closed |  | 0
25 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.1.5.3 | 1 | 17 | 26 | E | Imperative sentence should be rewritten. | Revised sentence: "The installer should ensure that …" | See resolution of comment #24. | Accept |  | Closed |  | 0
26 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.3 | 1 | 18 | 10 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should configure Configure the BS ... | See resolution of comment #27. | Revise |  | Closed |  | 0
27 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.2.3 | 1 | 18 | 10 | E | Imperative sentence should be rewritten. | Revised sentence: "The BS should be configured with …" |  | Accept |  | Closed |  | 0
28 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.4 | 1 | 18 | 12 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should configure Configure the BS ... | See resolution of comment #28. | Revise |  | Closed |  | 0
29 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.2.4 | 1 | 18 | 12 | E | Imperative sentence should be rewritten. | Revised sentence: "The BS should be configured with …" |  | Accept |  | Closed |  | 0
30 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.5 | 4 | 18 | 32 | E | Apostrophe after "its" should be deleted. | Delete apostrophe after "its" |  | Accept |  | Closed |  | 0
31 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.6.1 | 1 | 19 | 13 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should Use use ... |  | Accept |  | Closed |  | 0
32 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.2.6.1 | 1 | 19 | 13 | E | Imperative sentence should be rewritten. | Revised sentence: "A transmit/receive antenna at the BS should be used with …" | See resolution of comment #31. | Revise |  | Closed |  | 0
33 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.6.2 | 1 | 19 | 17 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should Orient orient ... |  | Accept |  | Closed |  | 0
34 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.2.6.2 | 1 | 19 | 17 | E | Imperative sentence should be rewritten. | Revised sentence: "The BS transmit/receive antenna should be oriented so that …" | See resolution of comment #33. | Revise |  | Closed |  | 0
35 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.7 | 1 | 19 | 22 | E | The word "it" refers to two different things. | The sensing antenna should be mounted above the transmit antenna if they are not integrated. it is not integrated to it. |  | Accept |  | Closed |  | 0
36 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.7.1 | 1 | 19 | 24 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should use Use ... |  | Accept |  | Closed |  | 0
37 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.2.7.1 | 1 | 19 | 24 | E | Imperative sentence should be rewritten. | Revised sentence: "The BS sensing antenna should be used with …" | See resolution of comment #36. | Revise |  | Closed |  | 0
38 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.7.2 | 1 | 19 | 29 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | decrease the sensing threshold the sensing threshold should be decreased by ... |  | Accept |  | Closed |  | 0
39 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.8 | 1 | 19 | 33 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | The installer should make Make ... |  | Accept |  | Closed |  | 0
40 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.2.8 | 1 | 19 | 33 | E | Imperative sentence should be rewritten. | Revised sentence: "The GPS unit should be located …" | See resolution of comment #39. | Revise |  | Closed |  | 0
41 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.2.8 | 1 | 20 | 3 | E | Sentence might read better if "to" is added after second "not". | ... will need not to be exceeded. |  | Accept |  | Closed |  | 0
42 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.3 | 1 | 20 | 14 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Prevent CPE transmissions should be prevented absent ... |  | Accept |  | Closed |  | 0
43 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.3 | 1 | 20 | 14 | E | Imperative sentence should be rewritten. | Revised sentence: "Installer should install CPE not to transmit unless reliable verification of the Recommendations … is guaranteed." | See resolution of comment #42. | Revise |  | Closed |  | 0
44 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.4 | 1 | 20 | 17 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Employ provisions Provisions should be employed to ... |  | Accept |  | Closed |  | 0
45 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.4 | 1 | 20 | 17 | E | Imperative sentence should be rewritten. | Revised sentence: "Employ Pprovisions to prevent the use of antenna equipment that … 6.3.1-6.3.3 should be employed." | See resolution of comment #44. | Revise |  | Closed |  | 0
46 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.1 | 1 | 20 | 21 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Enforce a A minimum separation should be enforced … | "Enforce aA minimum separation distance should be enforced as specified in the last row of Table 1 between the CPE transmit/receive antenna and TV receiving antennas as a function of the type of CPE used." | Revise |  | Closed |  | 0
47 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.1 | 1 | 20 | 21 | E | Imperative sentence should be rewritten. | Revised sentence: "A minimum separation distance is enforced as specified …" | See resolution of comment #46. | Revise |  | Closed |  | 0
48 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.2 | 1 | 20 | 24 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Enforce a A minimum separation distance should be enforced ... | See resolution of comment #49. | Revise |  | Closed |  | 0
49 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.2 | 1 | 20 | 24 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE transmit/receive antenna should be oriented so that …" |  | Accept |  | Closed |  | 0
50 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.3 | 1 | 20 | 27 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Install the The CPE transmit/receive antenna should be installed ... |  | Accept |  | Closed |  | 0
51 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.3 | 1 | 20 | 27 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE transmit/receive antenna should be installed so that …" |  | Accept |  | Closed |  | 0
52 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.4 | 1 | 21 | 2 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Avoid cable Cable and connectors leakage should be avoided ... |  | Accept |  | Closed |  | 0
53 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.4 | 1 | 21 | 2 | E | Imperative sentence should be rewritten. | Revised sentence: "Cable and connectors leakage should be avoided between …" |  | Accept |  | Closed |  | 0
54 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.6 | 1 | 21 | 13 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Install the The CPE transmit/receive antenna should be installed ... |  | Accept |  | Closed |  | 0
55 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.6 | 1 | 21 | 13 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE transmit/receive antenna should be installed outdoors at …" |  | Accept |  | Closed |  | 0
56 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.7 | 1 | 21 | 16 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Orient the The CPE transmit/receive antenna should be oriented ... |  | Accept |  | Closed |  | 0
57 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.7 | 1 | 21 | 16 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE transmit/receive antenna should be oriented toward …" |  | Accept |  | Closed |  | 0
58 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.8 | 1 | 21 | 17 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE transmit/receive antenna should be re-oriented toward …" |  | Accept |  | Closed |  | 0
59 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.8 | 1 | 21 | 18 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Re-orient the The CPE transmit/receive antenna should be re-oriented ... |  | Accept |  | Closed |  | 0
60 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.9 |  | 21 | 21 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Further adjust the The CPE transmit/receive antenna should be further adjusted ... |  | Accept |  | Closed |  | 0
61 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.9 | 1 | 21 | 21 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE transmit/receive antenna should be adjusted further to minimize …" | See resolution of comment #60. | Revise |  | Closed |  | 0
62 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.10 | 1 | 21 | 24 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Adjust the orientation of fixed Fixed CPE transmit/receive antennas should be oriented ... | See resolution of comment #63. | Revise |  | Closed |  | 0
63 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.10 | 1 | 21 | 24 | E | Imperative sentence should be rewritten. | Revised sentence: "The orientation of fixed CPE transmit/receive antenna should be adjusted so that …" |  | Accept |  | Closed |  | 0
64 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.10 | 1 | 21 | 25 | E | "extend" should be "extent" | "extend" > "extent" |  | Accept |  | Closed |  | 0
65 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.5.11 | 1 | 21 | 29 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Mount the The CPE transmit/receive antenna should be mounted ... |  | Accept |  | Closed |  | 0
66 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.5.11 | 1 | 21 | 29 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE transmit/receive antenna should be mounted at the same…" |  | Accept |  | Closed |  | 0
67 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.6.1 | 1 | 22 | 3 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Install the The CPE sensing antenna should be installed ... |  | Accept |  | Closed |  | 0
68 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.6.1 | 1 | 22 | 3 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE sensing antenna should be installed outdoors …" |  | Accept |  | Closed |  | 0
69 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.6.1 | 1 | 22 | 4 | E | "it" refers to two different things. | Change "if it is not integrated with it" to "if they are not integrated". |  | Accept |  | Closed |  | 0
70 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.6.2 | 1 | 22 | 8 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Give The installer should give special attention ... |  | Accept |  | Closed |  | 0
71 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.6.2 | 1 | 22 | 8 | E | Imperative sentence should be rewritten. | Revised sentence: "Special attention to the installation of the sensing antenna should be given to make sure …" | See resolution of comment #70. | Revise |  | Closed |  | 0
72 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.6.3 | 1 | 22 | 11 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Use The installer should use ... |  | Accept |  | Closed |  | 0
73 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.6.3 | 1 | 22 | 11 | E | Imperative sentence should be rewritten. | Revised sentence: "The CPE sensing antenna should be used with …" | See resolution of comment #72. | Revise |  | Closed |  | 0
74 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.7 | 1 | 22 | 15 | E | The style should be changed from imperative to agree with previous style changes made in other parts of the document. | Make The installer should make .. |  | Accept |  | Closed |  | 0
75 | Tom Gurley | IEEE-BTS | tgurley@ieee.org | 252-443-3115 | 6 | 6.3.7 | 1 | 22 | 20 | E | Sentence might read better if "to" is added after second "not". | … need not to be exceeded |  | Accept |  | Closed |  | 0
76 | Shigenobu Sasaki | Niigata University | kojiro@eng.niigata-u.ac.jp | 81-25-262-6737 | 6 | 6.3.6.4 | 1 | 22 | 27 | E | Imperative sentence should be rewritten. | Revised sentence: "It should be confirmed that the GPS unit is located outdoors." | See resolution of comment #74. | Revise |  | Closed |  | 0
77 | Hwang, Sunghyun | ETRI, Korea | shwang@etri.re.kr | 82-42-860-1133 | Annex B |  |  | 26 | 2, 4, 16 | E | Figure A.1 and Figure A.2 should be Figure B.1 and Figure B.2. | Replace Figure A.1 and Figure A.2 with Figure B.1 and Figure B.2. |  | Accept |  | Closed |  | 0
Note on K1: TR: Technical required T: Technical ER: Editoral required E: Editorial
Note on O1: A= Accept B= Revise C: Reject D= Defer P= Pending S= Superceded
Note on P1: MA= Motion adopted MP= Motion pending MF= Motion failed AB= Approved Ballot FB= Failed Ballot
Note on Q1: O= Open C= Closed A= Abstain W= Withdrawn
Note on S1: 0 = no further change, 1= need editorial verification, up to 9 = need further discussions of increasing importance in WG 'system'

## References
References:
IEEEStd 802.22-2011, Wireless Regional Area Networks (WRAN) Part 22: Cognitive Wireless RAN Medium Access Control (MAC) and Physical Layer (PHY) Specifications: Policies and Procedures for Operation in the TV Bands, 1st July 2011.
IEEE P802.22 Draft Recommended Practice for the Installation and Deployment of IEEE 802.22 Systems, Draft 3.0, November 2011
802.22.2_D3.0_clean.pdf
802.22.2_D3.0_redline.pdf
22-11-0111-09-0002 IEEE P802.22.2 Recommended Practice Draft 2.0 Ballot Comments Database.xls