## Slide 1: OmniRAN EC SG November 2013 EC Opening Report
Chair:
Max Riegel (NSN)

## Slide 2: OmniRAN EC SG Status and Objectives
OmniRAN EC SG submitted PAR proposal on ‘Recommended Practice for Network Reference Model and Functional Description of IEEE 802 Access Network’ on October 10th for consideration in the November plenary meeting
  https://mentor.ieee.org/omniran/dcn/13/omniran-13-0086-00-ecsg-proposed-par-and-5c.docx
  PAR proposal creation outlined on next slide
It is proposed to run the project within 802.1 WG
  No conclusion yet, how this would/should work within 802.1 WG
  Technical discussions took place between OmniRAN EC SG and 802.1 (Security TG) in the September interim
OmniRAN EC SG will review comments on PAR proposal and will submit final proposal for the EC closing plenary.
Organizational arrangements of running the project in 802.1 will be discussed during the week (and in the EC workshop on Saturday)

## Slide 3: OmniRAN EC SG Timeline
F2F meeting
Conf Call
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug’7
Apr’11
May’2
Jun’20
Aug
Sep
Oct
Sep
Oct
‘4
‘17
‘27
‘4
‘10
Oct’11
Nov’11
Feb’28
Initial meeting
Use cases harmonization
Use cases contributions
Requirements within scope of IEEE 802
Gap analysis to existing solutions
Socializing of gap analysis
Refine scope of EC SG (crisp words)
Potential standardization topics for IEEE 802
Plan for PAR proposal submission until Oct’11
Create draft PAR proposal
Refine wording of draft PAR proposal
Finalize PAR proposal

## Slide 4: OmniRAN EC SG Plan Nov 2013 F2F
Meetings
  Tuesday, Nov 12th, 13:30 – 15:30
  Wednesday, Nov 13th, 08:00 – 10:00
  Wednesday, Nov 13th, 13:30 – 15:30
  Thursday, Nov 14th, 08:00 – 10:00
Meeting Room: Cockrell
Proposed Agenda:
  Call Meeting to Order
  Attendance recording, secretary
  Approval of minutes
  Reports
  Comment resolution and responses on PAR & 5C comments
  Presentation to closing EC meeting
  Conditional extension of OmniRAN EC SG
  Technical presentations on OmniRAN related matters
  AOB
  Adjourn

## Slide 5: OmniRAN ECSG Resources
Website: http://www.ieee802.org/OmniRANsg/
Document Archive on mentor: https://mentor.ieee.org/omniran/documents
Email reflector: ecsg-802-omniran@listserv.ieee.org
Email archive: http://grouper.ieee.org/groups/802/OmniRANsg/email/
Attendance: Paper list (normative) + IMAT
  IMAT mandatory for participants seeking attendence credits
  Reciprocal rights for most WGs