## Comments
Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied
Technical | 13 | 1.1 | 389 | When reading Scope and Purpose I did not at all get the understanding that this IEEE 802 document would be about a Backhaul network. In the context of IEEE 802.1, "access" typically refers to granting access to a LAN (e.g., using IEEE 802.1X). | Clarify in the Scope and Purpose the type of network that an "access network" is intended to be and how it differs from LAN access. Both of these sections need to be a lot more clear in descibing what is an access newtork, and why it is different from existing network topology definitions. | Yes | Brian | Max will write a motivation section at the beginning of chapter 6: https://mentor.ieee.org/omniran/dcn/17/omniran-17-0039-00-CF00-chapt-6-intro-amendment-proposal.docx accepted
Editorial | 16 | 4.1 | 461 | Spell out AP, BS in e.g. clause | Node of Attachment (e.g. Access Point, or Base Station) | No | Max | o.k
Editorial | 23 | 6.1.5 | 575 | Reference provided to legacy version of 802.1Q standard. | Reference not really needed; either update to 3.207 of 802.1Q-2014, or remove reference completely | No | Max | Remove complete clause containing the 802.1Q reference.
Technical | 24 | 6.2 | 608 | The name "IEEE 802 Network Reference Model" sounds like it is intended to describe all of IEEE 802 networks. But Figure 5 shows something that looks more like a form of carrier bridging, and it does not claim to be an example, but rather define the model. | Please consider whether "IEEE 802 Network Reference Model" is too wide of a scope for this document because it is intended to solve a particular access problem to SP newtorks. Or alternatively, if it is intended to cover all of IEEE 802 network topologies then this needs to be better motivated in this section. | Yes | Brian | Change heading of chapter 6 to 'Network Reference Model for Access Network'
Technical | 29 | 6.3.2 | 725 | inapporiate use of 'controller' | delete 'controller' | Yes | Hao | o.k.
Technical | 29 | 6.3.2 | 730 | inapporiate use of 'controller' | delete two usage of 'controller' | Yes | Hao | o.k. Mention access network and access router instead of access network controller and access router controller, respectively.
Technical | 33 | 6.7 | 832 | Sentence misses explanation of what kind of operational parameters can be adapted. | Add to the end of the sentence: " of the shared processing and transmission resources." | Yes | Max | o.k
Technical | 34 | 6.7.1 | 841 | Unclear meaning of 'It does not, however, show the particulars of a virtualized infrastructure.' | Change to "It does not, however, show the internal structure and operation of a virtualized infrastructure." | Yes | Max | o.k
Technical | 37 | 6.9 | 910 | The content of the chapter is not well structured and content appears multiple times. | Clean structure of 6.9 up through establishment of the following outline: "6.9 Deployment scenarios 6.9.1 Wi-Fi router 6.9.2 Residential network 6.9.3 Enterprise network 6.9.4 Public hotspot" Rename headline 6.9.1.2 Home gateway to '6.9.2 Residential network' Remove lines 963-966 Keep lines 967-975 as chapters 6.9.5 and 6.9.6 awaiting further input. | Yes | Max | o.k.
Technical | 37 | 6.9.1.1 | 917 | Insufficient description of 'Wi-Fi router' | Replace lines 917-919 by description given in document omniran-17-0021-00-CF00-deployment-scenario-wi-fi-router.docx | Yes | Max | further revision showing more real circuit uploaded. Use https://mentor.ieee.org/omniran/dcn/17/omniran-17-0021-02-CF00-deployment-scenario-wi-fi-router.docx o.k.
Technical | 38 | 6.9.1.2 | 948 | R5 may not be a physical link | change 'physical links' to 'interfaces' | Yes | Hao | o.k
Technical | 39 | 6.9.1.2 | 949 | Dublicated figure?? | Remove figure at line 949 | Yes | Max | dublicated
Editorial | 38 | 6.9.1.2 | 949 | duplicate figure | delete the figure on P.39 | Yes | Hao | o.k.
Technical | 40 | 6.9.2 | 963 | Missing content for description of enterprise network deployment scenario | Insert description given in document description given in document omniran-17-0022-00-CF00-deployment-scenario-enterprise-network.docx | Yes | Max | for adoption after final review omniran-17-0022-01-CF00-deployment-scenario-enterprise-network.docx o.k.
Technical | 41 | 6.9.2 | 963 | Missing content for description of public hotspot deployment scenario | Insert description given in document description given in document omniran-17-0023-00-CF00-deployment-scenario-public-hotspot.docx | Yes | Max | for adoption after final review o.k.
Editorial | 40 | 6.9.2 | 963 | duplicate texts from L963 to L966 | delete the duplicate texts | Yes | Hao | ok, same as comment #10
Technical | 58 | 7.2.5.2 | 1483 | The requirement here is for the Access Network to have "a valid Certificate to enable the other entities to verify its identity." But it's not clear how the other entities will know this is an authorized entity. Is the intent that authorization is implicit simply because it is signed by the proper CA? This sometimes is not sufficient, because another entity also with a certificate signed by the same CA may be able to act as a man in the middle. Since the CA has a special role in the system, it seems likely that that other entities should be able to verfy that this certificate holder is authorized to be an Access Network device. NOTE: This comment should be applied to other special devices in the system as well where it is stated that they have a certificate to verify identity (e.g., Subscription Service). | Clarify here or elsewhere how another entity can be certain that this is a valid AN certificate (rather than some other entity signed by the same CA). | Yes | Brian | Replace in chapter 7.2 'certificate' by 'credential'
Technical | 62 | 7.2.8 | 1620 | Content missing | Insert mapping to IEEE 802 technologies as given in document omniran-17-0024-00-CF00-chapt-7-2-8-mapping-to-IEEE802-technologies.docx | Yes | Max | o.k
Editorial | 62 | 7.2.8.1 | 1621 | No content available | Remove headline | No | Max | o.k
Editorial | 62 | 7.2.8.3 | 1628 | No content available | Remove the two headlines without content | No | Max | o.k.
Editorial | 67 | 7.3.8.1 | 1809 | Superfluous headline | Remove headline | No | Max | o.k.
Editorial | 68 | 7.3.8.2 | 1815 | No content available | Remove headlines 7.3.8.2 - 7.3.8.5 | No | Max | o.k.
Technical | 69 | 7.4.1 | 1850 | The sentence beginning on this line indicates that only authentication messages are exchanged between the Authenticator and Supplicant. I believe that on 802.3 networks that Network Announcements may also be distributed (and in fact, earlier in the document they seem expected to announce available services.) I'm not sure if there is an analog for wireless networks. | Clarify that EAPOL-based network announcements may also be distributed by the Authenticator when the controlled ports are closed. | Yes | Brian | Change 'authentication messages of the EAP' to 'EAPoL messages' and mention announcement message in this section.
Technical | 69 | 7.4.1 | 1856 | Althought good advice, the motivation for this paragraph is unclear. Presumably the authentication is using a standardized EAP method, which is comprised of a modern and vetted authentication protocol and does NOT do the unsafe practices listed here. | Re-state this paragraph in terms of guidance on the types of safe EAP methods to use. | No | Brian | Change beginning of paragraph 'It is common in IEEE 802 and good practice not to...' Add sentence at end of paragraph 'Current best practise EAP methods are fullfilling these requirements'
Editorial | 75 | 7.4.8.1 | 2036 | Superfluous headline | Remove headline | No | Max | o.k.
Technical | 75 | 7.4.8.1 | 2040 | In the "EAP support" row for 802.11, 802.11i is listed. I believe that 802.11i points to 802.1X for EAP support. | Replace 802.11i with 802.1X in this cell | No | Brian | o.k.
Editorial | 75 | 7.4.8.1 | 2040 | Since "802.11i" has been rolled-up into more recent versions of 802.11 standard shouldn't the table refer to "802.11"? | Replace 802.11i with 802.11 where 802.11i is referenced. | No | Brian | o.k.
Editorial | 75 | 7.4.8.2 | 2041 | No content available | Remove headlines 7.4.8.2 - 7.4.8.5 | No | Max | o.k.
Editorial | 80 | 7.5.3.1 | 2196 | Some of the icons in this and subsequent figures seem to either be actual product icons or are derived from product icons. For example, the blue/black one looks like a well-known consumer DSL router. Are there copyright problems using these icons? | Verify that the icons as safe to use, or replace with stock images that are known to be safe. |  | Brian | Walter will check whether IEEE SA could provide a icon library for use in standards
Editorial | 82 | 7.5.4 | 2230 | I believe "SHOULD" is not proper terminology in IEEE 802 documents. A lower case "should" is taken to be a requirement. | Change SHOULD to should. | Yes | Brian | o.k.
Editorial | 87 | 7.5.8.1 | 2353 | Superfluous headline | Remove headline | No | Max | o.k.
Technical | 87 | 7.5.8.1 | 2356 | No content in table; format not appropriate | Insert mapping to IEEE 802 technologies as given in document omniran-17-0025-00-CF00-chapt-7-5-8-mapping-to-IEEE802-technologies.docx | Yes | Max
Editorial | 88 | 7.5.8.2 | 2357 | No content available | Remove headlines 7.5.8.2 - 7.5.8.5 | No | Max | o.k.
Editorial | 97 | 7.6.8.1 | 2605 | Superfluous headline | Remove headline | No | Max | o.k.
Technical | 97 | 7.6.8.1 | 2606 | Sufficient content missing | Insert mapping to IEEE 802 technologies as given in document omniran-17-0026-00-CF00-chapt-7-6-8-mapping-to-IEEE802-technologies.docx | Yes | Max | Revision https://mentor.ieee.org/omniran/dcn/17/omniran-17-0026-01-CF00-chapt-7-6-8-mapping-to-ieee802-technologies.docx accepted in alignment to the revised contribution https://mentor.ieee.org/omniran/dcn/17/omniran-17-0006-01-CF00-mapping-accounting-and-monitoring-to-ieee-802-technologies.docx
Editorial | 97 | 7.6.8.2 | 2611 | No content available | Remove headlines 7.6.8.2 - 7.6.8.5 | No | Max | o.k.
Editorial | 105 | 7.7.8.1 | 2880 | Superfluous headline | Remove headline | No | Max | o.k.
Editorial | 105 | 7.7.8.1 | 2881 | prefer to mention the relevant chapter number as shown in Table 5. | replace the sentence with the following one copied from DCN17-05-00, 'The following table provides an overview about the functions of accounting and monitoring supported by the various IEEE 802 technologies with some of the references to the related sections of the specifications.' | Yes | Hao | o.k.
Editorial | 107 | 7.7.8.1 | 2884 | duplicated row of 'transmit volume' | delete duplicated rows | Yes | Hao | transmit volume erroneously was put into the header portion'
Editorial | 107 | 7.7.8.1 | 2884 | part of 'QoS parameters' under '802.16' is missing, please find the complete list in the original contribution 17-0006-00. | as in the comment | Yes | Hao | seems to be an editorial issue. Bottom of table fells off the page.
Editorial | 109 | 7.7.8.2 | 2885 | No content available | Remove headlines 7.7.8.2 - 7.7.8.5 | No | Max | o.k.
Editorial | 115 | 7.8.7.1 | 3081 | "FDN" should be "FDM" | Change "FDN" to "FDM" | Yes | Hao | o.k.
Editorial | 120 | 7.8.8.1 | 3225 | Superfluous headline | Remove headline | No | Max | o.k.
Technical | 120 | 7.8.8.1 | 3225 | The whole subclause is mis-copied. | See a separate proposal: omniran-17-0007-01-CF00-mapping-fdm-to-ieee-802-technologies.docx | Yes | Hao | o.k.
Editorial | 125 | 7.8.8.2 | 3236 | No content available | Remove headlines 7.8.8.2 - 7.8.8.5 | No | Max | o.k.
Technical | 142 | 8.3 | 3801 | Missing content | Insert text proposal as given in document omniran-17-0027-00-CF00-Chapt-8-3-Virtual-Network-instantiation | Yes | Max | Replace section by content provided in https://mentor.ieee.org/omniran/dcn/17/omniran-17-0027-03-CF00-chapt-8-3-virtualized-network-instantiation.docx Introduce same coloring as figure 8.3.1 into figure 14 in section 6.7.2