## Slide 1: IEEE 802.1 OmniRAN TG Status Report to IEEE 802 WGs
2018-05-23

## Slide 2: IEEE 802.1 OmniRAN TG Resources
OmniRAN TG page reflecting its status and achievements
  https://1.ieee802.org/omniran/
  Also showing meeting announcements and conference call dial-in information
OmniRAN filespace on mentor is used for contributions and meeting documents
  https://mentor.ieee.org/omniran/documents
Recent P802.1CF D2.0 draft is available by
  http://www.ieee802.org/1/files/private/cf-drafts/d2/802-1cf-d2-0.pdf
FYI: OmniRAN P802.1 PAR
  https://development.standards.ieee.org/get-file/P802.1CF.pdf?t=81644900003

## Slide 3: OmniRAN TG Achievements Pittsburgh, PA meeting, May 21st – 23rd
Progressing P802.1CF
  D2.0 WG ballot resulted in 95% approval
    105 comments received, 11 binding
  D2.0 comment resolution and development of remedies for nearly all comments
    Major open to add additional information on the function specific attributes.
    Several figures have to revised through adjusting NMS to Network Management System
Estimated timeline for P802.1CF with extended scope:
  Sponsor Ballot intended after Jul 2018
Progressing P802.1CQ
  2 contributions reviewed
  Major discussions on impact on wireless technologies
Discussion of contributions to IC NEND
  Review of draft report on industrial IoT reviewed to provide hints adding information and revision prior to presentation to Nendica

## Slide 4: Looking forward to next session in San Diego, CA, July 9-12, 2018
Envisioned topics:
  Comment resolution of comments on P802.1CF D2.1
  Prepare for sponsor ballot initiation after July F2F
  Discussions on P802.1CQ
  Potentially, review of intended submissions to Nendica
Upcoming conference calls:
  June 5th , 0930AM ET, 1hr
    1CF Review of open remedies
    1CF Review and completion of documentation of proposed disposition
    1CQ discussions depending on input
  June 11th, 0930AM ET, 1hr
    1CF Final review of D2.1 in preparation of WG ballot recirculation
    1CQ discussions depending on input
Next WG ballot recirculation:
  Start latest at June 18th with closure on July 3rd