## comments
Comment # | Name | Affiliation | Category | Page | Subclause | Line | Comment | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Hints to editor
i-47 | Montemurro, Michael | BlackBerry | Technical | 17 | 4.1 | 477 | The use of the BSS acronym is a bit confusing for a reader with an IEEE 802.11 background. Since BSS in IEEE 802.11 stands for Basic Service Set and BSSID and HESSID are used in this document. | Yes | Change the Business Supporting System to something different llkk BUS | Revise | In the text, BSS is never used as standalone acronym, but always in combination with OSS, i.e. either OSS/BSS or rarely BSS/OSS. Acronym list will spell out BSS as Basic Service Set and in addition OSS/BSS for Operation Supporting System/Business Supporting System. #ed# change fig 92, 94, 95, 96 to OSS/BSS ## | Acronyms: 1. Change BSS to Basic Service Set 2. Remove OSS Operation Supporting System 3. Add OSS/BSS Operation Supporting System/Business Supporting System 4. Replace/revise figures 92, 93, 94, 95, 96
i-46 | Montemurro, Michael | BlackBerry | Technical | 23 | 5.3.1.1 | 620 | The TE subclause should make a reference to terminal control somewhere in its description. | Yes | Add a statement about TEC and how it facilitiates interaction with a client. In siome cases, terminal control may be performed out-of-band. There may even be co-ordinatoin between the TEC and the SS. | Revise | Amend text of section 5.3.1.1 by - L622: replace 'particular' in front of parameters by 'the'. - L623: add after the text '... Interfaces to ANC and SS for establishment and maintenance of the network connectivity. Some terminal configurations may be performed out-of-band through a user interface or other means.' | <---
i-45 | Montemurro, Michael | BlackBerry | Technical | 24 | 5.3.1.5 | 640 | I believe the paragraph defining the subscription service provides a means to ensure that a client, once provisioned can authenticate succesfully to the AN. | Yes | Update the subscription service description noting that the SS has a role in provisioning. If there isn't any, note that provisionng is beyond the scope of this document. | Revise | Add following text starting at full stop in L642: ", and potentially means to provision terminals to enable successful authentication." | <---
i-48 | Montemurro, Michael | BlackBerry | Technical | 30 | 5.8.1 | 797 | For a virtualized IEEE 802 access network, what are the assumptions on the terminal. | Yes | I believe the simplest assumption is that the terminal can discovver multiple virtual networks but selects and connects to only one of the mulitple virtual networks. Update the assumptions for the terminal | Revise | Add following text starting at a new line after L800: "The terminal has not to be aware of virtualized AN. The interface to the terminal does not change through virtualization." | <---
i-49 | Montemurro, Michael | BlackBerry | Technical | 36 | 5.9.1 | 900 | "fast roaming" is called "fast BSS transition" in IEEE 802.11 | Yes | Change "fast roaming" to "Fast BSS-Transition" at cited location. | Accept
i-50 | Montemurro, Michael | BlackBerry | Technical | 45 | 5.9.6 | 1092 | For Hotspot 2.0, likely "Wi-Fi CERTIFIED Passpoint should be used and there should be a reference to the Wi-Fi Alliance description of the technology. | Yes | Change "Hotspot 2.0" to "WI-FI CERTIFIED Passpoint^TM" and add a footnote with a reference to the following URL"https://www.wi-fi.org/discover-wi-fi/passpoint" | Accept
i-31 | Petry, Brian | Broadcom Corporation | Technical | 45 | 5.9.6 | 1092 | The document references "Hotspot 2.0". This is an obsolete Wi-Fi Alliance term. | Yes | The document should reference Wi-Fi Alliance Passpoint and should include an informative reference to the Wi-Fi Alliance specifications. | Revise | Change "Hotspot 2.0" to "WI-FI CERTIFIED Passpoint^TM" and add a footnote with a reference to the following URL"https://www.wi-fi.org/discover-wi-fi/passpoint" #ed# same as comment i-50 # | Duplicate to i-50
i-32 | Petry, Brian | Broadcom Corporation | Technical | 46 | 5.9.6 | 1111 | The reference model fixes the R3 and R5 reference points before (to left of) access gateway and IP services. However, a trend of Wi-Fi public hotspot and even small enterprise deployments is to locate control and captive portal services further to the right, even on the other side of an IP network. Known as "cloud managed Wi-Fi". It seems throughout D2.2 (not just in the Wi-Fi deployment scenarios, cloud-managed networks are not accommodated by the reference model. | Yes | It seems specific change proposals would be too big to fit here, because the base reference model and descriptions throughout the document in a pervasive sense, to address cloud-managed networks. | Revise | There are many flavors of cloud managed Wi-Fi solutions. 802.1CF is applicable to cloud managed Wi-Fi solutions in the defined scope of IEEE 802 technologies, i.e. performing control of layer 2 and beneath. The applicability of 802.1CF to cloud managed Wi-Fi will be described in a amendment to 5.9.3 Enterprise network. as provided through https://mentor.ieee.org/omniran/dcn/18/omniran-18-0078-00-CF00-d2-2-cid32-remedy-proposal.docx | Insert amendments to 5.9.3 provided through https://mentor.ieee.org/omniran/dcn/18/omniran-18-0078-00-CF00-d2-2-cid32-remedy-proposal.docx btw: svg-figure was slightly amended for better differentiation of cloud
i-33 | Petry, Brian | Broadcom Corporation | Technical | 46 | 5.9.7 | 1128 | The whole section proposes il-contrived solutions. The document should not propose new solutions, but just show how the reference model applies to deployment models. For instance, the document does not describe Wi-Fi network (SSID) virtualization for a single AP (sometimes called Virtual AP--VAP--or multi-BSSID). The document does not describe the scenario that home users are likely to replace their Wi-Fi AP/Router more frequently than their IOT devices. | Yes | Delete the whole section, or vastly simplify it to just explain how the NRM applies to IOT Wi-Fi devices. | Revise | The presented solution is subject of a project of Wi-Fi Alliance called 'Managed Residential IoT Connectivity (https://www.wi-fi.org/who-we-are/current-work-areas)'. The section shows how 802.1CF provides an architectural model for such kind of widely encouraged deployments. The virtualization of a single 802.11 AP is already mentioned in section 5.8. To describe the missed case that CPEs might be more frequently replaced than IoT devices, 5.9.7 will be amended by a description referencing remote CPE configuration and management. (https://mentor.ieee.org/omniran/dcn/18/omniran-18-0079-00-CF00-d2-2-cid30-33-remedy-proposal.docx). #ed# Add references to TR-069 and TR-181 to the bibligraphy ## | 1. Insert amendments to 5.9.7 provided through https://mentor.ieee.org/omniran/dcn/18/omniran-18-0079-00-CF00-d2-2-cid30-33-remedy-proposal.docx 2. Renew figure 25 through F25-22_vWLAN4IoT-scenario.svg ('CPE' added) 3. Add to bibliography references to BBF TR-069 and BBF TR-181
i-51 | Montemurro, Michael | BlackBerry | Technical | 51 | 6.1.1 | 1264 | There should be some reference to terminal provisioning somewhere. Terminals cannot connect if they are not provisoined somehow. Particularly if you are deploying a secure solution. | Yes | Add a description to address how provisining is handled, even if its simply to state that it can be done out-of-band and is beyond the scope of this document. | Revise | Clause 6.2 is the more appropriate place to introduce terminal provisioning aspects. Replace the sentence starting in L1680 by: "To facilitate a terminal to process the necessary procedures for selecting and establishing network access, local configuration and policy data has to be provisioned beforehand from the subscription service. The provisioning is usually performed by means out-of-band and therefore beyond the scope of this document." | <---
i-34 | Petry, Brian | Broadcom Corporation | Technical | 54 | 6.1.4.3 | 1390 | Channel selection and re-selection procedures allow the network (ANC) to force or steer terminals (NA) to different radio channels and different ANCs (APs) within the same Access Network. It seems the detailed discussion about channel selection and re-selection should be outside the scope the document. Also, the language and reference model do not fit with newly developing standards in the Wi-Fi alliance, such as "Optimized Connectivity Experience (OCE)." | Yes | Remove section 6.1.4.3 and 6.1.4.4 and just refer to the possibility of channel selection and re-selection by the terminal or driven by the network. | Revise | Remove text of section 6.1.4.3 and 6.1.4.4. New text under 6.1.4.3 Channel selection: "Channel selection is part of NA initialization to tune each of its radio to a designated channel on the unlicensed band. Each NA should preferably select a non-overlapping channel either autonomously or following instructions from ANC. Each NA should be able to determine and to report all the channels on which one or more over-lapping NAs or terminals are operating. The algorithm used by the NA to select the channel is beyond the scope of this specification." New text under 6.1.4.4 Channel re-selection: "The NA may re-select another channel for operation either autonomously or following instructions from ANC. Switching to that channel will cause its connected terminals to lose connectivity temporarily. The algorithm used by the NA to re-select the channel is beyond the scope of this specification." | Edits contained in remedy to i-36
i-35 | Petry, Brian | Broadcom Corporation | Technical | 58 | 6.1.7 | 1518 | Detailed procedures (6.1.7) for Access Network Setup (6.1) seem out of scope for this document. This document should recommend any details about operating in unlicensed spectrum or provide guidance about how a radio network should behave in this manner. If standards are available for various radio networks (including Wi-Fi or other), they should just be referenced. Also, 6.1.7 seems to be focused on radio networks and not wired networks. Wired networks have similar issues about setup procedures. | Yes | Delete section 6.1.7 or provide references to radio network standards. Include information about wired access networks. | Revise | The comment is ambiguous and may express 'should _not_ recommend any details about operating in unlicensed spectrum', to which the CRC agrees. As unlicensed spectrum is not mentioned in text of 6.1.7.1, the title should be rephrased to 'Access network set-up procedure' applicable to wired networks as well. | Edits contained in remedy to i-36
i-52 | Montemurro, Michael | BlackBerry | Technical | 63 | 6.1.8 | 1642 | Technically with IEEE 802.11-2016, IEEE 802.11af no longer exists. | Yes | Change IEEE 802.11af to IEEE 802.11 TVWS | Accept |  | Edits contained in remedy to i-36
i-53 | Montemurro, Michael | BlackBerry | Technical | 64 | 6.2.1 | 1664 | A terminal needs to be provisioned to discover a subscriber. | Yes | Change "A terminal belonging to a subscriber of service" to "A terminal provisioned for service" | Accept
i-36 | Petry, Brian | Broadcom Corporation | General |  |  |  | Generally, the recommendation is too detailed and too big to be consumed, followed and adopted effectively by future standards. Consider removing text that describes details about internal workings, especially those of radio networks. And instead focus only on the reference points of the model. To meet a goal of the PAR, that the recommendation actually be used by the community and future standards, I strongly feel the document needs to be greatly simplified. | Yes | Delete and rework about 1/3 to 1/2 of the document that describes details that don't relate directly to the reference model. | Revise | The specification is very focused on the scope defined in the PAR: defining a Network Reference Model and providing functional description of messaging between functional entities of the NRM across the reference points. A highly orthogonal structure reapplying the same outline for all the subsections was chosen for the functional description clause, which details the messaging across the reference points. The approach enables addressing multiple IEEE 802 technologies and flexible deployments in a single text with clear alignment to normative specifications in subsections of various IEEE 802 standards. Some additional simplification of the main body was achieved by removing the authorized spectrum management procedures used in IEEE 802.11 TVWS, IEEE 802.19.1, and IEEE 802.22 from the main body and moving them into an annex. #ed# editorial information for the move of authorized spectrum functions to annex ## | Apply split of clause 6.1 into a much smaller 6.1 and an additional Annex A (normative) according to https://mentor.ieee.org/omniran/dcn/18/omniran-18-0077-01-CF00-d2-2-cid36-remedy-proposal.docx Increment previous annexes to B (informative), C (informative), and D (informative) and correct reference in line 533 to 'Annex B'
i-1 | Obara, Satoshi | FUJITSU | General |  |  |  | The term "Network Management System" is too much general. In this document, this "Network Management System" only covers "Access Network". Then, this term should be changed into more accurate term. | Yes | In the enire documents, "Network Management System" and "NMS" should be changed into "Access Network Management System" and "ANMS". | Revise | Agreed, that the document demands a more precise description of the meaning of NMS in the scope of the specification. The term 'NMS' is not limited to one particular implementation, but is a general term for various kinds of Network Management Systems. In IEEE 802 'NMS' it is used to describe the operation, administration and maintenance of IEEE 802 networks, e.g. IEEE 802.1AB definess: 'Network Management System (NMS): A management system that is capable of utilizing the information in a MIB.' In P802.1CF, the NMS does not only manage the IEEE 802-based network elements of the access network, but also the IEEE 802 interfaces of Terminal (TE) and Access Router (AR). Therefore, the term 'Access Network Management System' would not be appropriate. Instead of using another term, which may be misleading to experienced IEEE 802 experts (we had such comment in the WG letter ballot phase to resolve), the scope of 'NMS' in P802.1CF will be further detailed through amendments in the text: 1. L612: Add to the end of the sentence: "..and the IEEE 802 interfaces with the TE and AR" (resulting in 'The NMS comprises the services for operation, administration, and maintenance of the IEEE 802 access network and the IEEE 802 interfaces with the TE and AR.') 2. L648: Insert after 'network elements': ".. and between access network and TE and AR," (resulting in 'The Network Management System consists of the functions that allow the operator of an access network to configure the access network infrastructure, manage functions related to the interaction between multiple network elements and between access network and TE and AR, monitor the usage and correct operation of the access network, and to perform tests for detection, determination and correction of faults.') | 1. L612: Add to the end of the sentence: "..and the IEEE 802 interfaces with the TE and AR" (resulting in 'The NMS comprises the services for operation, administration, and maintenance of the IEEE 802 access network and the IEEE 802 interfaces with the TE and AR.') 2. L648: Insert after 'network elements': ".. and between access network and TE and AR," (resulting in 'The Network Management System consists of the functions that allow the operator of an access network to configure the access network infrastructure, manage functions related to the interaction between multiple network elements and between access network and TE and AR, monitor the usage and correct operation of the access network, and to perform tests for detection, determination and correction of faults.')
i-30 | Lepp, James | BlackBerry | Technical | 46 | 5.9.7 | 1128 | Remove all instances of the term IoT from section 5.9.7. IoT stands for "Internet of Things" (which happens to be not defined in this document) and the main point of the Virtualized network described in this section is to segregate these devices on a separate network which does not have access to the Internet. How then are they IoT devices then? | No | Change all instances of the term IoT to "non-internet" or something that conveys the devices are not connected to the public Internet. | Revise | The described deployment scenario addresses the secure deployment of 'IoT' devices, which are based on Internet protocols and aimed for operation in the Internet. The described deployment does not change the nature of the devices. To better explain the intention of the virtual access network to protect common IoT devices from attacks from the Internet through a virtualized access network without need for any changes to the devices a statement will be added after line 1158: "The IoT devices still use Internet protocols for communication, but their communications are restricted within a virtual private network to mitigate the risks of the public Internet." ##ed#Edits ontained in https://mentor.ieee.org/omniran/dcn/18/omniran-18-0079-00-CF00-d2-2-cid30-33-remedy-proposal.docx# | Edits contained in remedy to i-30
i-41 | Riegel, Maximilian | Nokia | Technical | 49 | 5.9 | 1212 | Important Fog deployment scenario missing. Fog computing is an emerging technology which benefits from application of P802.1CF. A Fog node based on Ethernet connectivity can be represented of a Terminal containing one or more instances of a virtual computing instance like a VM or container. P802.1CF can be applied to model such distributed system. | No | Insert a new clause 5.9.8 describing the application of P802.1CF to model the network architecture of a Fog computing system. Document omniran-18-0069-00-CF00-fog-deploymdent-scenario.docx contains a proposal for the text of the subclause. | Accept |  | Insert new clause 5.9.8 according to https://mentor.ieee.org/omniran/dcn/18/omniran-18-0069-00-CF00-fog-deployment-scenario.docx
i-37 | Furuichi, Sho | Sony Corporation | Technical | 53 | 6.1.2.7 | 1347 | In Europe, current spectrum usage information (operating frequency channel and power) is required to send to database. Therefore, the information in CIS should include it. | No | Add new bullet for current spectrum usage information. | Revise | Change L1351 into " - current spectrum usage information" | Edits contained in remedy to i-36
i-38 | Furuichi, Sho | Sony Corporation | Technical | 53 | 6.1.2.7 | 1348 | "available bands" is unclear. And, the difference from the next bullet is also unclear. Does this bullet says capability or supporting band? | No | Clarify it. | Revise | Line 1348 and L1349 essentially address the same; therefore delete L1348. | Edits contained in remedy to i-36
i-42 | Riegel, Maximilian | Nokia | Technical | 80 | 6.4.2 | 2238 | The representation and description of 'user' in the section indicates that user is always a human being. Such indication is misleading and may limit the acceptance of the model for deployments where terminals are IoT devices, Fog nodes or machinery belonging to a factory floor. | No | Emphasize that 'user' represents any kind of entity being in charge for requesting and gaining access to a communication infrastructure through the following modifications: - Replace the human representation in figure 40 through a geometric shape representing an entity, e.g. a circle - Add at the end of line 2238: 'User denotes the entity being in charge of enabling network access to a terminal through establishment of an appropriate agreement (contract) with a service provider.' | Revise | Replace sentence starting L2253 with "User denotes the entity being in charge of enabling network access to a terminal through establishment of an appropriate agreement (contract) with a service provider" and revise shape of human being in figure 40 with geometric shape. | 1. Replace sentence starting L2253 with "User denotes the entity being in charge of enabling network access to a terminal through establishment of an appropriate agreement (contract) with a service provider" 2. Replace figure 40 by F40-22_Authentication-architecture.svg
i-39 | Furuichi, Sho | Sony Corporation | General | 178 | Bibliography | 4810 | Standard number is wrong. ".1" is missing. | No | 802.19.1-2014 | Accept
i-40 | Furuichi, Sho | Sony Corporation | General | 178 | Bibliography | 4811 | Draft Standard should not be used as reference. | No | Remove | Accept
i-4 | Webb, Stephen | INDEPENDENT | General | 1 |  |  | Very nicely done | No |  | Accept
i-43 | Montemurro, Michael | BlackBerry | Editorial | 22 | 5.2.2 | 589 | Shouldn't "information" be capitalized? | No | change "information" to "Information" | Revise | Maintain consistent style in figure, therefore keep small letter for 'information' but change in figure 3 IEEE 802 Network Management into 'IEEE 802 network management' | Replace figure 3 by F03-22_Ref-point-types_rev.svg
i-44 | Montemurro, Michael | BlackBerry | Editorial | 23 | 5.3 | 605 | The components are capalized in Fig 4 but not in the paragraphs below. | No | Decide the capitalization requirements and be consistent in the figure and the text. | Revise | Use capital letters in sentence starting line 609 for elements appearing in the figure above, like in sentence starting on L612. | <---
i-3 | Wang, Hao | FUJITSU | Editorial | 26 | 5.5.2 | 722 | 'user plane' is the same as 'data plane'? | No | There are several occurances of 'x plane', maybe more explaination on these 'planes' is needed | Revise | Use consistently 'data plane'; replace 'user' plane by 'data plane' in footnote following L581, L722, and L2427. Introduce lower case in L4300. | <---
i-5 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 52 | 6.1.2.2 | 1303 | typo in "kind" | No | should be "kinds" | Accept
i-6 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 63 | 6.1.8 | 1642 | missing word between "support operations in" | No | should be "support operations exist in" | Accept
i-7 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 68 | 6.2.5.4 | 1806 | missing word after "by attributes such" | No | should be "by attributes such as" | Accept
i-8 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 76 | 6.3.6.2 | 2119 | wrong word in "is send to" | No | should be "is sent to" | Accept
i-9 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 76 | 6.3.6.3 | 2129 | wrong word in "message send" | No | should be "message sent" | Accept
i-10 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 76 | 6.3.6.3 | 2132 | wrong word in "any further message" | No | should be "any further messages" | Accept
i-11 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 77 | 6.3.7.2 | 2153 | wrong word in "which send the" | No | should be "which sends the" | Accept
i-12 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 80 | 6.4.1 | 2233 | wrong word in "and provisioning of right" | No | should be "and provisioning of the right kind" | Accept
i-13 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 84 | 6.4.7.1 | 2387 | wrong words in "to terminal by access" | No | should be "to the terminal by the access" | Accept
i-14 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 86 | 6.5.1 | 2443 | missing word in "configured when" | No | should be "configured when the" | Accept
i-15 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 97 | 6.5.6.7 | 2768 | wrong word in all caps "ANC MAY" | No | should be "ANC may" | Accept
i-16 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 109 | 6.6.7.1 | 3105 | missong words in "for certain times" | No | should be "for certain amount of times" | Revise | "a number of times" | <---
i-17 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 110 | 6.6.7.2 | 3110 | missing word in "flow initialization by terminal" | No | should be "flow initialization by the terminal" | Accept
i-18 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 110 | 6.6.7.2 | 3123 | missing word in "flow initialization by terminal" | No | should be "flow initialization by the terminal" | Accept
i-19 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 111 | 6.6.7.3 | 3136 | missing words in phrase | No | should be "AR should reply with a service flow addition ack, and ANC will send a SF..." | Accept
i-20 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 112 | 6.6.7.5 | 3156 | missing space between "terminal.Terminal" | No | should be "terminal. Terminal" | Accept
i-21 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 120 | 6.7.7.2 | 3429 | missing word in "otward specific user" | No | should be "toward a specific user" | Accept
i-22 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 136 | 6.8.7.3 | 3794 | missing word in "When report condition" | No | should be "wWhen the report condition" | Revise | "When the report condition" | <---
i-23 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 138 | 6.8.7.4 | 3832 | missing word in "ANC sends request" | No | should be "ANC sends a request" | Accept
i-24 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 155 | 7.2.4.1 | 4122 | wrong word in"validates and verify" | No | should be "validates and verifies" | Accept
i-25 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 157 | 7.2.4.3 | 4167 | Inclomplete Figure, missing the provider and operator text | No | should have "Infrastructure Provider" and "Access Network Operator" at the top of the signalling diagram | Accept
i-26 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 167 | B.1.4.1 | 4457 | wrong word in "considering what parameters" | No | should be "considering which parameters" | Accept
i-27 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 167 | B.1.4.2 | 4479 | wrong word in "should be consider in order" | No | should be "should be considered in order" | Accept
i-28 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 169 | B.1.4.9 | 4569 | duplicated article in "ther is a currently a " | No | should be "there is currently a" | Accept
i-29 | Corujo, Daniel | Instituto de Telecomunicacoes | Editorial | 177 | C.1.3 | 4782 | When this section refers to "NFV Layer" it is not clear if it is referring to a generic NFV layer, or to one of the three layers presented in figures 106 and 107 (NFVI Layer, VNF Layer and Service Layer". The confusion is caused because the figures do not indicate a "NFV Layer", but it is referrenced in this text. | No | The text should be changed to reflect a specific layer pointed out in the figures, or to refferr to NFV as just NFV. | Revise | L4782: Change "NFV layer"into "VNF layer" | <---
i-2 | Alessi, Julie |  | Editorial |  |  |  | Draft meets all editorial requirements. | No |  | Accept