## TIMELINE
Revised and Updated 17JUN2013
IEEE Timeline | STATUS | MAY | JUNE | JULY | AUG | SEPTEMBER |  |  |  | OCT | DEC
Form Sponsor Ballot Pool -start may 15 end june 20 | PENDING | 2013-05-15 | 2013-06-15
Announce first WG meeting | complete | 2013-05-15
Hold first WG meeting |  |  | 2013-06-17
At WG meeting approve normal SA operating P&P
At WG meeting conduct call for essential IP
Start Sponsor Ballot |  |  |  | 2013-07-01
Complete first ballot |  |  |  |  | 2013-08-01
Complete initial Comment Resolution. | [5 empty] | 2013-08-15
Complete first recirc | [6 empty] | 2013-09-01
Comment Resolution | [7 empty] | 2013-09-15
Start 2nd recirc of an unchanged draft. | [7 empty] | 2013-09-15
Complete 2nd recirc and Sponsor Ballot. | [8 empty] | 2013-09-30
Submit to IEEE RevCom for consideration at the Dec 8 meeting - submission deadline | [9 empty] | 2013-10-21
Standards Board approval | [10 empty] | 2013-12-11

## ASSUMPTIONS
o we have a motivated friendly WG attendance of Corp Members in Athens who then become the voting members ( strongly in our control).
o we have a reasonable Sponsor Ballot pool (the one area where we have the least control other to encourage friendly's to accept the invitation to ballot)
o we get the requisite 75% on the first ballot- reasonable that we will if we have encouraged the right participation
o we have relatively few comments seeking to modify the technical aspects of the draft and that rejecting those comments will be supported by the super majority of the ballot pool. ( we will get a very good indicator of that based in initial voting results)
o we take best advantage of the IEEE SA P&P.